## Notes (hidden)
From 1 Nov 2014 - SARS start phasing out paper tax clearance certificates
From 1 April 2015 - No paper TCC but a PIN0 from SARS

## Menu
Department of Public Works
General Conditions of Contract for Construction Works - 2nd Edition (2010)
Click onto the buttons below to make your selection.
In terms of Preferential Procurement Regulations, 2022
Print : | Print coloured Title Pages:
Disclaimer: Each person that downloads this file does so at their own peril and discretion. This document is compiled as a courtesy to other users and each person is still responsible to ensure that their document complies in all respects with the requirements of the client. Each user must ensure that they proof read their completed document and correct any patent errors that might have been in the downloaded file. The compiler of this file does not accept any responsibility for any mistake or error once this file is downloaded and populated by the user. It is also not the compiler of this file's responsibility to ensure that this file is updated or that this file contains the latest statutory requirements in terms of CIDB or the Government.
Please do a print preview before printing. To do this click onto the Enter Bid Data button above. Then click onto the button of the document you want to go to and click onto the Print Preview button. Note that you can use the Page Break Preview to adjust the page breaks.
Click here to Enter Bid Data
Click here to Print PART T1 - BID PRODECURES
Click here to Print PART T2 - RETURNABLE DOCUMENTS
Click here to Print PART C1 - AGREEMENT AND CONTRACT DATA
Click here to Print PART C2 - PRICING DATA
Click here to Print PART C3 - SCOPE OF WORKS
Click here to Print PART C4 - SITE INFORMATION
Click here to Print DRAWINGS / ANNEXURES
PART T1 - BID DATA - Pink Page
PART T2 - RETURNABLE DOCUMENTS - Yellow Page
PART C1.1 FORM OF OFFER & CONTRACT DATA
- Yellow Pages
PART C2 - PRICING DATA - Yellow Page
PART C3 - SCOPE OF WORKS - Blue Page
PART C4 - SITE INFORMATION - Green Page
Click here to Go to a particular Document

## Advert
HEAD OFFICE - PIETERMARITZBURG
Notification of tender
The KZN Department of Public Works: Head Office invites tenders for the following service:
| DESCRIPTION OF SERVICE: |  |  |  | KZN Public Works: 191 Prince Alfred Street
| WIMS NUMBER: |  |  |  | 012345
| tender NUMBER /QUOTATION NUMBER: |  |  |  | ZNTM012345W
| CIDB GRADING |  |  |  | 6SF
| CONSTRUCTION PERIOD: |  |  |  | 19 Calendar Months
| CLOSING DATE: |  |  |  | As Per Tender Advert
| TIME: |  |  |  | 11:00
| TENDER VALIDITY PERIOD: |  |  |  | 84 Calendar Days
| DOCUMENTS AVAILABLE FORM: |  |  |  | tender documents are avaliable from 10 Prince Alfred Street, Pietermaritzburg,, 3200. These will only be handed out on receipt of payment of the required deposit.
| COST OF tender DOCUMENT: |  |  |  | A non-refundable payment of R450 must be made for collection of this document to the following banking details & proof of thereof must be produced upon collection:
| Bank Name: |  |  |  | KZN PROV GOV-WORKS
| Bank: |  |  |  | STANDARD BANK
| Account No: |  |  |  | 052106446
| Account Type: |  |  |  | BUSINESS CHEQUE ACCOUNT
| Branch: |  |  |  | 057525
| Reference Number: |  |  |  | Ref No 14019647
| TENDER CLOSE AT: |  |  |  | , Southern Region, Southern Region Office, 10 Prince Alfred Street, Pietermarizburg, 3200
ENQUIRIES:
| Enquiries relating to tender document may be directed to: |  |  |  |  | Mr. Khumalo
| Contact Number: tender Document: |  |  |  |  | 033-897 1421/1422
COMPULSORY SITE BRIEFING:
| DATE: |  |  |  | As per Tender Advertisement
| TIME: |  |  |  | 11:00
| VENUE: |  |  |  | As per Tender Advertisement
| TECHNICAL ENQUIRIES: |  |  |  | [Identify the Company or person]
[Telephone Number including Area Code]
[Fax Number including Area Code]
[Email Address]
EVALUATION CRITERIA
tenders will be evaluated firstly in terms of the functionality criteria stipulated in the tender document before assessment in terms of price and preference. tenderders must meet the minimum qualifying score of 50 for functionality before assessment in terms of price and preference can be considered.
tenders will be evaluated in terms of the applicable procurement legislation, 80/20 preference point system as per the Preferential Procurement Regulations of 2011 issued in terms of section 5 of the Preferential Procurement Policy Framework Act of 2000.
Preference points for this tender shall be awarded for:
|  | (a) | Price; and
|  | (b) | B-BBEE Status Level of Contribution
In terms of Regulation 5 (2) and 6 (2) of the Preferencial Procurement Regulations, preference points will be awarded to a tenderder for attaining the B-BBEE status level of contribution in accordance with the table below:
Points Awarded for B-BBEE Status Level of Contribution
| B-BBEE Status Level of Contributor |  |  |  | Number of points (80/20 system)
| Level 1 |  |  |  | 0
| Level 2 |  |  |  | 0
| Level 3 |  |  |  | 0
| Level 4 |  |  |  | 0
| Level 5 |  |  |  | 0
| Level 6 |  |  |  | 0
| Level 7 |  |  |  | 0
| Level 8 |  |  |  | 0
| Non-compliant contributor |  |  |  | #REF!
tenderders to Note that:
| 1. | A non-refundable deposit of R450 is payable for collection of this document to the following banking details and proof of deposit must be produced upon collection at the briefing session:
|  | Bank Name: |  | KZN PROV GOV-WORKS
|  | Bank: |  | STANDARD BANK
|  | Account No: |  | 052106446
|  | Account Type: |  | BUSINESS CHEQUE ACCOUNT
|  | Branch: |  | 057525
|  | Reference Number: |  | Ref No 14019647
Please note no payment will be accepted at the site isnpection / briefing meeting.
| 2. | A PDF copy of the completed tender document together with all supporting documents and the Complete Priced Bill of Quantities must be submitted on a readable compact disc together with the tender at time of close of the tender.
| 3. | Late submissions will not be accepted.
| 4. | Faxed or e-mailed tenders are not acceptable.
| 5. | Only tenderders registered on the Provincial Suppliers Database and within the applicable CIDB grading or with the relevant JV will be eligible to submit tenders.
| 1. | Requirements for sealing, addressing, delivery, opening and assessment of the tender are contained in the tender document.
| 2. | The Department reserves the right not to award to the lowest tenderder.
| 3. | In addition, the Department will conduct a detailed risk assessment prior to the award of the tender.
| 4. | Tender documents must be purchased prior to the starting time of pre tender briefing meeting. No tender documents will be issued at the pre tender briefing meeting and no site inspection meeting certificates will be issued at the pre tender briefing meeting.
| 5. | tenderders who attend without a tender document will not be allowed to the briefing.
| 6. | No late arrivals will be admitted to the pre tender briefing meeting.
| 7. | Submission of a PDF copy of the completed tender tender document together with all supporting tender. | documents must be submitted on a readable compact disc together with the bid at close of tender.
| 8. | Late submissions will not be accepted.
| 9. | Faxed or e-mailed tenders are not accepted.
| 10. | Only tenderders registered on the Central Suppliers Database and within the applicable CIDB grading 6SF or higher will be legible to submit tenders/quotations.
| 11. | This project is subjected to the CIDB Best Practice Standards (Compiler to list the standard)
Project Code: / 012345 / ZNTM012345W / KZN Public Works: 191 Prince Alfred Street
PROPOSED PROCUREMENT PROGRAMME
| Submission to BSC: |  |  | 2014-08-09
| BSC Meeting: |  |  | 2014-08-16
| Advertisement: |  |  | 2014-08-30
| Compulsory Site Meeting Briefing: |  |  | As per Tender Advertisement
| Closing: |  |  | 2014-09-30
| Tender Adjudication: |  |  | 2014-09-30 |  | to | 2014-10-30
| Estimated Site Hand Over: |  |  | 2014-11-29 12:00
| Estimated Completion: |  |  | 2016-06-12

## Master Data
Provincial Administration of KwaZulu-Natal
DEPARTMENT OF PUBLIC WORKS & INFRASTRUCTURE
GCC2010 DATA TENDER INPUT SHEET
Please complete the areas in blue including drop downs below :
Areas in black are calculated automatically once the areas in blue are filled in.
A. TENDER DATA
For Planning Purposes only
|  | Client | KZN Department of Public Works |  |  |  | KZN Department of Public Works |  | Submission to BSC: | 2014-08-09
|  | Tender No | ZNTM012345W | Project Code: | 012345 |  |  |  | BSC Meeting: | 2014-08-16
|  | Classes of Construction works | [6 empty] | Advertisement: | 2014-08-30
|  | Is this an EPWP project? | 2 | EPWP No (If Applicable) | N/A |  |  |  | Compulsory Site Meeting Briefing: | As per Tender Advertisement
[9 empty] | Closing: | 2014-09-30
|  | Institution: | MOSVOLD HOSPITAL
|  | Project Title | KZN Public Works: 191 Prince Alfred Street | [5 empty] | Tender Adjudication: | 2014-09-30 |  |  | to | 2014-10-30
|  | Estimated Including VAT | 20000000 | CIDB Grading | 6SF |  |  |  | Estimated Site Hand Over: | 2014-11-29 12:00
[9 empty] | Estimated Completion: | 2016-06-12
|  | Site (Property title deed description) | Region: District Municipality: Local Municipality: Ward Nr.: Cluster Nr x: | [5 empty] | Contract Period: | 19 |  |  | Calendar Months |  | 19
|  | Closing Date | As Per Tender Advert | Closing Time | 11:00
|  | Advertisement Date | To be determined | Validity Period (Days) | 84 | Calendar Days
|  | Tender Fee | 450 | Price Preference Ratio | 80
|  | Functionality: (Points) Threshold score should be between 50% and 60%. | 50
|  | Banking Details | Bank Name: | KZN PROV GOV-WORKS
|  |  | Bank: | STANDARD BANK
|  |  | Account No: | 052106446
|  |  | Account Type: | BUSINESS CHEQUE ACCOUNT
|  |  | Branch: | 057525
|  | Reference Number: | Ref No 14019647
|  | Preference Points for SPECIFIC GOAL/S |  | 20 | Maximum points
|  | Price: (Points) |  | 80
|  | Functionality: (Points) | 50 | 50
TENDER DATA INPUT
|  | F.2.13.1 - Tenderers may offer tenders for the following: |  | 1
|  | F.2.18 - Number of Days to submit priced Bill of Quantities |  | 2
|  | F.2.18 - Do you require tenderder to submit priced Bill of Quantities with tender? |  | 1
|  | Site Inspection | 1
|  | Site Inspection Date | As per Tender Advertisement |  |  | or if you don't know the date say "As per Tender Advertisement"
|  | Site Inspection Time | 11:00
|  | Site Inspection Meeting location and time | As per Tender Advertisement
|  | Location for collection of tender | 5
|  | Location for opening of tender | 5
|  |  |  | Alternative tender offer permitted |  |  | 1
|  | Standard for Developing Skills (COMPILER TO NOTE: ONLY ONE STANDARD CAN APPLY TO THIS PROJECT) | The contractor shall achieve in the execution of this contract the Contract Skills Development Goal (CSDG) established in the Standard for Developing Skills through Infrastructure Contracts (Published in Government Gazette No 48491) |  | No
|  |  | The contractor shall achieve in the execution of this contract the Contract Participation Goals (CPG) relating to the engagement of targeted enterprises as established in the CIDB Standard for Indirect Targeting for Enterprise Development through Construction works Contracts Published in Government Gazette No 48491) |  | Yes
|  | Standard Procurement Procedure | 2 | [7 empty] | Departmental Procurement Circ 8 of 2010
|  | Type of Procedures | 2 | [7 empty] | 2014-12-01
|  | Contracting Strategy | 2
2
|  | (If specialist works were selected specify the type of works) | 2
|  | It is estimated that Potentially Emerging enterprises should have a CIDB contractor grading of (N/A) and satisfy the criteria stated in the Tender Data. (Only applicable if Client has an Official Mentorship programme in place to assist potentially emerging enterprises). |  |  |  |  | FALSE
Only Tenderers who are responsive to the following responsiveness criteria are eligible to submit tenders:
|  | Tender offer must be properly received on the tender closing date and time specified on the invitation, fully completed and signed in ink (All as per Standard Conditions of Tender). |  |  |  |  | TRUE
|  | Submission of applicable: Resolution by the Legal Entity, or consortium /Joint Venture, authorizing a dedicated person(s) to sign documents on behalf of the firm / consortium / Joint Venture. |  |  |  |  | TRUE
|  | Bidder's Disclosure - SBD 4 (T2.11) |  |  | 3 | Pages | TRUE
|  | List of returnable documents |  |  | 3 | Pages | TRUE
|  | Site Inspection Certificate as proof for attendance of compulsory briefing meeting (T2.10) |  |  | 1 | Page | TRUE
|  | Contractor's Safety, Health and Environmental Declaration (T2.17) |  |  | 1 | Page | TRUE
|  | Certified Proof of Good Standing with the Compensation Commissioner (Attach) (T2.20) |  |  | 1 | Page | TRUE
|  | Certified Proof of Paid Municipal Rates and Taxes (Attach) (T2.23) |  |  | 1 | Page | TRUE
|  | Certified Proof of UIF Registration (Attach) (T2.24) |  |  | 1 | Page | TRUE
|  | Financial Standing and other resources of Business Declaration (T2.8) |  |  | 1 | Page | TRUE
|  | Compulsory Enterprise Questionnaire (T2.18) |  |  | 2 | Pages | TRUE
|  | Preference Points Claim Form (T2.9) |  |  | 5 | Pages | TRUE
|  | Tax Compliance Status (TCS) PIN to verify on line Compliance Supplier Status via e-Filing (T2.19) |  |  | 1 | Page | TRUE
|  | Certified Proof of CIDB Registration Number (T2.27) |  |  | 1 | Page | TRUE
|  | Authority to Sign Tender (T2.2) |  |  | 1 | Page | TRUE
|  | Form of Offer and Acceptance (Bound into Section 1 of 2) (T2.21) |  |  | 5 | Pages | TRUE
|  | Functionality Criteria (T2.34) |  |  | 3 | Pages | TRUE
|  | Invitation to Tender - SBD 1 (T2.35) |  |  | 3
|  | CIDB B U I L D Programme Undertaking (T2.36) |  |  | 3 | Pages | TRUE
1. RETURNABLE SCHEDULES REQUIRED FOR TENDER EVALUATION PURPOSES
|  | Form of Offer and Acceptance (Bound into Section 1 of 2) (T2.21) |  |  | 5 | Pages | TRUE | Pages
|  | Bidder's Disclosure - SBD 4 (T2.11) |  |  | 3 | Pages | TRUE | Pages
|  | Authority to Sign Tender (T2.2) |  |  | 1 | Page | TRUE | Page
|  | Authority for Consortia or Joint Venture’s to Sign Tender (T2.3) |  |  | 2 | Pages | TRUE | Pages
|  | Special Resolution of Consortia or Joint Venture’s (T2.4) |  |  | 3 | Pages | TRUE | Pages
|  | Joint Venture Involvement Declaration (T2.5) |  |  | 2 | Pages | TRUE | Pages
|  | Schedule of Proposed Sub-Contractors (T2.6) |  |  | 1 | Page | TRUE | Page
|  | Capacity of Tenderer (T2.7) |  |  | 6 | Pages | TRUE | Pages
|  | Annual Financial Statement for past financial year (2.15) |  |  | 1 | Page | TRUE | Page
|  | Financial Standing and other resources of Business Declaration (T2.8) |  |  | 1 | Page | TRUE | Page
|  | Site Inspection Certificate as proof for attendance of compulsory briefing meeting (T2.10) |  |  | 1 | Page | TRUE | Page
|  | Compulsory Enterprise Questionnaire (T2.18) |  |  | 2 | Pages | TRUE | Pages
|  | Preference Points Claim Form (T2.9) |  |  | 5 | Pages | TRUE | Pages
|  | Complete Priced Bill of Quantities |  | (Tenderder to attach) (T2.22) | 1 | Page | TRUE | Page
|  | Certified Proof of CIDB Registration Number (T2.27) |  |  | 1 | Page | TRUE | Page
|  | Contract Form - Purchase of Goods/Works - Part 1 (T2.29) |  |  | 1 | Page | TRUE | Page
|  | Contract Form - Purchase of Goods/Works - Part 2 (T2.30) |  |  | 1 | Page | TRUE | Page
|  | The National Industrial Participation Programme (T2.25) |  |  | 2 | Pages | TRUE | Pages
|  | Certified Proof of Registration Number on the Central Suppliers Database (T2.26) |  |  | 2 | Pages | TRUE | Pages
2. RETURNABLE SCHEDULES REQUIRED FOR TENDER EVALUATION PURPOSES BUT TO BE SUPPLIED BY THE TENDERER
|  | Tax Compliance Status (TCS) PIN to verify on line Compliance Supplier Status via e-Filing (T2.19) |  |  | 1 | Page | TRUE | Page
|  | Certified Proof of Good Standing with the Compensation Commissioner (Attach) (T2.20) |  |  | 1 | Page | TRUE | Page
|  | Proof of payment of Tender deposit (T2.28) |  |  | 1 | Page | TRUE | Page |  |  | CIDB Registration form or application for Registration form
|  | Certified Proof of Paid Municipal Rates and Taxes (Attach) (T2.23) |  |  | 1 | Page | TRUE | Page
|  | Certified Proof of UIF Registration (Attach) (T2.24) |  |  | 1 | Page | TRUE | Page
|  | Annual Financial Statement for past financial year (2.15) |  |  | 1 | Page | TRUE | Page
|  | CIDB B U I L D Programme Undertaking (T2.36) |  |  | 1
|  | Entire tender document including returnable and supporting documents, scanned as PDF onto a CD, clearly marked with the Tender information. |  |  |  | Pages | TRUE | Pages |  |  | Copy of entire procurement document on CD -The procedure in terms of item 3.2 of Circular No 6 of 2013
3. RETURNABLE SCHEDULES THAT WILL BE INCORPORATED INTO THE CONTRACT
|  | Record of Addenda to Tender Documents (T2.12) |  |  | 1 | Page | TRUE | Page
|  | Particulars of Electrical Contractor (T2.13) |  |  | 1 | Page | TRUE | Page
|  | Equipment Schedules-Mechanical / Electrical / Security Material (T2.16) |  |  | 1 | Page | TRUE | Page
|  | Schedule of Imported Materials and Equipment (T2.14) |  |  | 5 | Pages | TRUE | Pages
|  | Contractor's Safety, Health and Environmental Declaration (T2.17) |  |  | 1 | Page | TRUE | Page
4. OTHER DOCUMENTS THAT WILL BE INCORPORATED INTO THE CONTRACT
|  | Bill of Quantities (T2.22) |  | 70 | Pages |  | TRUE | Pages
|  | Form of Guarantee (C1.3) |  | 2 | Pages |  | TRUE | Pages
|  | List of Drawings/Annexure's (C5.1) |  | 2 | Pages |  | TRUE | Pages
|  | Confirm Receipt of Offer and Acceptance (T2.21a) |  | 1 | Page |  | TRUE | Page
|  | The National Industrial Participation Programme (T2.25) |  | 2 | Pages |  | TRUE | Pages
|  | Required Structure of Contractor's detailed OHSE Plan (T2.31) |  | 2 | Pages |  | TRUE | Pages
|  | Client's specific requirements for the Contractor's detailed OHSE Plan (T2.32) |  | 8 | Pages |  | TRUE | Pages
|  | Base line Risk Assessment (T2.33) |  | 1 | Page |  | TRUE | Page
|  | Functionality CRITERIA |  |  |  | Deliverables
| 1 | Financial Standing |  | 30 | Points | The submission of all financial requirements stipulated in the tender
|  | Proof of working capital of at least 25% of project value |  |  | 10
|  | Letters of credit reference from suppliers and credit limits to be stipulated with supporting documents |  |  | 10
|  | Annual/Audited Financial Statement/Management Account/income and Expenditure Statements |  |  | 10
| 2 | Competency, Experience and Resource Capacity |  | 25 | Points | Tenderer to demonstrate their technical competency, human resource capacity and relevant project experience
|  | Detailed schedule of resources at all levels |  |  | 5
|  | Schedule of years of experience on similar projects |  |  | 5
|  | Schedule of experience on projects of similar value and duration (Past 3 years) – letters of award to be attached and practical completion certificate for all work completed in the preceding 3 years |  |  | 5
|  | Demonstrated ability to work on an accelerated programme |  |  | 5
|  | Experience in projects that have operational challenges i.e. public interface |  |  | 5
| 3 | Tenderer’s Project Management Structure and Organogram and Experience of Resources Proposed for the Project |  | 10 | Points | A tenderer that submits a detailed project organogram that sets out the roles and responsibilities of each proposed team member, which is backed up By their curriculum vitae that demonstrate extensive experience, together with a project implementation structure shall be allocated maximum sub-points. In all other instances zero (0) sub-points shall be allocated.
|  | Submission of a detailed organogram |  |  | 2
|  | All key project resources have more than (5) years’ experience in the construction industry. All key project resources have experience in projects of a similar value and nature |  |  | 1
|  | Detailed CV. Traceable reference. Certificates of qualified professionals in their full employment to be attached. |  |  | 1
|  | Detailed CV of each team member (Category) and Traceable references to be detailed |  |  | 2
|  | All key project resources are dedicated full time for the duration of the project including proof of UIF contributions |  |  | 2
|  | Tenderer to demonstrate key/resource deployment over the various work package |  |  | 2
| 4 | Tenderers ability to provide a Letter of Intent for the provision of a guarantee |  | 5 | Points | Original letter of intent on a bank’s letterhead.
|  | Letter from a registered financial institution confirming intention to issue a provision of a guarantee |  |  | 5
| 5 | Methodology and Approach | 20 | 20 | Points | Detailed method statement and programme to be submitted.
|  | Site establishment indicating proposed layout for all prescribed facilities, hoarding, etc. |  |  | 3
|  | Resourcing strategy for the various work breakdown structures including resource deployment plan (PS) |  |  | 5
|  | Material storage, handling and distribution |  |  | 1
|  | Productivity, programming, resource investment, progress tracking, corrective action plans, etc. |  |  | 3
|  | Programme and progress reporting, including tracking of long lead procurement items |  |  | 3
|  | OHS Management, compliance and reporting |  |  | 1
|  | Site documentation control, filing and archiving |  |  | 1
|  | Queries and information required approach |  |  | 1
|  | Procurement of outsourced resources e.g. sub-contractors |  |  | 2
| 6 | Enterprise Development (Targeting of Youth Owned Contractors) |  | 10 | Points | Contract Participation Goal (CPG) to meet specified Enterprise Development target of 50% (fifty Percent)
|  | Tendered CPG less than 50% pro-rata to minimum target |  |  | 0 ≤ 5
|  | Tendered CPG is 50% |  |  | 5
|  | Tendered CPG is greater than 50% pro-rata to minimum target |  |  | ≥ 5 ≥ 10
The threshold score, below which tenderers are eliminated from further consideration, should be between 50% and 60%
5. DOCUMENTS REQUIRED FOR THE EVALUATION OF Functionality
|  | Proof of working capital of at least 25% of project value |  |  |  |  | TRUE | Pages
|  | Letters of credit reference from suppliers and credit limits to be stipulated with supporting documents |  |  |  |  | TRUE | Pages
|  | Annual/Audited Financial Statement/Management Account/income and Expenditure Statements |  |  |  |  | TRUE | Pages
|  | Detailed schedule of resources at all levels |  |  |  |  | TRUE | Pages
|  | Schedule of years of experience on similar projects |  |  |  |  | TRUE | Pages
|  | Schedule of experience on projects of similar value and duration (Past 3 years) – letters of award to be attached and practical completion certificate for all work completed in the preceding 3 years |  |  |  |  | TRUE | Pages
|  | Demonstrated ability to work on an accelerated programme |  |  |  |  | TRUE | Pages
|  | Experience in projects that have operational challenges i.e. public interface |  |  |  |  | TRUE | Pages
|  | Submission of a detailed organogram |  |  |  |  | TRUE | Pages
|  | All key project resources have more than (5) years’ experience in the construction industry. All key project resources have experience in projects of a similar value and nature |  |  |  |  | TRUE | Pages
|  | Detailed CV. Traceable reference. Certificates of qualified professionals in their full employment to be attached. |  |  |  |  | TRUE | Pages
|  | Detailed CV of each team member (Category) and Traceable references to be detailed |  |  |  |  | TRUE | Pages
|  | All key project resources are dedicated full time for the duration of the project including proof of UIF contributions |  |  |  |  | TRUE | Pages
|  | Tenderer to demonstrate key/resource deployment over the various work package |  |  |  |  | TRUE | Pages
|  | Letter from a registered financial institution confirming intention to issue a provision of a guarantee |  |  |  |  | TRUE | Pages
|  | Site establishment indicating proposed layout for all prescribed facilities, hoarding, etc. |  |  |  |  | TRUE | Pages
|  | Resourcing strategy for the various work breakdown structures including resource deployment plan (PS) |  |  |  |  | TRUE | Pages
|  | Material storage, handling and distribution |  |  |  |  | TRUE | Pages
|  | Productivity, programming, resource investment, progress tracking, corrective action plans, etc. |  |  |  |  | TRUE | Pages
|  | Programme and progress reporting, including tracking of long lead procurement items |  |  |  |  | TRUE | Pages
|  | OHS Management, compliance and reporting |  |  |  |  | TRUE | Pages
|  | Site documentation control, filing and archiving |  |  |  |  | TRUE | Pages
|  | Queries and information required approach |  |  |  |  | TRUE | Pages
|  | Procurement of outsourced resources e.g. sub-contractors |  |  |  |  | TRUE | Pages
[7 empty] | FALSE | Pages
[7 empty] | FALSE | Pages
[7 empty] | FALSE | Pages
[7 empty] | FALSE | Pages
[7 empty] | FALSE | Pages
[7 empty] | FALSE | Pages
B. CONTRACT DATA
|  | Employer | Head: Public Works (KZN Department of Public Works: Province of KwaZulu-Natal)
|  | Physical Address | 191 Prince Alfred Street
|  | Town | PIETERMARITZBURG
|  | Code | 3200
|  | Postal Address | Private Bag X 9041
|  | Town | PIETERMARITZBURG
|  | Code | 3200
|  | Telephone Number (Including area code) | 033 - 8971300
|  | Fax Number (Including area code) | 033 - 8971399
|  | Engineer/Principal Agent Name | Mr. Brightspark Knowitall
|  | Engineer/Principal Agent | [Identify the Company or person]
|  | Capacity | 1
|  | Postal Address | [P.O. Box number]
|  | Town | [Name of town]
|  | City | [Name of City]
|  | Postal Code | [Code]
|  | Physical Address | ABC Street
|  | Town | [Name of town]
|  | Code | [Code]
|  | Telephone number | [Telephone Number including Area Code]
|  | Cell No. | N/A
|  | Fax number | [Fax Number including Area Code]
|  | Email Address | [Email Address]
|  | Client | KZN Department of Public Works
|  | Representative of Employer (Regional Office) | Regional Manager
|  | Private Box/Postal Address | X9041
|  | Town | Pietermarizburg
|  | Postal Code | 3200
|  | Telephone number | 033-897 1421/1422
|  | Fax number | 033-897 1399
|  | Physical Address | 10 Prince Alfred Street, Pietermaritzburg,
|  | Street | 10 Prince Alfred Street
|  | Town | Pietermarizburg
|  | Code | 3200
|  | DOPW Project Manager [Name]: | Mr. Khumalo
|  | DOPW Project Manager [Cell Number]: | 082 123 4568
|  | DOPW Project Manager [Email address]: | mkhumalo@kznworks.gov.za
Employers Agent 1
|  | Agent’s Service | [Identify Agent's Service, eg. Engineer] | [5 empty] | Architect
|  | Agent's Name | [Agents Name]
|  | Private Box/Postal Address | [P.O. Box number]
|  | Town | [Name of town]
|  | Postal Code | [Code]
|  | Telephone number | [Tel Number including Area Code]
|  | Fax number | [Fax Number including Area Code]
|  | Email Address | [Email Address]
Employers Agent 2
|  | Agent’s Service | [Identify Agent's Service, eg. Engineer] | [5 empty] | QS
|  | Agent's Name | [Agents Name]
|  | Private Box/Postal Address | [P.O. Box number]
|  | Town | [Name of town]
|  | Postal Code | [Code]
|  | Telephone number | [Tel Number including Area Code]
|  | Fax number | [Fax Number including Area Code]
|  | Email Address | [Email Address]
Employers Agent 3
|  | Agent’s Service | [Identify Agent's Service, eg. Engineer] | [5 empty] | Engineer
|  | Agent's Name | [Agents Name]
|  | Private Box/Postal Address | [P.O. Box number]
|  | Town | [Name of town]
|  | Postal Code | [Code]
|  | Telephone number | [Tel Number including Area Code]
|  | Fax number | [Fax Number including Area Code]
|  | Email Address | [Email Address]
Employers Agent 4
|  | Agent’s Service | [Identify Agent's Service, eg. Engineer] | [5 empty] | Engineer
|  | Agent's Name | [Agents Name]
|  | Private Box/Postal Address | [P.O. Box number]
|  | Town | [Name of town]
|  | Postal Code | [Code]
|  | Telephone number | [Tel Number including Area Code]
|  | Fax number | [Fax Number including Area Code]
|  | Email Address | [Email Address]
Employers Agent 5
|  | Agent’s Service | [Identify Agent's Service, eg. Engineer] | [5 empty] | Engineer
|  | Agent's Name | [Agents Name]
|  | Private Box/Postal Address | [P.O. Box number]
|  | Town | [Name of town]
|  | Postal Code | [Code]
|  | Telephone number | [Tel Number including Area Code]
|  | Fax number | [Fax Number including Area Code]
|  | Email Address | [Email Address]
Employers Agent 6
|  | Agent’s Service | [Identify Agent's Service, eg. Engineer]
|  | Agent's Name | [Agents Name]
|  | Private Box/Postal Address | [P.O. Box number]
|  | Town | [Name of town]
|  | Postal Code | [Code]
|  | Telephone number | [Tel Number including Area Code]
|  | Fax number | [Fax Number including Area Code]
|  | Email Address | [Email Address]
Employers Agent 7
|  | Agent’s Service | [Identify Agent's Service, eg. Engineer]
|  | Agent's Name | [Agents Name]
|  | Private Box/Postal Address | [P.O. Box number]
|  | Town | [Name of town]
|  | Postal Code | [Code]
|  | Telephone number | [Tel Number including Area Code]
|  | Fax number | [Fax Number including Area Code]
|  | Email Address | [Email Address]
Employers Agent 8
|  | Agent’s Service | [Identify Agent's Service, eg. Engineer]
|  | Agent's Name | [Agents Name]
|  | Private Box/Postal Address | [P.O. Box number]
|  | Town | [Name of town]
|  | Postal Code | [Code]
|  | Telephone number | [Tel Number including Area Code]
|  | Fax number | [Fax Number including Area Code]
|  | Email Address | [Email Address]
|  | Practical Completion Date | A time measured from the Commencement date.
|  | Waiver of Lien or right of continuing possession is required |  |  | Yes
This is a requirement of the DOPW and must remain "Yes"
Non-Working days
|  | Non-Working days | Sundays |  |  | Please note the following; All special non-working days must be added to the number of days allocated as the construction period in terms of GCC2010 clause 5.1, to determine the Due Completion Date. For all DOPW projects the period from the 16 December to the second Monday in January of the following year must be indicated as BUILDERS HOLIDAY.
|  | Special non- working days | All Nationally Recognized Public Holidays and the year end break
|  | First Year end break - commences | 2016-12-16
|  | ends on | 2017-01-09
|  | Second Year end break - commences | N/A
|  | ends on | N/A
|  | Third Year end break - commences | N/A
|  | ends on | N/A
|  | Fourth Year end break - commences | N/A
|  | ends on | N/A
Delivery of Guarantee
|  | The time to deliver the deed of guarantee is within: | Prior to site hand over in terms of clause 5.3.1 and 5.3.2. | [7 empty] | 15/1/2013
|  | The Guarantee will be for a sum of: | 10 | % |  |  | of the Contract Price
Type of Guarantee required by Employer
(a) the Tenderder accepts that in respect of contracts up to R1 million, a payment reduction of 5% of the contact value will be applicable and will be reduced by the Employer in terms of the applicable conditions of contract.
(b) in respect of contracts above R1 million, the Tenderder offers to provide security as indicated below:
(i) cash deposit of 10 % of the Contract Price
(ii) bank or insurance Performance Guarantee of 10 % of the Contract Price
(iii) cash deposit of 5% of the Contract Price and a payment reduction of 5% of the value certified in the payment certificate (excluding VAT)
(iv) bank or insurance guarantee of 5% of the Contract Price and a payment reduction of 5% of the value certified in the payment certificate (excluding VAT)
Commencement date
|  | The contractor shall commence executing the Works: | within 7 calendar days from the Commencement Date.
Programme
|  | The Contractor shall deliver his programme of work | The Contractor shall deliver his programme of work within 10 calendar days after notice from the Employer, prior to the Commencement Date.
Insurance
|  | The Value of material, supplied by the Employer, and not included in the Contract Price, is: (cl 8.6.1.1.2) |  |  | 0
|  | The amount to cover Professional Fees, not included in the Contract Price, for repairing damage and loss to be included in the insurance: (cl 8.6.1.1.3) |  |  | 30% of the Contract Price
|  | The limit for indemnity for liable insurance is: | Unlimited
Valuations of variations
|  | The percentage allowance to cover overhead charges for contractor and subcontractors, is: |  |  | 33.3%
|  | The time to submit the documentation required before commencement with Works execution is: |  | 14 | Calendar Days
Submission of documents required in terms of clause 5.3.1
|  | Health and Safety Plan | The Contractor shall deliver his Health and Safety Plan of the Works within 14 calendar days after notice from the Employer, prior to the Commencement Date.
|  | Guarantee chosen by the Contractor | The Contractor shall deliver his chosen Guarantee (security) for this Works within 14 calendar days after notice from the Employer, prior to the Commencement Date.
|  | Insurances | The Contractor shall deliver his insurance for the Works within 14 calendar days after notice from the Employer, prior to the Commencement Date.
|  | Priced Bill of Quantity | The Contractor shall deliver his Priced Bill of Quantity within 14 calendar days after notice from the Employer, prior to the Commencement Date.
|  | Cash flow of Project | The Contractor shall deliver his Cash flow for the Works within 14 calendar days after notice from the Employer, prior to the Commencement Date.
|  | Programme | The Contractor is required to submit his Programme of Works in terms of Clause 5.6.1 and 5.3.1 and the Principal Agent is required to approve this within 7 days in terms of Clause 5.6.3
Other requirements
|  | Breakdown of contractor's General Items/preliminaries needs to be submitted within; |  | 10 | Working days
|  | Percentage of Fixed General Items/preliminaries charges: |  | 10% | %
|  | Percentage of Variable General Items/preliminaries with Value charges: |  | 15% | %
|  | Percentage of Variable with Time General Items/preliminaries charges: |  | 75% | %
|  | The preliminaries amounts shall be paid in terms of: |  | 1
Alternative A - Assessed by the Engineer/principal agent as an amount prorated to the value of the work duly executed in the same ratio as the preliminaries bears to the contract price excluding VAT, Preliminary amount, contingencies and any CPAP.
Alternative B - Calculated from the priced Bill of Quantity/lump sum document. The contractor and the engineer/principal agent shall agree on a division of the priced preliminaries items into: initial establishment charge, monthly charge and final disestablishment charge.
|  | Bill of Quantity/Lump Sum | 1
|  | Method of Measurement | 2
|  | Other systems: | N/A |  |  |  | N/A
|  | CPAP (See P&G – E16) | 2
|  | CPAP Base month (Type in the base month) | N/A |  |  |  | N/A
Scope of Works Description
The DATA CAPTURER is reminded that for DOH projects ALL SPECIFICATIONS AND BILLS OF QUANTITIES MUST BE ALIGNED TO THE MOST CURRENT DEPARTMENT OF HEALTH POLICY DOCUMENTS THAT ARE AVAILABLE OFF THEIR WEBSITE. To access all DOH updated specifications and Policy Documents for all building, electrical and mechanical services access. www.kznhealth.gov.za under "Internal departments/Infrastructure Development" or www.iussonline.co.za. Quantity Surveyors are referred to Government Notice No R.116, dated 17 February 2014 that require that all DOH projects are measured in locations.
1.1 EMPLOYER'S OBJECTIVE
Upgrade existing domestic and fire water supply and reticulation by installing new pipes, water storage tanks, pumps, pump house, boreholes, etc. whilst the existing system remains in operation, and switching over to the new system upon completion.
1.2 OVERVIEW OF THE WORKS
The rehabilitation of all road and pavement crossings.
1.3 EXTENT OF WORK
The contract comprises the construction of the above (Item 1) face brick buildings with tiled roofs.
1.4 LOCATION OF THE WORKS
The site is situated within the premises of the Mosvold Hospital on the fringe of the town of Ingwavuma. GPS Co-ordinates for the site is .............................................................................................................
1.5 TEMPORARY WORKS
All temporary work to comply with the Occupational Health and safety Act (Act 85 of 1993)
2.1 EMPLOYER'S DESIGN
Not applicable
2.2 DESIGN BRIEF
Not applicable
2.3 DRAWINGS
See list of drawings/Annexure's attached to this document.
2.4 DESIGN PROCEDURES
|  | Not applicable | [8 empty] | 20000000
|  | 3.1 PREFERENTIAL PROCUREMENT PROCEDURES | [8 empty] | not exceeding
This tender will be subject to the implementation of the Preferential Procurement Regulations, 2022, pertaining to the Preferential Procurement Policy Framework Act, Act Number 5 of 2000 and the relevant Supply Chain Management Legislation and the KwaZulu-Natal Supply Chain Management Policy Framework published by the KwaZulu-Natal Provincial Treasury. Tenderders are referred to www.kzntreasury.gov.za for access to the relevant documents. Tenderders are advised to familiarize themselves with the contents of the KwaZulu-Natal Supply Chain Management Policy Framework regarding Preference Point Systems, evaluation of tenders appeals and other matters.
3.2 RESOURCE STANDARD PERTAINING TO TARGETED PROCUREMENT
|  | NOTE : This project will be adjudicated as not exceeding R 50,000 000,00 | [7 empty] | Do not type anything here. Will adjust automatically.
3.3 SCOPE OF MANDATORY SUBCONTRACT WORK
Not applicable
3.4 PREFERRED SUBCONTRACTORS/SUPPLIERS
Not applicable
3.5 SUBCONTRACTING PROCEDURES
Not applicable
4.1 APPLICABLE SANS 2001 STANDARDS FOR CONSTRUCTION WORKS
The Contractor is referred to the "Model Preambles to Trades - 2008", any "Supplementary Preambles", the Electrical Specifications and Mechanical Specification for full descriptions of materials and methods referred to in these Bills of Quantities/Lump Sum documents, insofar as they apply. The Contractor is advised to study the "Standard Preambles to all Trades", any "Supplementary Preambles", the Electrical Specifications and Mechanical Specification, before pricing Bills of Quantities/Lump Sum documents.
Where the description in the Bills of Quantities/Lump Sum documents differ from those in the Standard Electrical Specifications, the descriptions in the Bills of Quantities/Lump Sum documents are to apply. No claim whatsoever will be allowed in respect of errors in pricing due to brevity of description of items in the Bills of Quantities/Lump Sum documents which are fully described when read in conjunction with the relevant Preambles and/or Specifications. Suppliers of materials and the like, whose quality systems apply with one or more of the SABS/SANS ISO 9000 Series should be used whenever possible in the absence of a particular SABS/SANS Specification Standard Mark.
Wherever the words "shall be deemed to be included in the description", "shall be stated" or other words having the same effect, appear in the Standard System, it shall be deemed that all descriptions in these Bills of Quantities/Lump Sum documents incorporated such inclusions and statements whether specifically stated or not.
The Contractor is hereby informed that where SABS/SANS Specifications are referred to in these Bills of Quantities/Lump Sums documents and Specifications thereto, then ONLY the Specification of Work Clauses will apply. The method of measurement and payment clauses will NOT apply to this Contract.
The Contractor is hereby informed that risk of collapse and keeping excavations free from water (excluding subterranean water) generally are deemed to be included in the descriptions unless accommodated in the system of measurement. Please refer to the Geotechnical Investigation report when included at the end of these tender documents. Whenever reference is made to "Sub-Contractor", "Nominated Sub-Contractor" or the like in the specifications included or referred to in these Bills of Quantities/Lump Sums documents, it shall be deemed to mean "Contractor" as defined.
4.2 APPLICABLE NATIONAL AND INTERNATIONAL STANDARDS
See above 4.1
4.3 PARTICULAR / GENERIC SPECIFICATIONS
The Contractor is referred to the following documents whether attached to this document or not:
|  | Specification for HIV/AIDS Awareness (CIDB) |  |  | HIV1 TO HIV3 | Compiler to note that if it is a Department of Health project, to select DOH Preambles from the menu. Just make sure that this is still the latest's DOH Preambles. See - http://www.kznhealth.gov.za/facilities/trades09.pdf
Specific Construction, Safety, Health and Environmental Plan
|  | 2 |  |  | 1 to 95
|  | General Electrical Specification |  |  | E/1 to E/20
|  | Lightning Protection Installation |  |  | LP/1 to LP/6
4.4 CERTIFICATION BY RECOGNIZED BODIES
Only contractors registered with the Electrical Contracting Board of South Africa in accordance with the Regulations of the Occupational Health and Safety Act will be accepted and permitted to do work under this contract.
4.5 AGRÉMENT CERTIFICATES
Not applicable
4.6 PLANT AND MATERIAL PROVIDED BY THE EMPLOYER
Not applicable
4.7 SERVICES AND FACILITIES PROVIDED BY THE EMPLOYER
Not applicable
4.8 OTHER SERVICES AND FACILITIES
The Contractor shall provide any artificial lighting which may be necessary or required for the proper execution of the works, and provide electric power and water required by all Sub-Contractors, Nominated Sub-Contractors and Sub-Contractors appointed directly by the Administration. The Contractor shall give all notices and pay all fees in connection with temporary electrical and water connections and shall connect temporary Electrical and Water meters for and pay for all current and water consumed. The Contractor is advised that the permanent light fittings and water points of any kind installed in the Works are not to be used to provide temporary lighting and supplement water requirements for construction purposes.
5.1 APPLICABLE SANS 1921 STANDARDS
Tenderders are referred to SECTION 2 : SPECIFICATION DATA ASSOCIATED WITH SANS 1921-1:2004 IN THIS DOCUMENT
5.2 RECORDING OF WEATHER
The Contractor shall keep record of abnormal climatic conditions to facilitate the adjudication of claims for extension of the contract period.
5.3 MANAGEMENT MEETINGS
In order to facilitate the smooth functioning of the Works and to ensure the closest co-operation between all the parties concerned, the Employer will call for regular meetings to be held on the site, at which a senior member of the Contracting firm and the General Foreman of the Works will always be required to be present. In addition to the above, other persons will be required to attend these meetings as and when their presence is necessary, e.g., Consultants in all disciplines, representatives of the various Sub-Contractors, etc. Proper minutes of these meetings will be kept by the Employer\Principal Agent and copies will be circulated to all persons attending the meetings and to others who need to be kept informed.
5.4 FORMS FOR CONTRACT ADMINISTRATION
The Employer shall provide all necessary forms.
5.5 ELECTRONIC PAYMENTS
The Contractor shall provide all required information to the Employer to facilitate electronic payments upon request.
5.6 DAILY RECORDS
The Contractor shall keep daily records of people and equipment employed as well as a site diary in respect of work performed on the site. At the end of each week the Contractor shall provide the Principal Agent with a written record, in schedule form, reflecting the number and description of tradesmen and labourers employed by him and all Sub-Contractors on the works each day. At the end of each week the Contractor shall provide the Principal Agent with a written record, in schedule form, reflecting the number, type and capacity of all plant, excluding hand tools, currently used on the works.
5.7 BONDS AND GUARANTEES
The Contractor shall within 10 calendar days after receiving notice from the Engineer and prior to receiving a completed copy of this agreement, including the schedule of deviations (if any), contact the Employer’s agent (whose details are given in the contract data) to arrange the delivery of any bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data.
5.8 PAYMENT CERTIFICATES
Requirements will be in accordance with the Employers prescriptions.
5.9 PERMITS
The Contractor is advised that, in the case of an existing building or institution, all security measures in force will remain in operation and he must acquaint himself and his Employees with them as he and his Employees will at all times be subject to these measures. The Contractor will on no account extend his operations beyond the confines of the building site as indicated by the Employer and must ensure that all his Employees are made aware of these limits. Any Employee disregarding this instruction and found outside the limit of the building site without authority, shall be redeployed immediately and shall not again be employed on this Contract. The Contractor will be responsible for ensuring that this instruction is strictly enforced and must provide and remove upon completion or when directed, such other necessary temporary barriers, fences, etc., as may be required and is to allow opposite this item for any charges he may wish to make in this connection. The Employer will accept no responsibility whatsoever for damage to or the loss of plant, materials, etc., from the site.
5.10 PROOF OF COMPLIANCE WITH THE LAW
The following certificates must be provided before first delivery is taken: - HIV/STI Report (Bound into this document) - Electrical Compliance Certificate - Plumbing Compliance Certificate - Lightning Certificate - Soil Protection Certificate - Concrete test and cube certificates - Waterproofing Guarantee certificates - TR1 and TR2 prefabricated roof truss certificates - Soil compaction certificates - Electrical and Mechanical test certificates - Plumbing and drainage pressure test certificates - Fire Compliance Certificate - Entomology Certificate - SANS 10400-A:2010 compliance certificates - Latest National Building Regulation
5.11 INSURANCE PROVIDED BY THE EMPLOYER
Not Applicable
The requirements for drawings, information and calculations for which the Contractor is responsible are:
Prefabricated roof trusses design must be submitted for approval 30 days prior to erections.
The responsibility strategy assigned to the Contractor for the works is:
Strategy A
The structural engineer is:
ABC Engineers
Drawings & other info are to be submitted in accordance with the contractors programme
N/A
The planning, programme and method statement are to comply with the following:
N/A
Samples of materials
The work is to be executed with materials of the best specified and in the most substantial and workmanlike manner under the inspection of the Employer and to his satisfaction. The Contractor shall furnish, without delay, such samples as called for or may be called for by the Employer, who may reject all materials or workmanship not corresponding with the approved sample. The samples of materials, workmanship and finishes that the Contractor is to provide and deliver to the employer are:
- Tile sample. - Brick sample. - Light fitting sample. - Screed panel 2m x 2m impact test. - Tested trial mix to be approved by the Engineer.
Fabrication drawings that the contractor is to provide to the employer are:
None
Office accommodation, equipment, accommodation for site meetings and other facilities for use by the employer and his agents are:
OFFICE FOR FOREMAN
Provide, erect, maintain and remove at completion a suitable temporary office for the Contractor or his Foreman, perfectly secured, lighted and ventilated and having a desk with drawers.
TELEPHONE
The Contractor shall provide a telephone on the site for the use of the Contractor and all Sub-Contractors for the duration of the Contract, and must make the necessary application for connection, give all notices and pay all fees, rentals and charges for the service and also for all calls.
OFFICE FOR INSPECTOR OF WORKS
Provide, erect, maintain and remove at completion a well constructed temporary office for the Inspector of Works not less than 4 x 3 m on plan and 3 m high to eaves to the approval of the Employer. The office shall be constructed of wood framing covered externally with corrugated iron or corrugated asbestos and with a lean-to roof covered with the same material as the external wall covering. The office shall be lined internally with soft board or other approved material and a ceiling shall be provided of the same material as the internal lining. A suspended wood floor shall be provided and is to finish not less than 300 mm above the ground level. A lockable door and a window, which provides adequate light and ventilation, shall be fitted. An office constructed of 115 mm thick brick-work and provided with a screeded concrete floor and roofed and ceiled as above described may be accepted as an alterative but prior permission of the Employer will be necessary before construction of such an office is commenced and his requirements shall be stated and fulfilled by the Contractor. The office shall be fitted in an approved manner with a sloping topped desk of height and length suitable for the laying out and studying of drawings, a desk or table with not less than two lock-up drawers, shelves, seating and wash-stand, and the Contractor shall provide all necessary attendance.
TELEPHONE IN OFFICE FOR INSPECTOR OF WORKS
The Contractor shall arrange for the installation of a lockable telephone in the Office for the Inspector of Works for the duration of the Contract. The Contractor will be required to make the necessary application for connection and give all notices on behalf of the Employer. The Employer will, however, be responsible for the direct payment of all fees, rentals and other charges by Telkom for the service for the Inspector of Works and for all calls made from this telephone.
SHED
Provide, erect, maintain and remove at completion, ample temporary sheds for the proper storage of materials and for the use of the workmen, and remove when no longer required.
The requirement for provision and erection of signboards are:
Supply, erect, maintain and remove at completion a painted notice board, size overall 2800 x 2345 mm high sign written to detail as Drawing No. T9506 which drawing is available from offices of the Department of Public Works. Only the official notice board is to be displayed on the site and no Sub-Contractor's boards will be permitted. The Contractor, at his own cost, may provide a board on which all sub-contract firms' names may be sign written. The notice board is to be to the approval of the Employer and is to be maintained in first class condition and placed where directed at the entrance to the site and remain there for the duration of the Contract.
Requirement for the termination, diversion or maintenance of existing services:
Should the Contractor come in contact with any underground cables or pipes during excavations, immediate notification must be made to the Employer and all work in the vicinity of such cables, pipes, etc., shall cease until authority to proceed has been obtained from the Employer. Should the Contractor damage underground cables or pipes resulting in a disruption of services to an existing institution such damage shall be repaired immediately.
Services which are known to exist on the site:
Investigate and provide detail drawings.
Requirement for detection apparatus
None
ADDITIONAL HEALTH AND SAFETY REQUIREMENTS ARE:
By the submission of a tender, any Tenderder will, if awarded the contract to which this tender document relates, be deemed to be the mandatory as envisaged by Section 37 (2) of the Act. As a mandatory the successful Tenderder will be deemed to be the “principal contractor” and an employer in his/her/their own right with duties as prescribed in the Act and accordingly will be deemed to have agreed to be solely responsible for ensuring that in connection with the service to which this tender document relates, all work will be performed and machinery and plant used in accordance with the Act. Should the Contractor, for whatever reason be unable to perform as required by the Act, the Contractor undertakes to inform the Employer accordingly. Tenderders are advised that it is a Condition of this Tender that a 'Construction Phase Safety, Health and Environmental Plan' specifically relates to the project for which tenders are being submitted and must be prepared by the Tenderder and submitted with the other tender documents at the time of tender. Failure to do so will invalidate the tender.
Tenderders are therefore advised to study the 'Construction Safety, Health and Environmental Specification' which is issued as part of this tender document, the Model Preambles to Trades - 2008, any project Specification included in this tender document and any and all drawings which are referred to and issued as part of this tender document before preparing their own project specific 'Construction Phase Safety, Health and Environmental Plan' . Tenderders are also advised that such a plan which is submitted with a tender but is incomplete or considered inadequate by the Employer or his Representative will invalidate the tender. The Contractor will be deemed to have satisfied himself with his obligations in terms of the Act and to have allowed for all costs arising from compliance with the Act as no claim for extra costs arising from compliance with, and obligations in terms of the Act will be entertained.
WORK BY NOMINATED AND SELECTED SUBCONTRACTORS COMPRISE:
[Provide list of applicable contractors]
EPWP Scope of Works (If Applicable)
DESCRIPTION OF THE WORKS
1. Employer’s objectives
The employer’s objectives are to deliver public infrastructure using labour-intensive methods in accordance with EPWP Guidelines.
2. Labour-intensive works
Labour-intensive works comprise the activities described in the Labour-Intensive Specification. Labour-intensive works shall be constructed/maintained using local workers who are temporarily employed in terms of the scope of work.
3. Labour-intensive competencies of supervisory and management staff
Contractors shall only engage supervisory and management staff in labour-intensive works that have completed the skills programme including Foremen/ Supervisors at NQF level 4 “National Certificate: Supervision of Civil Engineering Construction Processes” and Site Agent/ Manager at NQF level 5 "Manage Labour-Intensive Construction Processes" or equivalent QCTO qualifications (See Appendix C). at NQF outlined in Table 1. (See GUIDELINES FOR THE IMPLEMENTATION OF LABOUR-INTENSIVE INFRASTRUCTURE PROJECTS UNDER THE EXPANDED PUBLIC WORKS PROGRAMME (EPWP) -THIRD EDITION 2015)
Emerging contractors shall have personally completed, or be registered on a skills programme for the NQF level 2 unit standard. All other site supervisory staff in the employ of emerging contractors must have completed, or be registered on a skills programme for the NQF level 2 unit standards or NQF level 4 unit standards. Table 1: Skills programme for supervisory and management staff.
4. Tasks established by the contractor must be such that:
| a) | the average worker completes 5 tasks per week in 40 hours or less; and
| b) | the weakest worker completes 5 tasks per week in 55 hours or less.
5. Training of targeted labour
The contractor shall provide all the necessary on-the-job training to targeted labour to enable such labour to master the basic work techniques required to undertake the work in accordance with the requirements of the contract in a manner that does not compromise worker health and safety.
The cost of the formal training of targeted labour, will be funded by the local office of the Department of Labour. This training will take place as close to the project site as practically possible. The contractor must access this training by informing the relevant regional office of the Department of Labour in writing, within 14 days of being awarded the contract, of the likely number of persons that will undergo training and when such training is required. The Employer and the Department of Public Works (Fax: 012 3258625/ EPWP Unit, Private Bag X65, Pretoria 0001) must be furnished with a copy of this request.
The contractor shall do nothing to dissuade targeted labour from participating in training programmes and shall take all reasonable steps to ensure that each beneficiary is provided with two days of formal training for every 22 days worked.
An allowance equal to 100% of the task rate or daily rate shall be paid by the contractor to workers who attend formal training, in terms of the above.
Proof of compliance with the above requirements must be provided by the Contractor to the Employer prior to submission of the final payment certificate.
EMPLOYMENT AND TRAINING OF LABOUR ON THE EPWP BENEFICIARY INFRASTRUCTURE PROJECTS
|  |  | BILL NO: | 2
|  | Payment for training of EPWP beneficiary : Target: | 50 | (number of workers)
|  | The number of EPWP beneficiary specified for this contract that will receive; |  | life skills training is | 50 | Youths
|  |  |  | technical training is | 50 | Youths
|  | Penalties for not meeting target per EPWP beneficiary | 2000 | per EPWP beneficiary
|  | Skills development and Technical training for EPWP beneficiary for an average of : |  | 10 | days
The above item is only applicable if DoL does not fund the Technical Training PRIOR to site handover.
|  | Life skills training for [number of day] | 26 | days
|  | Travelling based on [number of km/EPWP beneficiary] | 50 | km/EPWP beneficiary
Employment of Youth Workers
|  | Statutory labour rates of: | 100 | per day | New Office Block
|  | Duration of employment of EPWP beneficiary: | 6 | months
|  | Employment of EPWP beneficiary | 30 | Number | Location: | New Office Block
|  | Employment of EPWP beneficiary | 40 | Number | Location: | Parking garage
|  | Employment of EPWP beneficiary | 30 | Number | Location: | Conference Centre & Canteen
|  | Statutory labour rates of: | 110 | per day | Parking garage
|  | Duration of employment of EPWP beneficiarys: | 12 | months
|  | Statutory labour rates of: | 120 | per day | Conference Centre & Canteen
|  | Duration of employment of EPWP beneficiary: | 12 | months
|  | Supply EPWP designed overalls to: | 100 | Youths
|  | Supply of small tools to: | 100 | Youths
|  | Liaison with Service Provider (ref. SL 11.08) | 30 | hours
|  | Target of unskilled labour to woman: | 55%
|  | Target of unskilled labour to youth (18 - 35): | 55%
|  | Target of unskilled labour to disabled people: | 2%
|  | Target for unskilled labour to be utilised that must reside within the boundaries of the Municipality where this contract is executed: | 100%
E20 |  | UTILISATION OF A COMMUNITY LIAISON OFFICER
In addition to the requirements of Clause E9 "LOCAL LABOUR" on page 8 of Bill No. 1: Preliminaries, contained in this tender document, the Contractor shall allow for and pay any and all costs necessary for the engagement of the services of a Community Liaison Officer (CLO) for the full duration of this contract.
In the interests of providing a sound service to both the community and the Contractor, a CLO may only manage one project at any given time.
A CLO will be identified by the local community of the surrounding areas and be approved by the Councillors(s) of the local Municipality, in order to assist the Contractor in the procurement of any local labour, etc. required for this project and the Contractor is to liaise with the CLO and afford him any assistance needed in ensuring harmonious working relations with the local community.
Key Responsibilities of the CLO are envisaged to include and not necessarily be limited to:
1.Assisting local leadership in conducting skills and resources audit which facilitates sourcing labour from within the ward or targeted areas for employment, as required by contractor
2. Assisting in sourcing labour-only domestic sub-contractors and the procurement of materials from local resources, as required by the Contractor.
3. Assisting the Contractor by identifying areas of potential conflict and/or threats to the project or to stakeholders in the Project and recommend appropriate action to the Contractor.
4.Establishing and ensuring that efficient and open communication channels between the Contractor and the workforce are maintained.
5.Assisting the Contractor and stakeholders in the Project in the resolution of any conflict which may arise.
6. Establishing and ensuring that sufficient and open communication channels between the Contractor and the community are maintained.
7. Identifying and reporting to the Contractor regarding issues where communication between stakeholders is necessary, recommend courses of action and facilitate such communications.
8. Assisting the Contractor and the work force in the establishment of grievance procedures and make recommendations to the Contractor regarding the grievances and solutions thereto.
9. Attending site meetings and project implementation meetings as required by the Contractor and prepare periodic reports as may be required by the Contractor from time to time.
10. Attending to such other duties which are consistent with the functions of a CLO, as may be required by the Contractor from time to time.
Tenderers are to price against this item for any and all costs arising out of compliance with the foregoing and in the event of a Tenderer failing to price against this item or making inadequate financial provision against this item for compliance as aforesaid, then no claim for costs or additional costs incurred will be entertained by the Head: Works.
E21 |  | SKILLS DEVELOPMENT ON SITE
Contractor in conforming to the object of EPWP that its beneficiaries need to be capacitated with skills that will render them employable in the future. It is then the responsibility of the contractor that mandatory life skills are provided to 100% of workforce on site and on the job training to labourers from whom the potential for further development has been identified. The latter is not mandatory to all as it covers technical skills.
Contractor should also make provision for the possibility that there might be local youth that will need to be placed on the project with an intention to be provided support towards improving their level of competency and productivity.
Contractor shall also provide all necessary on-the-job training to targeted labour to enable such labour to master and advance on techniques required to undertake the work in accordance with requirements of the contract in a manner that does not compromise workers health and safety.
E22 |  | LABOUR ONLY SUB-CONTRACTING FOR LOCAL EMERGING ENTERPRISES
Tenderer’s are advised that this contract is subject to the Expanded Public Works Programme (EPWP) and the following criteria will apply:
African Equity Ownership
a) The Tenderer is to allow for 5% of the total value of works to be undertaken by a Priority Population Group. This percentage excludes the costs of employing local unskilled labour. The allocation of this percentage from the Project, the screening of people, the selection of skills, will be for the Contractor to adjudicate.
b) The Priority Population Group consists of women, youth and disabled people.
c) The Contractor is to give first option for prospective PPG’s from the surrounding areas of the Project. Should there be insufficient suitable people fitting the criteria of PPG’s, the Contractor may hire people from further afield. This is to be done only after consultation with the Department of Works EPWP Co-ordinator and the Community Liaison Officer (CLO),
d) A Mentor is to be employed by the Contractor, in consultation with the Department of Works for the purposes of quality control and liaison between the Contractor and the selected PPG’s on site. The mentor will be responsible for ensuring an acceptable level of quality workmanship and that such work carried out by the PPG's is executed within the time frames stipulated.
In so far as possible, the Contractor is encouraged to expand the PPG’s skills, knowledge and performance levels.
TENDERER’S TO NOTE CONDITIONS
a) The contract to be entered into between the Contractor and the PPG’s will be a LABOUR ONLY sub-contract.
Site Information (PG-03.2)
General Information
Describe nature of ground, surface conditions, water table as visible in test holes, and other indisputable facts that may affect construction. Provide available data and information.
Specific requirements must be described.
Any additional site information such as location, improvements on site, adjacent buildings, environmental issues, etc. must be described in detail herein. If project is phased, indicate the phased work procedure with a colour coded site plan or graphical key or sorts.
Geotechnical report
Not applicable
Pricing Instructions
FOR ALL DEPARTMENT OF HEALTH PROJECTS All Quantity Surveyors and Electrical and Mechanical Engineers are reminded that the IT (INFORMATION TECHNOLOGY) Specifications and measured quantities should be fully described and measured as per DOH IT and SITA standards and requirements. The consultants to ensure that prior to preparing the documentation the “Prerequisites for IT Consultants" are fully complied with and that the document bills and specifications MUST be approved by DOH IT section. Any omission to comply with DOH policies and specifications will be for the Consultants account.
BILLS OF QUANTITIES
The Bills of Quantities document forms part of and must be read and priced in conjunction with all the other documents forming part of the contract documents, the Standard Conditions of Tender, Conditions of Contract, Standard Preambles to all Trades, Specifications, Drawings and all other relevant documentation.
VALUE ADDED TAX
The tender price must include for Value Added Tax (VAT). All rates, provisional sums, etc. in the Bills of Quantities must however be net (exclusive of VAT) with VAT calculated and added to the Total Value thereof in the Final Summary.
FIXED PRICE
Should the Bills of Quantities/Lump Sum Document be a fixed price contract, the following clause must be inserted in the Pricing Instructions: Tenderders are to take note that the contract price adjustments are not applicable to this contract. Tenderders should therefore make provision in the Contract Sum, schedule of rates, etc. for possible price increases during the contract period, as no claims in this regard shall be entertained.
The Contractor shall allow for the following days per month for rain:
|  |  | Current Year | Year +1 | Year +2
|  | January |  | 3 | 3
|  | February |  | 3 | 3
|  | March |  | 3 | 3
|  | April |  | 3 | 3
|  | May |  | 3 | 3
|  | June |  | 3 | 3
|  | July |  | 3
|  | August |  | 3
|  | September |  | 3
|  | October |  | 3
|  | November |  | 3
|  | December | 3 | 3
|  | Rain days allowed per month: | 3 | [5 empty] | The table is only a guide for the compilers of the project in determining contract period for the project.
|  | Rainfall exceeds(mm/day): | 10
|  | Estimated commencement month: | 11 | 2014-11-29 12:00
2014-11-29 12:00
2014-11-29 12:00
|  | Payments for material & goods |  | 1 | [7 empty] | 1
|  | Dispute resolution by litigation |  | 2
|  | The whole of the Works shall be completed in: |  | 19 | Calendar Months
|  | Estimated Date for Practical Completion (for planning purpose) |  | To be determined
|  | Date for Practical Completion |  | To be determined after Commencement
|  | Penalty (R per Calendar Days ) |  | 0.04% of the Contract Price, rounded to the nearest R10
|  | Extend Defects Liability Period for following elements: |  | Electrical, Mechanical and Civil work
SECTIONAL COMPLETION
|  | Date for Section 1 Practical Completion |  | 3 Calendar Months
|  | Penalty: Section 1(R per Calendar Days ) |  | 0.04% of the Contract Price, rounded to the nearest R10
|  | Date for Section 2 Practical Completion |  | N/A
|  | Penalty: Section 2(R per Calendar Days ) |  | 0.04% of the Contract Price, rounded to the nearest R10
|  | Date for Section 3 Practical Completion |  | N/A
|  | Penalty: Section 3(R per Calendar Days ) |  | 0.04% of the Contract Price, rounded to the nearest R10
|  | Date for Section 4 Practical Completion |  | N/A
|  | Penalty: Section 4(R per Calendar Days ) |  | 0.04% of the Contract Price, rounded to the nearest R10
|  | Date for Section 5 Practical Completion |  | N/A
|  | Penalty: Section 5(R per Calendar Days ) |  | 0.04% of the Contract Price, rounded to the nearest R10
|  | Date for Section 6 Practical Completion |  | N/A
|  | Penalty: Section 6(R per Calendar Days ) |  | 0.04% of the Contract Price, rounded to the nearest R10
|  | The percentage advance on materials not yet built into the Permanent Works is: |  | 80%
|  | Percentage retention on amounts due to contractor is: | The Percentage retention is nil. The only security required by the Employer will be such as selected by the Contractor on the Form of Offer and Acceptance and Part 2: CONTRACT DATA PROVIDED BY THE CONTRACTOR, point 2 - Documents, of the Contract Data. | [7 empty] | Amended 13/6/2014
|  | Maximum retention is: |  | 0% | [6 empty] | Amended 13/6/2014
|  | Latent Defect Period is: |  | 5 years after the Final Approval Certificate
|  | Defects Liability Period |  | A time measured from the date of the Certificate of Completion.
|  | Defects Liability Period (Electrical, Mechanical and Civil Works): |  | 12 Months
|  | Defects Liability Period (Works): |  | 12 Months
|  | The determinations of disputes shall be by: |  | ARBITRATION ONLY
|  | The number of Adjudication Board Members is: |  | 1
|  | Insurance by Contractor | 1
|  | Indicated Insured Sum | N/A | Indicated Amount: | 0
|  | Amount in Words | [Amount in Words]
|  | Supplementary Insurance Required | 2
|  | Public Liability Insurance by Contractor |  | 1
|  | Indicated Public Liability Insured Sum |  | 0
|  | Amount in Words |  | [Amount in Words]
|  | Lateral Support insurance |  | 1
|  | Support Insurance by contractor (Amount) |  | 3000
|  | Support Insurance By contractor (Amount in Words) |  | [Amount in Words]
|  | Support Insurance by contractor (Deductible Amount) |  | 0
|  | Support Insurance by contractor (Deductible Amount in Words) |  | [Amount in Words]
Note: All amounts must have the amount in words in brackets
|  | Drawings Number | Description of drawing |  |  | Date |  |  | Revision
|  | ???????? | Site Layout |  |  | 2015-04-12 |  |  | Rev 0
|  | ???????? | etc. |  |  | 2015-04-12 |  |  | Rev 0
|  | ???????? | etc. |  |  | 2015-04-12 |  |  | Rev 0
|  | ???????? | ect. |  |  | 2015-04-12 |  |  | Rev 0
|  | ???????? | ect. |  |  | 2015-04-12 |  |  | Rev 0
|  | ???????? | ect. |  |  | 2015-04-12 |  |  | Rev 0
Annexure's
|  | Standard Preambles for all Trades (Rev 3) - DOH 2009 |  | Annexure 1
|  | General Electrical Specifications |  | Annexure 2
|  | Lightning Protection Specifications |  | Annexure 3
|  | Map of Tender submission location |  | Annexure 4
|  | Joint Venture Agreement |  | Annexure 5
|  | Health and Safety Specification |  | Annexure 6
|  | Health and Safety Bill of Quantities |  | Annexure 7
|  | Builders Lien Agreement |  | Annexure 8
|  | Geotechnical Investigation Report (If applicable) |  | Annexure 9
|  | EPWP Employment Contract |  | Annexure 10
|  | Attendance Register - Infrastructure and Other projects |  | Annexure 11
|  | EPWP Data Collection tool for Phase 3 system |  | Annexure 12
Annexure 13
PRELIMINARY AND GENERAL
PLEASE CHOOSE Item OR N/A IN THE P&G'S NEXT TO EACH ITEM WICHEVER IS APPLICABLE - AS A DEFAULT WILL BE ITEM
Project Specific OHS Specification NOTICE In terms of Section 5(1)(b) of the CONSTRUCTION REGULATIONS 2014 as promulgated on the 7th of February 2014 in the Government Gazette No. 37305, a site specific health & safety specification is to be developed for the intended construction. This then prohibits the use of GENERIC HEALTH & SAFETY SPECIFICATIONS. The new regulations calls for inclusion of an OHS Agent during planning stages of the project so as to enable the development of the document mentioned above for it to be considered during design stage and finally incorporated into the tender document as stated under Sections 5(1)(d) & (f) of the Construction Regulations 2014.
Please note that the DOPW safety officer will prepare the OHS specification for the tender BUT REQUIRE ADEQUATE NOTICE. Compilers of this Data Input must liaise with DOPW to obtain the specification timeously. Document compilers to involve DOPW Safety officers from the outset of documentation stage. If DOPW indicate that they have no capacity, written approval must be obtained from the Project Leader to appoint an additional OHS consultant.
|  | Construction work will exceed | 180 | days
|  | Will involve more than | 1800 | person days of construction work
|  | The works contract is of the value equal to or exceeding: | 20000000
|  | Amount in words: |  |  |  | Don’t put a figure in here at tender stage
|  | CIDB grading: | 6
|  | Health and Safety Agent Name: | Ms L. Ntuli (Head Office)
|  | District Office: | Pietermarizburg
|  | Ward No: | ??
|  | Items | #REF!
|  | Site Office location | 1) The location of the site office should be in an area that will not require visitors to pass through or enter area where construction work is active and will not require the re-location of the office as the project progresses.
|  | Public Safety | 1) When working in a occupied facility the contractors risk assessment and subsequent safe work method statement must take into consideration the negative effect the Contractors activities may have on the health and safety of the occupants of the facility and make provisions for the implementation of all reasonably practicable measures to ensure the health and safety of members of the public.
|  | Extreme weather conditions | 1) If the weather condition poses a threat to the health & safety of employees be it extreme heat, cold, lighting or any adverse weather condition appropriate safety measures have to be taken.
|  | Change to scope of work | 1) Should there be changes to the original scope of work, the Principal Agent must inform appointed Construction Health and Safety Agent to effect changes to the OHSE Specification.
|  | Safety Plan Submission | 1) The successful Tenderer must submit a copy of the detailed OHSE Plan for approval and keep the original for onsite use during construction. The principal Contractor will not be allowed to start site establishment before his/her SHE Plan has been approved in writing.
|  | Bylaws | 1) The Principal Contractor must incorporate any aspects of the Local Municipal bylaws which affect the, Safety and Environmental wellbeing of the employees and the public into his/her OHSE Plan and ensure compliance to such bylaws.
|  | Risk assessment for construction work | 1) To comply with CR(9) and to also address environmental issues
2) Risk Assessment must be done if and when required.
3) DSTI’s must be performed on a daily basis be of an acceptable standard and need to be signed off prior to work starting and at the end of each shift.
4) No work may be performed without an approved DSTI.
See the attached baseline risk assessment to be considered by both the designer and the principal contractor.
|  | Fall protection | 1) To comply with CR (10),
2) Edge protection and protection of floor openings need to be of such a manner as to properly protect employees from falling off elevated positions or falling into floor openings
|  | Structures | 1) To comply with CR (11)
|  | Temporary work | 1) To comply with CR (12)
|  | Excavations | 1) To comply with CR(13) and the following;
2) If the risk exists of a person in an excavation being enclosed in an event of a collapse the following will apply; shoring sufficient to prevent enclosure, any excavated material must be placed at least 1metre from the edge and at the maximum angle of repose to the horizontal.
3) No excavation may affect the stability of any adjoining structure or road unless steps have been taken as identified by an Engineer or a Technologist.
4) Adequate provisions must be made to ensure that water is drained from excavations where water may enter such excavations as a result of seepage or rain
5) All excavations made by the Principal or Sub Contractors must be barricaded by means of solid barricading and barricading tape may only be used to make such barricading more visible
6) If more than one excavation is present on site all excavations must be numbered to ensure effective inspection and control
|  | Demolition work | 1) To comply with CR (14) and the following;
2) Demolition work may only start upon approval of the Demolition Plan by the Client or its duly appointed Agent
3) In the event that a structure identified for demolition incorporates substances such as, lead or asbestos it must be performed within the requirements of the applicable legislative requirements
|  | Scaffolding | 1) To comply with CR(16) and the following;
2) Scaffolding Inspectors and scaffolding Erectors must be different individuals.
3) Scaffold Harness must be used on scaffolding, normal Harnesses may not be used on scaffolding
4) Sufficient Scaffolding material e.g., tags, trapdoors etc. need to be on site as determined by the activities on site
5) Scaffold bases may not be supported by materials such as bricks and chipboard. Suitable material needs to be used as per SANS 10085
6) If more than one scaffold is present on site all scaffolds must be numbered to ensure effective inspection and control
|  | Construction vehicles and mobile plant | 1) To comply with CR (23)
|  | Electrical installations and machinery on construction sites | 1) To comply with CR (24)
|  | Use and temporary storage of flammable liquids on construction sites | 1) To comply with CR (25)
|  | Water environments | 1) To comply with CR (26)
|  | Housekeeping and general safeguarding on construction sites | 1) To comply with CR (27) and the following;
2) Contractor to designate areas for placing refuse and rubble prior to being removed from site
3) Contractor must implement a daily task site clean-up for all activities these should cover work areas, stairways, walkways etc. to free of any construction debris obstruction.
4) Refuse to be separated for recycling purposes
5) Hazardous materials such as asbestos may not be included in general rubble and need to be disposed of as per applicable legislative requirements
|  | Stacking and storage on construction sites | 1) To comply with CR (28)
|  | Fire precautions on construction sites | 1) To comply with CR (29) and the following;
2) No smoking may be permitted on site except in designated smoking areas
|  | Construction employees’ facilities | 1) To comply with CR (30) and the following;
2) Gender signs to be placed at appropriate locations
3) All welfare facilities to be kept in a hygienic condition at all times
4) Employees to be trained in good hygiene practices
5) Toilets to be fitted with doors which can be locked from the inside
6) Toilets to be sufficiently ventilated
7) Contractors or contractors employees are not permitted to any other facilities except those provided by the contractor.
|  | Public Safety & Signage | 1) The Principal Contractor engaged in construction work must ensure that each person working on or visiting a site, and the general public in the vicinity of the construction site, shall be made aware of the dangers likely to arise from onsite activities and the precautions to be observed to avoid or minimise those dangers.
2) Appropriate signage shall be posted at conspicuous points within and around the perimeter of the site. The steps to comply with this requirement must be outlined in the OHSE Plan.
3) The public or visitors may only be permitted on site if they go through an appropriate Health and Safety Induction detailing hazards and risks they may be exposed to and what measures are in place to control these hazards and risks
4) The entire project site must be secured against unauthorized access and provided with appropriate warning signage. Where roadways or walkways must be encroached or closed due to work, adequate barriers shall be installed to safely redirect the flow of vehicles and pedestrians and protect them from construction activities.
5) Whenever it is necessary to maintain public use of work areas (such as sidewalks, ramps, entrances to buildings, corridors, or stairways), the public shall be protected with appropriate guardrails, barricades, temporary fences, overhead protection, or temporary partitions and hoarding. The public must also be adequately protected from any work created hazards, such as excavations. Appropriate warnings, signs, warning lights and instructional safety signs shall be conspicuously posted and placed where necessary.
6) The public must also be protected from falling debris and objects from the project site. Overhead protection shall be provided that will fully protect the public and be capable of withstanding the maximum forces that could be applied from potential falling objects. Special attention shall also be given to developing adequate means to protect against wind-blown debris and construction-related materials.
|  | On Site Health and Safety Training & Induction | 1) The Principal Contractor shall ensure that all site personnel and visitors undergo a Risk-Specific Health & Safety Induction Training Session before starting work or being permitted to enter the site. A record of attendance shall be kept in the health & safety file.
2) The Principal Contractor shall ensure that, on site periodic toolbox talks take place at least once per week. These talks should deal with risks relevant to the construction work at hand. A record of attendance shall be kept in the Health & Safety file. The above should also cover all sub-contractors that are onsite.
3) All Contractors have to comply with this minimum requirement. Environmental issues to be included in toolbox talks where required.
|  | General Record Keeping | The Principal Contractor and all Sub Contractors must keep and maintain Health and Safety records to demonstrate compliance with this Specification, The OHS Act 85/1993; and with the Construction Regulations of 2014. The Principal Contractor shall ensure that all records of incidents/accidents, training, inspections; audits, etc. are kept in a Health & Safety file held in the site office, which must be present on site at all times. The Principal Contractor must ensure that every Sub Contractor opens its own Health & Safety file, maintains the file and makes it available on request.
|  | Health & Safety Audits, Monitoring and reporting | 1) The Client or its duly appointed Agent shall conduct monthly health & safety audits. The Principal Contractor is obligated to conduct similar audits on all Sub Contractors appointed by them at least once a month. Detailed audit reports must be presented and discussed at all levels of project management meetings and a copy of such audit will be provided to the Client or its duly appointed Agent within 7 working days of such audit. Copies of the Client’s audit reports shall be kept in the Principal Contractors Health & Safety File.
|  | Emergency Procedures | 1) The Principal Contractor shall submit a detailed Emergency Plan for approval by the Client prior to commencement on site. The plan shall detail the response procedure including the following key elements:
a. List of key competent personnel;
b. Details of emergency services;
c. Actions or steps to be taken in the event of the specific types of emergencies;
d. Information on hazardous material/situations.
|  | First Aid Boxes and First Aid Equipment | 1) The appointed First Aider(s) to be in possession of a valid first aid training certificate Level 2. Valid certificates are to be kept in the Site Safety File. All Sub Contractors with more than 5 employees shall supply their own first aid box, except if otherwise agreed upon between Principal and Sub- Contractor in writing.
|  | Accident / Incident Reporting and Investigation | 1) Injuries are to be categorised into Near miss, first aid, LTI, fatal etc. Fatal accidents to be reported in addition to applicable legislative requirements to the Client or its duly appointed Agent with immediate effect. The Principal Contractor must stipulate in its construction phase OHSE Plan how it will handle each of these categories. When reporting injuries to the Client, these categories shall be used. The Principal Contractor shall investigate all injuries, with a report being forwarded to the Client immediately. All Sub- Contractors have to report on the abovementioned categories of injuries to the Principal Contractor at least monthly. All categories of incidents/accidents must be in the Statistics Section of the Monthly Audit Reports, submitted to the Client or it’s duly appointed Agent.
|  | Hazards and Potential Situations | 1) The Principal Contractor shall immediately notify other Sub Contractors as well as the Client of any hazardous or potentially hazardous situations that may arise during performance of construction activities.
2) Should a hazardous situation require work stoppages, the work must be stopped and corrective steps taken such as the issue of Written Safe Work Procedures and the issue of Personal Protective Equipment.
|  | Personal Protective Equipment (PPE) and Clothing | 1) The Principal Contractor must ensure that all workers are issued with the required PPE as required by the risks associated with the activities they perform. The minimum PPE to be worn on site will be Safety Shoes/Boots, Hard Hats, Overalls. No Visitors may enter the site without Safety Shoes/Boots and Hard hats. The Principal Contractor and all Sub Contractors shall make provision and keep adequate quantities of SABS approved PPE on site at all times. All employees issued with PPE to be trained in correct use, records of training and issue to be kept in the Site SHE File. Procedure to be in place to deal with:
a. Lost or stolen PPE;
b. Worn out or damaged PPE replacement.
c. Employees not utilising PPE as required
2) The above procedure applies to Principal Contractors and their appointed Sub- Contractors, as they are all employers in their own right.
|  | Permits | 1) The Principal Contractor shall prepare and issue the required written permits relating to but not limited to the following:
a. Hot Work
b. Roof Work
c. Electrical work (both temporary and permanent)
d. Confined Space Entry
2) The Principal Contractor must ensure that where permits are required that they are properly implemented and adhered to.
|  | Speed Restrictions and Protections | Unless otherwise stipulated, the maximum speed limit on sites must be limited to 10 km/h.
1) Vehicle movement routes on site must be clearly indicated where applicable.
2) Signage to ensure the safe movement of vehicles on site, as well as to ensure the health and safety of all employees and visitors on site, must be displayed in strategic locations.
|  | Hazardous Chemical Substances (HCS) | 1) To comply with Hazardous Chemical Substances Regulations as published in Government Notice No. R. 1179 dated 25 August 1995.
2) In addition to the abovementioned, Material Safety Data Sheets must be kept on site for all materials, which may contain hazardous chemical substances
|  | Asbestos | 1) To comply with Asbestos Regulations as published in Government Notice No. R. 155 dated 10 February 2002.
2) Removal to be done by an accredited asbestos contractor
3) Proof of accreditation to be kept on site.
4) Proof of safe systems of work
5) Disposal certificate.
6) Under no circumstances may asbestos be handed over to the community irrespective of shape or condition.
|  | Fire Extinguishers and Fire Fighting Equipment | 1) The Principal Contractor and Sub-Contractors must allow for and provide adequate provision of regularly serviced temporary fire fighting equipment located at strategic points on site, specific for the classes of fire likely to occur.
2) The appropriate notices and signs must be allowed for and be erected as required
3) Contractors may not utilize fire protection equipment belonging to the Client without prior consent
|  | Ladders and Ladder Work | 1) The Principal Contractor must allow for and ensure that all ladders are inspected at least monthly, are in a good safe working order, are the correct height for the task, extend at least 1m above the landing, are fastened and secured and are placed at a safe angle.
2) Records of inspections must be kept in a Register on site
3) All ladders found to be unsafe must be removed from site immediately and not be permitted back onto site until it has been certified as being safe by the Safety Officer or Construction Supervisor.
|  | General Machinery | 1) To comply with Driven Machinery Regulations as published in Government Notice No. R. 1010 dated 18 July 2003
|  | Portable Electrical Tools and Hand Tools | 1) The Principal Contractor shall ensure that all electrical tools, electrical distribution boards, extension leads, and plugs are kept in a safe working order.
2) The Principal Contractor shall ensure that all Portable Electrical Equipment, is clearly numbered, inspected by a Competent appointed person and records of such inspections to be kept on record in an appropriate register on the site SHE file
3) The Principal Contractor shall allow for and ensure the following in relation to hand Tools:
a. That a “Competent Person” undertakes routine inspections and records are kept on site.
b. That only authorized trained persons use the tools.
c. That safe working procedures apply.
d. That PPE is provided and used.
4) All unsafe hand tools and portable electrical equipment found on site need to be removed from site with immediate effect, tagged as unsafe for use and only be permitted back on site after being certified as safe for use by the Safety Officer or the construction Supervisor.
|  | High Voltage Electrical Equipment Installations and Equipment | 1) All Employees must be made aware of the presence and location of High Voltage Equipment such as underground cables and overhead lines, and ensure that the necessary precautionary steps are taken where work has to be executed in the vicinity of such equipment.
2) Precautionary measures such as Isolation and Lock-Out of electrical systems or the use of electrically isolated tools must be used.
|  | Adequate Lighting | 1) All Contractors must allow for and ensure that adequate lighting is provided to allow for work to be carried out safely.
|  | Transportation of Workers | 1) In addition to CR 23 the following will apply. The Principal Contractor and Sub-Contractors shall not:
a. Transport persons together with goods or tools unless there is an appropriate area or section of the vehicle in which to store such goods.
b. Transport persons on the back of trucks except if a proper canopy (properly covering the sides and top) has been provided with suitable seating areas.
c. Permit workers to stand or sit on the edge of the transporting vehicle.
d. Transport workers in LDVs unless they are closed/covered and have the correct number of seats for the passengers.
e. No driver may transport more than six people on the back of a 1 Ton LDV and more than four passengers on the back of a ½ Ton LDV.
2) The driver of any LDV may not permit more than two passengers to occupy the cab of any LDV.
3) Drivers of such vehicles must have a valid driver’s license for the code of vehicle being driven by them.
4) No servicing of vehicles will be permitted on a Construction Site. No Vehicles or machinery leaking oil will be permitted on site due to the risk posed to the environment.
5) Any oil or diesel spilled on site must be cleaned up as per accepted environmental practice.
In the event that Earth Moving Machinery is present on site the following must be adhered to:
a. Drivers of vehicles must be instructed to avoid parking behind earth moving machinery in order to ensure that their vehicles are visible to the operators of earth moving machinery.
b. Right of way must be afforded to earth moving machinery at all times.
c. Vehicles must only be permitted to park, where possible, in designated areas.
|  | Occupational Hygiene | 1) Occupational exposure is a major problem and all Contractors must ensure that proper health and hygiene measures are put in place to prevent exposure to these hazards.
2) All Contractors must prevent inhalation, ingestion and absorption of any harmful chemical or biological agents.
3) Water to be utilized for drinking purposes may only be drawn from taps designated for drinking water purposes. Fire hydrants and fire hose reels may not be utilized for drinking water purposes.
|  | Environmental Management | 1) The Principal Contractor and Sub-Contractors must comply with the requirements of NEMA Act.
2) The Principal Contractor must develop a waste management plan, implement and maintained it onsite.
3 Cement mixing to be done at a predetermined location on site which must include a solid, slab, and bunded edges to prevent runoff.
4) Contaminated run off water from the site must be treated such as to ensure that it does not pose a risk to the environment.
5) Any material which may have a harmful effect when disposed of by normal means must be disposed of in an appropriate manner to eliminate its harmful effect on the environment after disposal.
6) The Principal Contractor must allow for and ensure that adequate procedures are implemented and maintained to ensure that waste generated is placed in suitable receptacles and removed from the site promptly.
7) Plans to deal with spillages must be in place and maintained.
8) No waste materials (liquid or solid) may be disposed of in drains.
9) No burning of waste material may take place on site as such material being burned may result in pollution of the air or give off toxic vapours which could be harmful to the health of employees or any other person present on site.
|  | Alcohol and other Drugs | 1) No alcohol and other drugs will be allowed on site without the express permission of the Principal Contractor.
2) No person may be under the influence of alcohol or any other drugs while on the construction site.
3) Any person on the construction site who is on prescription drugs must inform his/her Employer accordingly and the Employer shall in turn report this to the Principal Contractor immediately.
4) Any person on the construction site who is suffering from any illness/condition that may have a negative effect on his/her safety performance must report this to his/her Employer, who in turn must report this to the Principal Contractor forthwith.
5) Any person on the construction site who is suspected of being under the influence of alcohol or other drugs must be removed from site immediately and be instructed to report back the next day for a preliminary inquiry. A full disciplinary procedure must be followed by the Contractor concerned and a copy of the disciplinary action must be forwarded to the Principal Contractor for his records.
EXAMPLE OF A BASE LINE RISK ASSESSMENT - FOR REFERENCE PURPOSES
|  | Activity | Drilling |  |  |  | Control Measures
|  | Risk to Safety | Entanglement, struck by flying objects, electricity, hazardous substance dust , noise
|  | Risk to Health | Electrocution, dust inhalation, noise induced hearing loss, muscle strain, foreign objects in eyes
|  | Risk to Environmental | Contamination of natural resources (spillages)
|  | Risk to Public Safety | dust , noise
|  | Control Measures | Safe systems of work ,Training, PPE, barricading, Supervision etc.
|  | Activity | Sanding
|  | Safety | Grazing, wrist strain, bumping
|  | Health | Dust inhalation, dust in eyes, minor abrasions
|  | Environmental | none
|  | Public Safety | dust nuisance
|  | Control Measures | Safe systems of work ,PPE, Housekeeping, barricading, Supervision etc.
|  | Activity | Painting
|  | Safety | Bumping against, wrist strain
|  | Health | Inhalation of vapours, paint in eyes , minor abrasions
|  | Environmental | Contamination of natural resources (spillages)
|  | Public Safety | None
|  | Control Measures | Safe systems of work ,PPE, ventilation of area, good housekeeping
|  | Activity | Grinding |  |  |  | Noise induced hearing loss, cuts, loss of limbs, electrocution | none
|  | Safety | Electrocution, entanglement,, tripping hazards, struck by flying materials etc. |  |  |  | Safe systems of work ,Wet cutting, barricading, temporary guarding, signage Supervision ,etc
|  | Health | Noise induced hearing loss, cuts, loss of limbs, electrocution |  |  |  | Noise, dust etc | Safe systems of work ,Wet cutting, barricading, temporary guarding, signage Supervision ,etc
|  | Environmental | none
|  | Public Safety | Noise, dust etc.
|  | Control Measures | Safe systems of work ,Wet cutting, barricading, temporary guarding, signage Supervision ,etc.
|  | Activity | Excavation work
|  | Safety | Hidden services ,bumping against , uncomfortable working position etc.
|  | Health | Back strain , dust inhalation, cuts and abrasions
|  | Environmental | None
|  | Public Safety | None
|  | Control Measures | Safe systems of work , supervision , PPE , Barricading etc.
|  | Activity | Cement Mixing
|  | Safety | Struck by ,sharp edges, poor working position , hazardous substances
|  | Health | Inhalation of cement dust, back strain , dermatitis
|  | Environmental | Contamination of natural resources (spillages)
|  | Public Safety | Noise, dust
|  | Control Measures | Safe Systems of work ,PPE, Housekeeping, barricading, bunding, Supervision etc.
|  | Activity | Plastering
|  | Safety | Grazing abrasions, bumping against, struck by flying/falling objects, slipping hazards, hazardous substances etc.
|  | Health | Minor bruising, particles in eyes, dust inhalation, hazardous substances exposure effects
|  | Environmental | Contamination of natural resources
|  | Public Safety | None
|  | Control Measures | Safe systems of work, training , PPE Supervision ,etc.
|  | Activity | General brickwork
|  | Safety | Abrasive surfaces, hazardous substances , straining of muscles
|  | Health | Cut and abrasions, crushing injuries etc.
|  | Environmental | None
|  | Public Safety | dust
|  | Control Measures | Safe systems of work, barricading, signage PPE ,Supervision etc.
|  | Activity | Compaction of soil
|  | Safety | Struck by tools, flammable substances , flying materials
|  | Health | Back strain, heat exhaustion, bruising, dust inhalation, burns
|  | Environmental | Contamination of resources with fuel
|  | Public Safety | Noise
|  | Control Measures | Safe systems of work, barricading, signage , PPE, Supervision etc.
|  | Activity | Loading and unloading by hand
|  | Safety | Bumping against edges , Hands caught between , Sharp edges, muscle strain
|  | Health | Back strain, exhaustion, bruising, hand injuries,
|  | Environmental | None
|  | Public Safety | None
|  | Control Measures | Safe systems of work, PPE, Training in correct lifting procedures , Supervision etc.
|  | Activity | Ladder use
|  | Safety | Incorrect positioning, overreach , Overhead hazards , dropping of tools from ladder , Falls
|  | Health | Broken bones , death, electrocution
|  | Environmental | None
|  | Public Safety | None
|  | Control Measures | Safe systems of work , PPE usage, Supervision etc.
|  | Activity | Extension cords
|  | Safety | Electricity , tripping hazards
|  | Health | Electrocution , fractures etc.
|  | Environmental | none
|  | Public Safety | None
|  | Control Measures | Safe systems of work, PPE, Supervision etc.
|  | Activity | Hand tools
|  | Safety | Tripping, struck by, bumping against, abrasions, sharp edges, caught between surfaces, flying metal particles etc.
|  | Health | Cuts ,Bruising ,Foreign material in eyes
|  | Environmental | none
|  | Public Safety | None
|  | Control Measures | Safe systems of work, PPE, Supervision etc.
|  | Activity | Scaffolding erection, dismantling
|  | Safety | Falls from height, dropping of items, sharp edges, scaffolding collapse, etc.
|  | Health | Back strain, bruising, cuts, abrasions, broken bones, death
|  | Environmental | none
|  | Public Safety | None
|  | Control Measures | Safe system of work, use of fall arrest equip, erection of safe scaffolding, Supervision, etc.
|  | HEALTH AND SAFETY IMPLEMENTATION COSTING |  |  |  | Only a guide to be priced by contractor
Indicate to Tenderder what they need to provide for Health and Safety costs on this sheet.
|  | ITEM | DESCRIPTION | UNIT | Applicable (A)/ Not Applicable(N/A) |  |  |  | Rates
[5 empty] | (a) |  |  |  | Don’t enter any rates
|  | 1 | MEDICALS | [5 empty] | at tender stage.
|  | 1.1 | Pre-employment medical | Nr.
|  | 1.2 | Re-medicals - yearly | Nr.
TOTAL
|  | 2 | PERSONAL PROTECTIVE EQUIPMENT
|  | 2.1 | Overalls | Nr.
|  | 2.2 | Hard Hats | Nr.
|  | 2.3 | Safety boots/shoes | Nr.
|  | 2.4 | Gloves | Nr.
|  | 2.5 | Gumboots steel toe cap | Nr.
|  | 2.6 | Safety glasses | Nr.
|  | 2.7 | Reflector Bibs | Nr.
|  | 2.8 | Barricading Material | M
|  | 2.9 | Dust masks | Box 20
TOTAL
|  | 3 | FIRE FIGHTING
|  | 3.1 | Fire extinguishers - 4.5Kg | Nr.
|  | 3.2 | Surveys - Annual Service | Nr.
TOTAL
|  | 4 | HEALTH AND SAFETY PERSONNEL
|  | 4.1 | Safety Manager | Nr.
|  | 4.2 | Safety Officer | Nr.
|  | 4.3 | Construction Phase Safety, Health, Environmental and Waste Management Plan | Nr.
TOTAL
|  | 5 | FACILITIES
|  | 5.1 | Provision of ablution facilities | Nr.
|  | 5.2 | Service and maintenance of ablution facilities | Nr.
|  | 5.3 | Provision of eating areas | Nr.
|  | 5.4 | Cleaning of Lay down and other storage areas | Nr.
|  | 5.5 | Wash hand basin | Nr.
|  | 5.6 | Hot and Cold running water | Nr.
|  | 5.7 | Decreasing & Toilet soap | Nr.
TOTAL
|  | 6 | FALL PREVENTION / PROTECTION
|  | 6.1 | Safety harnesses with double lanyards | Nr.
|  | 6.2 | Safety harnesses with Scaffold hooks | Nr.
|  | 6.3 | Lifelines and vertical fall arrest systems | Nr.
|  | 6.4 | Scaffolding – material, erection and inspection (Estimate for project) | Nr.
|  | 6.5 | Temporary hand railing material and kick flats | Nr.
|  | 6.6 | Chin Straps/Toolbags/Wrist straps | Nr.
TOTAL
|  | 7 | FIRST AID
|  | 7.1 | Replenishment of boxes and other supplies | Nr
TOTAL
|  | 8 | TRAINING
|  | 8.1 | SHE Representative | Nr.
|  | 8.2 | First Aid Level 1 | Nr.
|  | 8.3 | Fire Fighting | Nr.
TOTAL
|  | 9 | SIGNAGE
|  | 9.1 | All Signage as required by Law, regulatory, warning and information | Nr.
|  | 9.2 | Posters for awareness | Nr.
TOTAL
|  | 10 | ELECTRICAL
|  | 10.1 | Replacement of Locks required for lockouts | Nr.
|  | 10.2 | Replacement of tags | Nr.
|  | 10.3 | Replacement for Permit books | Nr.
|  | 10.4 | Replacement of Callipers | Nr.
TOTAL
|  | 11 | OTHERS (Project Specific)
|  | 11.1 |  | Nr.
TOTAL
DO A PDF PRINTVIEW OF ALL THE SHEETS SELECTED FROM THE FRONT PAGE TO THE LAST SHEET. INSERT PAGE NUMBERS IN TABLE OF CONTENTS
EQUIPMENT SCHEDULE
TECHNICAL DATA: |  |  | STANDBY GENERATOR
Manufacturer:
Model number:
Serial number:
Voltage
KVA
Frequency
RPM
Cylinder/stroke
Fuel capacity and consumption
Sound pressure level
Condenser air flow rate
Attenuation type
Battery Type
AMF Change Over Panel Type
Starter Motor Type and Voltage
Standard Compliance
TECHNICAL DATA: |  |  | UNINTERRUPTABLE POWER SUPPLY UPS
Manufacturer
Model
Frequency
Harmonic Distortion Reduction
Operating Temperature
Range of Protection – Lightning Strike
KVA
Maximum current, cooling mode
Agent
Telephone number of Agent
Brochure enclosed |  |  | Yes/No
TECHNICAL DATA: |  |  | PARCEL X-RAY UNITS
Manufacturer
Model
Dimension /Size
Resolution
Zoom ranges
External Radiation Levels
Standard Compliance
Electrical nominal voltage |  |  | Volts
Monitor Type and size
Agent
Telephone no of Agent
Brochure enclosed |  |  | Yes/No
TECHNICAL DATA: |  |  | WALK THROUGH DETECTOR
Manufacturer
Model
Timer mode
No of sequential settings per time switch
No of N/O and N/C contacts per setting
Adjustable time lapse between settings
Operating voltage
Operating current
Agent
Telephone number
Brochure enclosed |  |  | Yes/No
TECHNICAL DATA: |  |  | TURNSTILE
Manufacturer
Size
Range
Voltage
Battery Back Up Time
Finish
Agent
Telephone number
Brochure enclosed |  |  | Yes/No
TECHNICAL DATA: |  |  | PARAPLEGIC LIFT
Manufacturer
Panel thickness
Load
Stops
Car Size
Door Opening
Door Type
Speed
Type of Drive
Speed Control
Type of Car and Landing Buttons
Type of Landing Door Frames
Type of Door
Internal Finishes
Pit
Head Room
Battery Type
Method of joining panels
Floor construction
Standard Compliance
Agent
Telephone number of Agent
Brochure enclosed |  |  | Yes/No
TECHNICAL DATA: |  |  | AIR-CONDITIONING AND VENTILATION INSTALLATION
Area:
Manufacturer:
Model number: |  | WCPU
Cooling Tower
Serial number: |  | WCPU
Cooling Tower
Voltage |  |  | V
Starting amps |  |  | A
Running amps |  |  | A
System supply gauge pressure |  |  | kPA
System return gauge pressure |  |  | kPA
Condenser water inlet temperature |  |  | °C
Condenser water outlet temperature |  |  | °C
Condenser water flow rate |  |  | l/s
Blower unit air inlet temperature |  |  | °C
Blower unit air outlet temperature |  |  | °C
Blower unit air flow rate |  |  | m³/s
Conditioned room air temperature after 1 hour, Design |  |  | °C
Conditioned room air temperature after 1 hour, Actual |  |  | °C
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Back to the Top
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Click
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Go To PG02.2
Yes
Yes
Select a Class
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Back to Main Menu
GoTo a Document
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes

## BUILD Sheet (hidden)
Yes
No

## Go To
TENDER & FLY SHEETS |  | CONTRACT DATA | PRICING INSTRUCTION | EPWP
RETURNABLES |  | SCOPE OF WORKS | SITE INFORMATION | OHS
GENERAL
FALSE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
Back to Main Menu
Cover Page
To Table of Contents
Cover Page 2
The Bid Flyer
The Bid
Procedures Flyer
Notice & Invitation to Bid Flyer
T1.1 - Notice & Invitation to Bid
Bid Data Flyer
T1.2 - Bid Data
T1.3 - Conditions of Bid
(Annex F)
Returnable Documents Flyer
T2.1 List of Returnable's
T2.2 Authority to Sign Bid
T2.3 Authority for JV's to sign
T2.4 JV special resolution
T2.6 Schedule of Proposed Contractors
The Contract Flyer
Agreement & Contract Flyer
Form of Offer & Acceptance Flyer
C1.1 Form of Offer & Acceptance substitution pg
Contract Data Flyer
Form of Guarantee Flyer
Pricing Data Flyer
T2.5 JV involvement declaration
T2.11
Declaration of Interest
T2.7 Capacity of Bidders
T2.10 Site Inspection Certificate
T2.9 Preference Cert
T2.12 Record of Addenda
T2.13 Particulars of Electrician
T2.14 Imported Materials & Equipment Schedule
T2.15 Declaration of past SCM practices
C1.2 Contract Data
C1.3 Form of Guarantee
C2.1 Pricing Data
C2.2 GCC P&G
C3.1 Scope of Works
Site Information Flyer
Scope of Works Flyer
C4.1 Site Information
C5.1 List of Drawings
C3.2 HIV Spec
C3.3 HIV Compliance
T2.19 Tax Clearance Certificate Flyer
T2.16 Equipment schedules
T2.36 Functionality Criteria
Map to Pietermaritzburg
Map to Ulundi
Map to Ladysmith
Map to Durban
Spell Check
T2.17 Contractors Safety, Health and Environmental Declaration
T2.8 Financial Standing & Other Resources of Business Declaration
T2.18 Compulsory Enterprise Questionnaire
T2.20 Proof of Good Standing with Comp. Comm.
T2.21a Confirm Receipts of Form of Offer & Acceptance
Bill of Quantities Flyer
T2.23 Proof of Paid Rates & Taxes
T2.24 Proof of UIF Registration
T2.25 The National Industrial Participation form
T2.26 Certificate of Independent Bid
T2.15a Latest Annual Financial Statements
T2.21 Form of Offer & Acceptance
T2.27 Proof of Reg No. on the Prov Suppliers Database
T2.29 Proof of Payment of Bid deposit
T2.28 Certified Proof of CIDB Registration No
EPWP Additional Spec
EPWP Scope
EPWP BQ
OHS Specification (Annex 6)
OHS BQ (Annex 7)
T2.30 Contract Form - Purchase of Goods and Works Part 1
T2.31 Contract Form - Purchase of Goods/Works Part 2
T2.32 Required Structure of Contractor's OHSE Plan
T2.33 Clients specific Req. for Contractors OHSE Plan
T2.34 Base line Risk Assessment
Waiver of Lien (Annex 8)
T2.35 SBD 6.2
Joint Venture Agreement
(Annexure 5)
Tender Advertisment
EPWP Employment
Contract (Annex 10)
EPWP Attendance
Register (Annex 11)
EPWP Data
Collection (Annex 12)

## EPWP Con&Spec
Please complete the areas in blue if this is a EPWP project :
The data is automatically transferred to the EPWP Bill No. 1
THE EPWP CONDITIONS AND SPECIFICATIONS
EPWP CONDITIONS AND SPECIFICATIONS
E12.1 a Employment Targets
The contractor needs to provide a realistic estimate on the number of jobs that the project has the potential to create throughout the project duration as the project will be implemented using labour intensive construction methods on elements where it is economical and feasible for this construction method.
F:............................. V:............................ T:..................................... |  | Item
E12.1 b Employment requirements
Tenderers are advised that this contract will be subject to the Expanded Public Works Program (EPWP) aimed at alleviating and reducing unemployment.
Tenderers must allow for any costs for the employement of unskilled labour as per the requirements of the EPWP program;
1. | 55% of unskilled labour to be women
2. | 55% of unskilled labour to be youth aged between 18 and 35 years
3. | 2% of unskilled labour to be people living with disability
100% | Unskilled labour utilised must reside within the boundries of the Municipality Ward where this contract is executed, with preference to the local community closest or at the walking distance to the contract site. Wherever possible local skilled tradesmen are to be employed on this contract with the view to maximize utilization of local resources.
F:............................. V:............................ T:..................................... |  | Item
E12.1 c Labour rate and payment intervals
The contractor should ensure that labour rate paid to unskilled local labour is commensurate to the daily task. When determining the rate, consideration should be given to that EPWP beneficiaries are mostly bread winners in their families, as the program intends alleviating poverty. There should also be consideration that the labour rate promotes creation of expanded number of jobs created and person days of work.
Contractors should make endeavours to ensure that labourers, particularly unskilled are remunerated on fortnight basis and prior notification be made should there be a shortfall on their wages.
The labour rate for local unskilled shall also be determined in consideration of the location of the project, i.e. for projects implemented in urbanized municipalities will not be the same as that for rural municipalities.
F:............................. V:............................ T:..................................... |  | Item
E12.2 a Labour Intensive Construction (LIC) method
On site there must a person(s) having competency in managing and implementing LIC methods.
*Foreman @ NQF Level 4 the Unit Standard on Implementing LIC methods on site.
*Site Agent/ Managers @ NQF level 5 the Unit Standard on Manage Labour-Intensive Skills Programme both must be CETA accredited
F:............................. V:............................ T:..................................... |  | Item
E12.2 b Labour Intensive Construction Method
Those parts of the contract to be constructed using Labour Intensive methods will be marked in the BoQ with letter LI (indicating Labour Intensive) against every item so designated. Such works will only be constructed using method so indicated.
Reference to be made to Guidelines for the implementation of Labour Intensive Infrastructure projects under EPWP. "Scope of Work in Respect of Work Relating to the Expanded Public Works Programme (EPWP)"
F:............................. V:............................ T:..................................... |  | Item
E12.3 RECORD KEEPING
12.3.1 Every employer must keep in the project site office the following minutes of site progress minutes; contractors’ monthly site progress reports; accurately recorded attendance register; proof of payment as means to verify authenticity of data in the EPWP Beneficiary form submitted with payment certificates. Copies of submitted EPWP beneficiary data forms should also be kept in the site office.
F:............................. V:............................ T:..................................... |  | Item
12.3.2 The employer must keep this record for a period of at least three (3) years after the completion of the project in his/her office as the project site office would have been relocated.
This should be safely kept for job creation data verifications and periodical audits on projects conducted by National and Provincial Department of Public Works after one (1) or two (2) quarters of submitting captured EPWP Data to the National EPWP coordinating Department.
F:............................. V:............................ T:..................................... |  | Item
E12.4 EPWP REPORTING as per EPWP DATA FORM
At the end of each month as part of site progress report and to be attached to every contractors’ progress payment certificate; the contractor shall provide the principal agent & Public Works with a written records, as per EPWP data form; which will be reflecting, beneficiaries full name & surname; ID No and job description of labour employed by main contractor and sub-contractors on site. At the end of each month the contractor must submit the following documents to be attached to the Progress payment certificate: 1. EPWP monthly data collection form 2. Worker monthly payment upload 3. Worker monthly proof of payment i.e 3.1 Acknowledgement of receipt of payment or 3.2 Payslips 3.3 Bank statement highlighted the workers paid 4. Worker monthly training form 5. Monthly attendance register 6. Certified copies of ID’s (once off) 7. ID size photos (once off) 8. Proof of UIF 9. Proof of COIDA
F:............................. V:............................ T:..................................... |  | Item
E12.5 EPWP PROMOTION
12.5.1 EPWP signage board
EPWP Program at the project level shall always be promoted through have the projects signage board that embrace EPWP logo at the bottom, correct measurement for this signage board will be provided by the project leader during the site handing over meeting. the standard "HELVETIVA MEDUIM " letters are to be used . Professional title to be 10 mm above line . Line thickness to be 8 mm thick . Space between bottom of the line and bottom of the lettering below the line has to be 100 mm. Letter sizes are as follows : Helvetica meduim 100 mm black upper case to be for project name and owner . Helvetica meduim 75mm black upper case only to be used for professional titles.Project name and owner shall be black lettering on white background.board sizes are as follows : Board to be minomum 2000mm from ground level and to be constructed from reinforced formed chromadek panels minimum 0,6mm thick chromadek. The contractor is responsible for ensuring that the project board remains neatly and safely erected for the full duration including maintenance period,after which the project board and post are to be dismantled and handed to the client in good order.
F:............................. V:............................ T:..................................... |  | Item
12.5.2 Branding of labour apparel
Contractor & Sub-contractors’ labourers shall be provided with EPWP branded Personal Protective Equipment (PPE), reflector vest with EPWP wording at the back is an ideal and cost effective means of promoting program on site.
The contractor is then advised to price for both item 17.5.1 and 17.5.2
F:............................. V:............................ T:..................................... |  | Item
E12.6 COMMUNITY LIAISON OFFICER (CLO)
UTILISATION OF A COMMUNITY LIAISON OFFICER
The Contractor shall allow for and pay any and all costs necessary for the engagement of the services of a Community Liaison Officer (CLO) for the full duration of this contract
A CLO will be identified by the local structures of the ward areas and appointed following fair and transparent interviewing process, to be conducted in the presence of local structures and the contractor representative, in order to assist the Contractor in the procurement of any local labour, etc. required for this project. The Contractor is to liaise with the CLO and afford him any assistance needed in ensuring sound working relations with the local community.
Key Responsibilities of the CLO are envisaged to include and not necessary be limited to:
1. Assisting local leadership in conducting skills and resources audit which facilitates sourcing labour from within the ward or targeted areas for employment, as required by contractor.
2. Assisting in sourcing labour-only domestic sub-contractors and the procurement of materials from local resources, as required by the contractor.
3. Assisting the contractor by identifying areas of potential conflict and or threats to the project or to stakeholders in the project and recommend appropriate action to the contractor.
4. Assisting contractor and stakeholders in the project in the resolution of any conflict which may arise.
5. Establishing and ensuring that sufficient and open communication channels between the contractor and the work force are maintained.
6. Establish and ensuring that efficient and open communication channels between the contractor and the community are maintained
7. Identifying and reporting to the Contractor regarding issues where communication between stakeholder is necessary, recommend courses of action and facilitate such communications
8. Assisting the Contractor and the work force in the establishment of grievance procedures and necessary recommenda-tion to the Contractor regarding the grievances and solution thereto.
9. Attending to site meetings and project implementation meetings as required by the Contractor and prepare periodic reports as may be required by the Contractor from time to time.
10. Attending to such other duties which are consistent with the functions of a CLO, as may be required by the Contractor from time to time.
Tenderers are to price twice the rate of unskilled local labour rate against this item for any and all costs arising out of compliance with the foregoing and in the event of a Tenderer failing to price against this item or making inadequate financial provision against this item for compliance as aforesaid, then no claim for costs or additional cost incurred will be entertained by the Head: Works
F:............................. V:............................ T:..................................... |  | Item
E12.7 SKILLS DEVELOPMENT ON SITE
Contractor in conforming to the object of EPWP that its beneficiaries need to be capacitated with skills that will render them employable in the future. It is then the responsibility of the Contractor that mandatory life skills are provided to 100% of workforce on site and on the job training to labourers from whom the potential for further development has been identified. The latter is not mandatory to all as it covers technical skills.
Contractor should also make provision for the possibility that there might be local youth that will need to be placed on the project with an intention to be provided support towards improving their level of competency and productivity.
Contractor shall also provide all necessary on-the-job training to targeted labour to enable such labour to master and advance on techniques required to undertake the work in accordance with requirements of the contract in a manner that does not compromise workers health and safety.
F:............................. V:............................ T:..................................... |  | Item
E12.8 LABOUR ONLY Sub Contracting for local emerging enterprises
Tenderer’s are advised that this contract is subject to the Expanded Public Works Programme (EPWP) and the following criteria will apply:
African Equity Ownership
a) The Tenderer is to allow for 5% of the total value of works to be undertaken by a Priority Population Group. This percentage excludes the costs of employing local unskilled labour. The allocation of this percentage from the Project, the screening of people, the selection of skills, will be for the Contractor to adjudicate.
b) The Priority Population Group consists of women, youth and disabled people.
c) The Contractor is to give first option for prospective PPG’s from the surrounding areas of the Project. Should there be insufficient suitable people fitting the criteria of PPG’s, the Contractor may hire people from further afield. This is to be done only after consultation with the Department of Works EPWP Co-ordinator and the Community Liaison Officer (CLO).
d) A Mentor is to be employed by the Contractor, in consultation with the Department of Works for the purposes of quality control and liaison between the Contractor and the selected PPG’s on site. The mentor will be responsible for ensuring an acceptable level of quality workmanship and that such work carried out by the PPG's is executed within the time frames stipulated.
In so far as possible, the Contractor is encouraged to expand the PPG’s skills, knowledge and performance levels.
F:............................. V:............................ T:..................................... |  | Item
TENDERER’S TO NOTE CONDITIONS
a) The contract to be entered into between the Contractor and the PPG’s will be a LABOUR ONLY sub-contract.
b) The Contractor will be responsible for ensuring that all materials for use by the PPG’s in the works are to be on site timeously. The Contractor shall liaise with The Mentor and PPG to determine the nature and extent of materials required and the lead time necessary.
c) The Contractor shall be responsible for the overall programming of the Works and he is to allow for monitoring the PPG’s programme and progress.
d) In conjunction with the Mentor, he is to allow for the supervision and mentoring (where necessary) of the PPG to ensure quality and adherence to standard building practice
e) The Contractor is to allow for extra storage facilities on site for the PPG’s tools and equipment.
f) Basic tools shall be provided by the PPG’s and where these are not available; the Contractor will supply him with the necessary tools and equipment and deduct the costs thereof from the interim claims made by the PPG.
g) Work requiring specialized tools will be provided free of chargeby the Contractor with the provision that these be returned upon completion of the Work.
CO-ORDINATION
The Contractor is to co-ordinate the work of all the PPG’s, Sub-Contractors and Nominated Sub- Contractors appointed direct by the Employer in such a manner and at all times as will suit the building programme and he is to allow adequate access, for the PPG’s, where required, to carry out their work in an efficient manner as no claims for extras in this connection will be entertained.
ATTENDANCE
The Contractor may allow for attendance upon the PPG’s concerned to execute the work. The Contractor is to allow the PPG’s the use of any scaffolding belonging to him while it remains so erected on the site.
Where scaffolding is necessary for the use by any PPG and the Contractor has not erected any for his own use or has removed same after his own use, the Contractor shall supply sufficient scaffolding to the PPG to be erected and dismantled by the PPG and returned to the Contractor.
This attendance upon PPG’s to execute the work is to include for the scaffolding provisions as aforesaid and, in addition, is to include for co-operating to the fullest extent with all the parties, attending on off-loading materials, providing suitable storage for tools and materials used by the PPG’s, use of general facilities such as latrines, etc., supply and cost of power, lighting, water and the like.
E12.9 EPWP CONTRACT FOR LABOUR
It is compulsory that shortly after the contractor and or sub contractor has appointed local labour, the employment contract should be signed by both parties, prior to commencement with works on site. The employment contract forms part of the Ministerial Determination or from the regional EPWP officials. Each contract will lapse at the end of each financial year therefore requiring the Contractor to do a renewal of each contract should the need of employment still exist for that particular labourer.
F:............................. V:............................ T:..................................... |  | Item
E12.10 EPWP SCOPE of WORK
Note:
Contractors are to price any item on the Bill of Quantities having below, bearing in mind that they are regarded as main sources of job creation, whether sub contracted or undertaken by the main contractor.
Elements on the scope of work where application of Labour Intensive Construction methods as will indicated with letters (LI) are regarded feasible are as follows;
i) Excavating trenches for foundations and any other civil works with the depth not more than 1.5 m
ii) All masonry works which include concrete mixing on site; brickwork; plastering; screed works; jointing; etc.
iii) Painting, Plumbing, Ironmongery; roof cladding; glazing; tilling; carpentry; flooring; waterproofing; etc.
iv) External works such as landscaping; cleaning; paving; fencing; tarmac; etc.
Note:
It is a general requirement of this contract that persons normally resident in the ward of the works (local labour) be given preference for employment on the contract. Provided, however, that should adequate and appropriate labour not be available within the ward, others may be employed subject to satisfactory proof being provided that every reasonable endeavour has been made to employ local labour (Local Sub-contractor(s); Skilled; Semi-Skilled and Unskilled). The contractor shall in consultation with the local community leaders with the purpose of negotiating with them regarding the utilization of local resources in the construction process. In this regard, the contractor shall furthermore give preference, wherever possible to the employment of single heads of households, women and youth as well as families declared as most indigent by War on Poverty/ Sukuma Sakhe program profiling process. The contractor should aim, in general, to maximise the involvement of the local community, however workers from other communities should not exceed 20% of all persons working on the project, where local employees possess skills at level of competency that meet contractors requirements.
Back to Main Menu
Go To a Document
To P&G's

## Datafordrops (hidden)
Date | 2025-06-25 11:29
Evaluation Method | Evaluation Method 1
Evaluation Method 2
Evaluation Method 3
Evaluation Method 4
Method of Measurement | Standard System of Measuring Builders Work (6th Edition) | Standard System of Measuring Building Works for Small or Simple Buildings 1999
Standard System of Measuring Builders Work (7th Edition)
Standard System of Measuring Building Works for Small or Simple Buildings 1999
Civil Engineering Standard Method of Measurement Southern African (Edition 3)
Other (Specify)
Adjudication Board Members: | One
Three
Insurance Contractor | Aggregate value of insured sum as Cl. 8.6.1.1
indicated sum
Public Liability Insurance by Contractor | Sum of R5 million
Indicated sum
CPAP (See P&G – A32) | Yes
No
Bill of Quantity/Lump Sum | Bills of Quantities
Lump Sum
Price Preference Ratio | 20000000 | 1
| No | exceed
Lateral Support insurance | Yes
No
Payments for material & goods | Yes
No
Dispute resolution by litigation | Yes
No
Supplementary Insurance Required | Yes
No
Alternative bid offer permitted | Yes
No
LA Building, King Dinuzulu highway, Ulundi 3838
Principal Agent Capacity | Engineer/Principal Agent
Project Leader
Project Manager
Location of Regional Office | Head Office
| EThekwini Region |  |  |  | http://www.kznworks.gov.za/ContactUs.aspx
Midlands Region
North Coast Region
Southern Region
Addresses of bid openings | KZN Department of Public Works, 191 Prince Alfred Street, Pietermaritzburg, 3200 at the time indicated on T1.1 Notice and Invitation to Bid
KZN Department of Public Works, eThekwini Region Office, (Ground Floor), 455A, Jan Smuts Highway, Mayville, 4091 at the time indicated on T1.1 Notice and Invitation to Bid
KZN Department of Public Works, Midlands Region Office, 40 Shepstone Road, Ladysmith, 3370 at the time indicated on T1.1 Notice and Invitation to Bid
KZN Department of Public Works, 1st Floor, Northern Region Office, Legislative Assembly & Administration Building, King Dinuzulu highway, ULUNDI at the time indicated on T1.1 Notice and Invitation to Bid
KZN Department of Public Works, Southern Region Office, 10 Prince Alfred Street, Pietermaritzburg, 3200 at the time indicated on T1.1 Notice and Invitation to Bid
Site Inspection | Compulsory | Compulsory
Non-Compulsory
JBCC Civil | Yes
No
Bidders may offer to submit bid for the following | Only the complete Service as per the Bills of Quantities
The Electrical
The Mechanical
Number of days to submit priced BoQ | 0
14
21
30
Standard Procurement Procedure | PP1 - Negotiation Procedure
PP2 - Competitive Selection Procedure
PP3 - Competitive Negotiation Procedure
Contracting Strategy | Design by Employer
Design and Build
Management Contractor / Construction Management
Develop and Construct
Banking Reference Numbers | Head Office | Ref No 14019605
| Ethekwini Region | Ref No 14019613
| Midlands Region | Ref No 14019621
| North Coast Region | Ref No 14019639
| Southern Region | Ref No 14019647
|  | Telephone | Fax | email
| Head Office | 033 - 8971300 | 033 - 8971399
| Ethekwini Region | 031-203 2210 | 031-261 5044
| Midlands Region | 036-638 8071 | 036-638 8050
| North Coast Region | 035 - 874 3349 | 035-874 2519
| Southern Region | 033-897 1421/1422 | 033-897 1399
Type of Procedures | PP2A-Nominated Procedure | Nominated Procedure
| PP2B-Open Procedure | Open Procedure
| PP2C-Qualified Procedure | Qualified Procedure
| PP2D-Quotation Procedure | Quotation Procedure
| PP2E-Proposal Procedure using the two envelope system | Proposal Procedure using the two envelope system
| PP2F-Proposal Procedure using the two stage system | Proposal Procedure using the two stage system
| PP2G-Shopping Procedure | Shopping Procedure
| PP3A-Restricted Competitive Negotiations | Restricted Competitive Negotiations
| PP3B-Open Competitive Negotiations | Open Competitive Negotiations
Months | January
February
March
April
May
June
July
August
September
October
November
December
Preliminary and General in terms of: | Alternative A
Alternative B
| Model Preambles for Trades - 2008 | 1 to 49
| Standard Preambles for all Trades (Rev 3) - DOH 2009 | 1 to 95
EPWP Project | Yes
N/A
Do you require BoQ with bid? | Yes
No

## ClassDropdown (hidden)
1 | Civil engineering works - CE | CE
2 | Electrical engineering works (Infrastructure) - EP | EP | Selected option:
3 | Electrical engineering works (buildings) - EB | EB | 10 | SF
4 | General building works - GB | GB
5 | Mechanical Engineering Works - ME | ME
6 | The extension, installation, repair, maintenance or renewal, or removal, of asphalt - SB | SB
7 | The development, extension, installation, removal, and dismantling, as relevant, associated with building excavations, shaft sinking and lateral earth support - SC | SC
8 | The development, extension, installation, repair, renewal, removal, or alteration of corrosion protection systems (cathodic, anodic and electrolytic) - SD | SD
9 | Demolition of buildings and engineering infrastructure and blasting - SE | SE
10 | The development, extension, installation, renewal, removal, renovation, alteration or dismantling of fire prevention and protection infrastructure (drencher and sprinkler systems and fire installation) - SF | SF
11 | The development, extension, installation, renewal, removal, renovation, alteration or dismantling of glazing, curtain walls and shop fronts - SG | SG
12 | The development, extension, installation, maintenance, renewal. removal, alteration or dismantling, as relevant, of landscaping, irrigation and horticultural works - SH | SH
13 | The development, extension, installation, repair, maintenance, renewal. removal, renovation, alteration or, dismantling of lifts, escalators, travellators and hoisting machinery - SI | SI
14 | The development, installation, removal, or dismantling, as relevant, of piles and other specialized foundations for buildings and structures - SJ | SJ
15 | The installation, renewal, removal, alteration or dismantling, as relevant, road markings and signage - SK | SK
16 | The development, extension, installation, renewal. removal, renovation, alteration or dismantling of structural steelwork and scaffolding - SL | SL
17 | SM Timber buildings and structures - SM | SM
18 | The extension, installation, repair, maintenance, renewal, removal, renovation or alteration, as relevant, of the waterproofing of basements, roofs and walls using specialist systems. - SN | SN
19 | The development, extension, installation, renewal, removal, alteration or dismantling or demolition of water installations and soil and waste water drainage associated with buildings (wet services, plumbing) - SO | SO
20 | The development, extension, installation, repair, removal, alteration, dismantling or demolition of precast concrete or steel fencing - SQ | SQ

## ClassList
Please choose a class from the list below by clicking onto the relevant option :
Back to Master Data

## GoTo (hidden)
Click onto the links below to go to that particular document.
| Notice and Invitation to Tender | Form of Offer and Acceptance - (Bound into Volume 1 of 2)
| Tender Data | Contract Data
| Annexure F - Standard Conditions of Tender | Form of Guarantee
Pricing Instructions
| List of Returnable Documents | Preliminaries for GCC for Construction Works, 1st Edition
| Authority to Sign Tender | Bills of Quantities
Authority for Consortia or JV’s to Sign Tender
Special Resolution of Consortia or JV’s
Joint Venture Involvement Declaration
| Schedule of Proposed Sub-Contractors | Scope of Works
| Capacity of Tenderer | Specification for HIV/AIDS awareness
| Financial Standing & Other Resources of Business Declaration | HIV/STI Compliance report
Preference Certificate
Site Inspection Meeting Certificate - (if applicable)
Declaration of Interest
| Medical Certificate: Confirmation of Permanent Disabled Status | Site Information
Record of Addenda to Tender Documents
Particulars of Electrical Contractor
Schedule of Imported Materials and Equipment
Declaration of Bidder’s Past SCM Practices
| Equipment Schedules-Mechanical / Electrical / Security Material | List of Drawings/Annexures
Contractor's Safety, Health and Environmental Declaration
Compulsory Enterprise Questionaire
Certified Proof of Enterprise's Registration & Good Standing with the Compensation Commisioner (Attach)
Form of Offer and Acceptance - (Bound into Volume 1 of 2)
Final Summary of Bill of Quantities
PART T1 - TENDER PRODECURES
PART T2 - RETURNABLE DOCUMENTS
PART C1 - AGREEMENT AND CONTRACT DATA
PART C2 - PRICING DATA
PART C3 - SCOPE OF WORKS
PART C4 - SITE INFORMATION
DRAWINGS / ANNEXURES
Back to Main Menu
Enter Data

## GB Rating (hidden)
Type in BOQ Final Estimate here to determine rating:
20000000 |  | MAX
Qualifying CIDB : | Designation | Less than or equal to | 20% Added
6 | 2 | 1000000 | 1200000 | 780001
| 3 | 3000000 | 3600000 | 2400001
| 4 | 6000000 | 7200000 | 4800001
| 5 | 10000000 | 12000000 | 7800001
| 6 | 20000000 | 24000000 | 15600001
| 7 | 60000000 | 72000000 | 48000001
| 8 | 200000000 | 240000000 | 156000001
| 9 | No Limit | No Limit
Contractors CIDB rating based on estimate | 6
SF
6SF
6
B-BBEE status level of Contributor
Points according to status level
Level 1 | 20 | 20
Level 2 | 18 | 18
Level 3 | 14 | 14
Level 4 | 12 | 12
Level 5 | 8 | 8
Level 6 | 6 | 6
Level 7 | 4 | 4
Level 8 | 2 | 2
Non-compliant contributor | 0 | 0

## Tender Fee (hidden)
Construction
20000000
Qualifying CIDB : | Designation | Less than or equal to | 20% Added
450 | 0 | 1 | 500000
| 190 | 500001 | 1000000
| 270 | 1000001 | 2000000
| 330 | 2000001 | 5000000
| 380 | 5000001 | 10000000
| 450 | 10000001 | 20000000
| 500 | 20000001 | 40000000
| 610 | 40000001 | 130000000
| 820 | > R130,000,000
| Effective date: |  | 2017-04-01

## Cover Page-Section 1 of 2
PROVINCIAL ADMINISTRATION OF KWAZULU-NATAL
DEPARTMENT OF PUBLIC WORKS & INFRASTRUCTURE
Please do a print preview before printing
BILLS OF QUANTITIES
with GCC for Construction Works - Second Edition 2010
RETURNABLE DOCUMENT
ONE VOLUME APPROACH
KZN Public Works: 191 Prince Alfred Street
Engineer/Principal Agent | [Identify Agent's Service, eg. Engineer]
[Identify the Company or person] | [Agents Name]
[P.O. Box number] | [P.O. Box number]
[Name of town] | [Name of town]
[Name of City] | [Code]
[Code]
[Telephone Number including Area Code] - Tel Number | [Tel Number including Area Code] - Tel Number
[Fax Number including Area Code] - Fax Number | [Fax Number including Area Code] - Fax Number
[Email Address] | [Email Address]
Employer: | Region:
Head: Public Works | Regional Manager
KZN Department of Public Works | KZN Department of Public Works
Private Bag X 9041 | X9041
PIETERMARITZBURG | Pietermarizburg
3200 | 3200
Tel Number: 033 - 8971300 | Tel Number: | 033-897 1421/1422
Fax Number: 033 - 8971399 | Fax Number: | 033-897 1399
Tender Number: ZNTM012345W | Project Code: | 012345
CIDB Grading: 6SF | Document Date: | As Per Tender Advert
ECDP Number: N/A | Contract Period: | 19 Calendar Months
Contracting Party: _____________________________________________________________________________
CIDB Registration number: | __________________________________
Central Suppliers Database Registration Number: | __________________________________
Back to Main Menu
Print
Print Preview
Enter Data

## Cover Page 2
PROVINCIAL ADMINISTRATION OF KWAZULU-NATAL
DEPARTMENT OF PUBLIC WORKS & INFRASTRUCTURE
BILLS OF QUANTITIES
Please do a print preview before printing
FOR
KZN Public Works: 191 Prince Alfred Street
[Identify Agent's Service, eg. Engineer] | [Identify Agent's Service, eg. Engineer]
[Agents Name] | [Agents Name]
[P.O. Box number] | [P.O. Box number]
[Name of town] | [Name of town]
[Code] | [Code]
Tel Number [Tel Number including Area Code] | Tel Number [Tel Number including Area Code]
Fax Number [Fax Number including Area Code] | Fax Number [Fax Number including Area Code]
[Email Address] | [Email Address]
Employer | Region
Head: Public Works | Regional Manager
KZN Department of Public Works | KZN Department of Public Works
Private Bag X 9041 | X9041
PIETERMARITZBURG | Pietermarizburg
3200 | 3200
Tel Number: 033 - 8971300 | Tel Number: | 033-897 1421/1422
Fax Number: 033 - 8971399 | Fax Number: | 033-897 1399
Tender Number: ZNTM012345W | Project Code: | 012345
CIDB Grading: 6SF | Document Date: | As Per Tender Advert
ECDP Number: N/A
Back to Main Menu
Print
Print Preview
Enter Data

## Table of Contents
KZN Public Works: 191 Prince Alfred Street
Compiler to check page numbers after pdf printview has been done to determine the consecutive page numbers
THE TENDER
1. | PART T1: TENDER PROCEDURES |  |  |  | Page No. |  | Colour Coding in accordance with CIDB
| T1.1 | Tender Notice and Invitation to Tender |  |  | 9 |  | White |  | 8 |  |  | Pages
| T1.2 | Tender Data |  |  | 14 |  | Pink |  | 13 |  |  | Pages
| T1.3 | Annexure C - Standard Conditions of Tender |  |  | 19 |  | White |  | 18 |  |  | Pages
2. | PART T2: RETURNABLE DOCUMENTS
| T2.1 | List of Returnable Documents |  |  | ?? |  |  | 3 | 30 |  |  | Pages
| T2.2 | Authority to Sign Tender (T2.2) |  |  | ?? |  |  | 1 | 32 |  |  | Page
| T2.3 | Authority for Consortia or Joint Venture’s to Sign Tender (T2.3) |  |  | ?? |  |  | 2 | 33 |  |  | Pages
| T2.4 | Special Resolution of Consortia or Joint Venture’s (T2.4) |  |  | ?? |  |  | 3 | 35 |  |  | Pages
| T2.5 | Joint Venture Involvement Declaration (T2.5) |  |  | ?? |  |  | 2 | 38 |  |  | Pages
| T2.6 | Schedule of Proposed Sub-Contractors (T2.6) |  |  | ?? |  |  | 1 | 40 |  |  | Page
| T2.7 | Capacity of Tenderer (T2.7) |  |  | ?? |  |  | 6 | 41 |  |  | Pages
| T2.8 | Financial Standing and other resources of Business Declaration (T2.8) |  |  | ?? |  |  | 1 | 47 |  |  | Page
| T2.9 | Preference Points Claim Form (T2.9) |  |  | ?? |  |  | 5 | 48 |  |  | Pages
| T2.10 | Site Inspection Certificate as proof for attendance of compulsory briefing meeting (T2.10) |  |  | ?? |  |  | 1 | 53 |  |  | Page
| T2.11 | Bidder's Disclosure - SBD 4 (T2.11) |  |  | ?? |  |  | 3 | 54 |  |  | Pages
| T2.12 | Record of Addenda to Tender Documents (T2.12) |  |  | ?? |  |  | 1 | 57 |  |  | Page
| T2.13 | Particulars of Electrical Contractor (T2.13) |  |  | ?? |  |  | 1 | 58 |  |  | Page
| T2.14 | Schedule of Imported Materials and Equipment (T2.14) |  |  | ?? |  |  | 5 | 59 |  |  | Pages
| T2.15a | Annual Financial Statement for past financial year (2.15) |  |  | ?? |  |  | #REF! | 60 |  |  | #REF!
| T2.16 | Equipment Schedules (T2.16) |  |  | ?? |  |  | 1 | 63 |  |  | Page
| T2.17 | Contractor's Safety, Health and Environmental Declaration (T2.17) |  |  | ?? |  |  | 1 | 68 |  |  | Page
| T2.18 | Compulsory Enterprise Questionaire (T2.18) | [5 empty] | 2 | 69 |  |  | Pages
| T2.19 | Tax Compliance Status (TCS) PIN to verify on line Compliance Supplier Status via e-Filing (T2.19) |  |  | ?? |  |  | 1 | 71 |  |  | Page
| T2.20 | Proof of Good Standing With the Compensation Commissioner (T2.20) |  |  | ?? |  |  | 1 | 72 |  |  | Page
| T2.21 | Form of Offer and Acceptance (Bound into Section 1 of 2) (T2.21) |  |  | ?? |  |  | 5 | 73 |  |  | Pages
| T2.21a | Confirm Receipt of Offer and Acceptance (T2.21a)
| T2.22 | Final Bill of Quantity (T2.22) |  |  | ?? |  |  | 1 | 79 |  |  | Page
| T2.23 | Certified Proof of Paid Municipal Rates and Taxes (Attach) (T2.23) |  |  | ?? |  |  | 1 | 80 |  |  | Page
| T2.24 | Proof of Unemployment Insurance Fund (2.24) |  |  | ?? |  |  | 1 | 81 |  |  | Page
| T2.25 | The National Industrial Participation Programme (T2.25) |  |  | ?? |  |  | 2 | 82 |  |  | Pages
| T2.26 | Proof of Registration on the Central Supplier Database (CSD) (T2.26) |  |  | ?? |  |  | 2 | 84 |  |  | Pages
| T2.27 | Certified Proof of CIDB Registration Number (T2.27) |  |  | ?? |  |  | 2 | 86 |  |  | Pages
| T2.28 | Proof of Deposit (T.28) |  |  | ?? |  |  | 1 |  |  |  | Page
| T2.29 | Contract Form - Purchase of Goods/Works - Part 1 (T2.29) |  |  | ?? |  |  | 1 |  |  |  | Page
| T2.30 | Contract Form - Purchase of Goods/Works - Part 2 (T2.30) |  |  | ?? |  |  | 1 |  |  |  | Page
| T2.31 | OHSE Plan Structure (T2.31) |  |  | ?? |  |  | 2 |  |  |  | Pages
| T2.32 | Client's specific requirements for the Contractor's detailed OHSE Plan (T2.32) |  |  | ?? |  |  | 8 |  |  |  | Pages
| T2.33 | Baseline Risk Assessment (T2.33) |  |  | ?? |  |  | 1 |  |  |  | Page
| T2.34 | Functionality Criteria (T2.34) |  |  | ?? |  |  | 3 |  |  |  | Pages
| T2.35 | Invitation to Tender - SBD 1 (T2.35) |  |  | ?? |  |  | 3 |  |  |  | Pages
| T2.36 | CIDB B U I L D Programme Undertaking (T2.36) |  |  | ?? |  |  | 3
THE CONTRACT
3. | PART C1: AGREEMENT AND CONTRACT DATA
| C1.1 | Form of Offer and Acceptance |  |  | ?? |  |  | 5 | 91 |  |  | Pages
| C1.2 | Contract Data |  |  | ?? |  | White | 7 | 93 |  |  | Pages
| C1.3 | Form of Guarantee (C1.3) |  |  | ?? |  |  | 2 | 99 |  |  | Pages
4. | PART C2: PRICING DATA
| C2.1 | Pricing Instructions |  |  | ?? |  |  | 4 | 103 |  |  | Pages
| C2.2 | Bills of Quantities |  |  | ?? |  |  | 70 | 119 |  |  | Pages
5. | PART C3: SCOPE OF WORKS
| C3.1 | Scope of Works |  |  | ?? |  |  | 8 | 121 |  |  | Pages
| C3.2 | Specification for HIV/AIDS awareness |  |  | ?? |  |  | 3 | 128 |  |  | Pages
| C3.3 | HIV/STI Compliance report |  |  | ?? |  |  | 2 | 131 |  |  | Pages
6. | PART C4: SITE INFORMATION
| C4.1 | Site Information |  |  | ?? |  |  | 1 | 134 |  |  | Page
7. | DRAWINGS
| C5.1 | List of Drawings |  |  | ?? |  |  | 2 | 136 |  |  | Pages
8. | ANNEXURES | [7 empty] | 137
| Annexure 1 |  | Standard Preambles for all Trades (Rev 3) - DOH 2009 | 1 to 95 |  |  |  |  | 5/11/2014-WITHDRAWN |  | Generic Construction Safety, Health and Environmental Specification |  |  | H1 to H33
| Annexure 2 |  | General Electrical Specifications | E/1 to E/20
| Annexure 3 |  | Lightning Protection Specifications | LP/1 to LP/6 |  |  |  |  | C3.6 | Supplementary Preambles |  |  | SUP1 to SUP5
| Annexure 4 |  | Map of Tender submission location
| Annexure 5 |  | Joint Venture Agreement
| Annexure 6 |  | Health and Safety Specification
| Annexure 7 |  | Health and Safety Bill of Quantities
| Annexure 8 |  | Builders Lien Agreement | [6 empty] | 7 | Pages
| Annexure 9 |  | Geotechnical Investigation Report (If applicable) | [6 empty] | 3 | Pages
| Annexure 10 |  | EPWP Employment Contract
| Annexure 11 |  | Attendance Register - Infrastructure and Other projects
| Annexure 12 |  | EPWP Data Collection tool for Phase 3 system
Annexure 13
IMPORTANT NOTICE TO TENDERERS
Any reference to words Tender or Tenderder herein and/or in any other documentation shall be construed to have the same meaning as the words Tender or Tenderer. These forms are for internal and external use for the KZN Department of Public Works, Provincial Administration of KwaZulu-Natal.
"Quality" shall mean totality of features and characteristics of a product or service that bears on the ability of the product or service to satisfy stated or implied needs.
No alternativeTenders will be accepted. The Total (Including Value Added Tax) on the Final Summary of the Bill of Quantities must be carried to the "Offer" part only of the Form of Offer and Acceptance - T2.21 "Enterprise" shall mean the legal Tendering Entity or Tenderer who, on acceptance of the Offer, would become the contractor"
Please do a print preview before printing
Back to Main Menu
Print
Print Preview
Enter Data

## TheTender-fly
KZN Public Works: 191 Prince Alfred Street
THE TENDER
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T1_TheTender Procedure-fly
KZN Public Works: 191 Prince Alfred Street
PART T1. - TENDER PROCEDURES
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T1.1_Notice & Inv to tender-fly
KZN Public Works: 191 Prince Alfred Street
T1.1 - TENDER NOTICE AND INVITATION TO TENDER
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T1.1_Tender Notice & Invitation
T1.1 TENDER NOTICE AND INVITATION TO TENDER
THE KZN DEPARTMENT OF PUBLIC WORKS & INFRASTRUCTURE INVITES TENDERS FOR THE PROVISION OF:
Project title: |  |  | KZN Public Works: 191 Prince Alfred Street
Tender no: |  |  | ZNTM012345W | Project Code: |  |  | 012345
Advertisement date: |  |  | To be determined | Closing date: |  |  | As Per Tender Advert
Closing time: |  |  | 11:00 | Validity period: |  |  | 84 | Calender Days
It is estimated that tenderers must have a CIDB contractor grading designation of 6SF or higher. No alternative Class of work, as refered to in Clause 25(3)(a)(i) of the CIDB Regulations, as amended, is anticipated for this project.
| It is estimated that Potentially Emerging enterprises should have a CIDB contractor grading of (N/A) and satisfy the criterion stated in the Tender Data. (Only applicable if Client has an Official Mentorship programme in place to assist potentially emerging enterprises) All Tenderer's should have a CIDB Class of Construction Contractor Grading Designation as indicated above. No Tenderer with a PE status can be considered If "N/A" is indicated above because the Department does not have an Official Mentorship Programme in place to assist a Potentially Emerging Enterprise. | [7 empty] | see clause 3.3 of Standardized construction procurement documents for the eng & constr works from CIDB
Only Tenderder’s who are responsive to the following responsiveness criteria are eligible to submit Tenders: | [8 empty] | (If specialist works were selected specify the type of works)
X | Only those tenderers who are registered with the CIDB, or are capable of being so prior to the evaluation of submissions, in a contractor grading designation equal to or higher than a contractor grading designation determined in accordance with the sum tendered, or a value determined in accordance with Regulation 25(1B) or 25(7A) of the Construction Industry Development Regulations for a :
6SF or higher, class of construction work, are eligible to have their Tenders evaluated.
x | Joint ventures are eligible to submit tenders provided that:
| 1 | every member of the joint venture is registered with the CIDB;
| 2 | the lead partner has a contractor grading designation in the 6SF or higher, class of construction work; or
not lower than one level below the required the required grading designation in the class of works construction works under considerations and possess the required recognition status
| 3 | the combined contractor grading designation calculated in accordance with the Construction Industry Development Regulations is equal to or higher than a contractor grading designation determined in accordance with the sum tendered for a :
|  | 6SF | or a value determined in accordance with Regulation 25 (1B) or 25 (7A) of the Construction Industry Development Regulations.
The contractor shall achieve in the execution of this contract the Contract Participation Goals (CPG) relating to the engagement of targeted enterprises as established in the CIDB Standard for Indirect Targeting for Enterprise Development through Construction works Contracts Published in Government Gazette No 48491)
X | Tender document must be properly received on or before the tender closing date and time specified on the invitation, fully completed and signed in ink (All as per Standard Conditions of Tender).
X | Submission of Compulsory Returnable Schedules documents as per List of returnable documents.
X | Tax Compliance Status (TCS) PIN number and Tenderder's or entity tax reference number.
X | Contractor's Safety, Health and Environmental Declaration.
X | Complete priced Bill of Quantities to be submitted on the day of the Tender closing date.
X | Proof of good standing with the Compensation Commissioner - In terms of Section 84(1)(b) of the Compensation for Occupation Injuries and Disease Act, 1993, a Tenderder may not be awarded a contract if he/she is not registered and in good standing with the Compensation Commissioner.
X | Certified Proof of Paid Municipal Rates and Taxes (Attach) (T2.23)
X | Certified Proof of UIF Registration (Attach) (T2.24)
X | Financial Standing and other resources of Business Declaration (T2.8)
X | Compulsory Enterprise Questionnaire (T2.18)
X | Tenderers must meet the minimum qualifying score for functionality criteria first before they can be considered for price and preference by means of specific goals
Invitation to Tender - SBD 1
Please note the following for POPIA: By submitting this tender, I hereby acknowledge consent that the KZN Department of Public Works, may, from time to time, collect/store/use/destroy/delete/share or otherwise process my Company and Director's/Shareholders personal information as the context or circumstances may require and as contemplated in terms of POPIA. 󠇮󠇮 (TICK)
THE FOLLOWING PARTICULARS MUST BE FURNISHED (FAILURE TO DO SO MAY RESULT IN YOUR TENDER BEING DISQUALIFIED)
Name of Tenderer:
Postal Address:
Street Address:
Telephone Number |  |  | CODE _______________ NUMBER ______________________________________________________________
Cellphone Number:
Facsimile Number: |  |  | CODE _______________ NUMBER ______________________________________________________________
E-mail Address:
VAT Registration Number:
TAX COMPLIANCE STATUS (TCS) PIN TO VERIFY ON LINE COMPLIANCE SUPPLIER STATUS VIA SARS e-FILING (T2.19) | [7 empty] | YES or NO
ARE YOU THE ACCREDITED REPRESENTATIVE IN SOUTH AFRICA FOR THE GOODS / SERVICES / WORKS OFFERED? [If yes, enclose proof] | [7 empty] | YES or NO
This tender will be evaluated according to the preferential procurement model in the Preferential Procurement Policy Framework Act, 2000: Preferential Procurement Regulations, 2022:
X | 80/20 Preference point scoring system |  |  |  | 90/10 Preference point scoring system |  |  |  | (Tick applicable preference point scoring system)
NOTE |  |  | Refer to T2.35 - Functionality Criteria
Functionality requirement: | [6 empty] | 50 | Points
Price: | [6 empty] | 80 | points
1. The Specific Goal/s Allocated Points in terms of this tender:
Preference points system: Preferences are offered to Tenderder's who have attained points for the specific goals in accordance with the table below; Documentary Proof required to satisfy the points claimed are also indicated in the table below:
No | Specific Goal | [5 empty] | Number of Points Allocated
1 | Ownership by People who are Youth Documentary Proof Required: 1) Certified copy of Identity Document/s 2) EME or QSE Sworn Affidavit; signed and dated by Commissioner of Oaths OR 3) SANAS approved B-BBEE Certificate OR 4) Certified copy of the original SANAS approved B-BBEE approved certificate
2
3
4
5
6
7
8
2. Other specific goals (according to the PPPFA):
(a) | The contractor shall achieve in the execution of this contract the Contract Skills Development Goal (CSDG) established in the Standard for Developing Skills through Infrastructure Contracts (Published in Government Gazette No 48491) | [5 empty] | No | Points
(b) | The contractor shall achieve in the execution of this contract the Contract Participation Goals (CPG) relating to the engagement of targeted enterprises as established in the CIDB Standard for Indirect Targeting for Enterprise Development through Construction works Contracts Published in Government Gazette No 48491) | [5 empty] | Yes | Points
(c) | #REF! | [5 empty] | #REF! | Points
(d) | #REF! | [5 empty] | #REF! | Points
Total must equal 10 or 20 points | [6 empty] | 20 | Points
Notes:
1 | The successful Tenderder will be required to fill in and sign a written GCC 2010 2nd Edition Contract.
2 | Tenderders should ensure that Tenders are delivered timeously to the correct address. If the Tender is late, it will not be accepted for consideration.
3 | The requirements in respect of the application of either 80/20 and 90/10 preference points scoring system, will apply and the points reflected above for preferences will be adjusted accordingly on a pro-rata basis if required.
4 | The Tender box is generally open during official working hours.
5 | All Tenders must be submitted on the official forms – (Not to be re-typed)
6 | This Tender is subject to the PREFERENTIAL PROCUREMENT POLICY FRAMEWORK ACT AND THE PREFERENTIAL PROCUREMENT REGULATIONS, 2022, THE GENERAL CONDITIONS OF CONTRACT FOR CONSTRUCTION WORKS (GCC2010) AND, IF APPLICABLE, ANY OTHER SPECIAL CONDITIONS OF CONTRACT
7 | The documentary proof required to satisfy the points claimed for specific goals in terms of this tender, are duly indicated on the table (1) above.
8 | Where stated in the tender data that a two-envelope system has been followed, open only the non-financial proposal of valid tenders in the presence of tenderer's agents, who choose to attend, at the time and place stated in the tender data and announce the name of each tenderer whose technical proposal is opened.
Evaluate that non-financial proposals offered by tenderers, then advise tenderers who remain in contention for the award of the contract of the time and place when the financial proposals are to be opened.
Open only the financial proposals of tenderers who, in the Functionality evaluation score, have more than the minimum number of points for Functionality stated in the tender data, and announce the score obtained for the non-financial proposals and the total price and any preferences claimed. Return unopened financial proposals to tenderers whose non-financial proposals failed to achieve the minimum number of points for Functionality.
THE PHYSICAL ADDRESS FOR COLLECTION OF TENDER DOCUMENTS:
Tender documents may be collected during working hours at the following address :
Department of Public Works, Physical Address, Pietermaritzburg, Southern Region
A non-refundable tender deposit of R450 is payable as per the tender advertisement , on collection of the Tender documents. The Tenderders must deposit the the above amount into the Department's bank account. The Account details are:
| Account Name: |  | KZN PROV GOV-WORKS
| Bank Name: |  | STANDARD BANK
| Account Number: |  | 052106446
| Bank Code: |  | 057525
| Reference No: |  | Ref No 14019647
The Tenderder must attach the account statement with above reference, to this Tender as proof of payment of the deposit.
COMPULSORY CLARIFICATION MEETING
A Compulsory clarification Meeting with representatives of the Employer will take place as follows:
As per Tender Advertisement
| on: | As per Tender Advertisement
QUERIES REGARDING THE TENDERING PROCEDURE OR TECHNICAL INFORMATION MAY BE DIRECTED TO:
DOPW Project Manager: |  |  | Mr. Khumalo | Telephone no: |  | 033-897 1421/1422
Cell no: |  |  | 082 123 4568 | Fax no: |  | 033-897 1399
E-mail: |  |  | mkhumalo@kznworks.gov.za
DEPOSIT / RETURN OF TENDER DOCUMENTS:
Telegraphic, telephonic, telex, facsimile, electronic, posted and / or late tenders will not be accepted.
Requirements for sealing, addressing, delivery, opening and assessment of tenders are stated in the Tender Data document.
All tenders must be submitted on the official forms – (not to be re-typed)
TENDER DOCUMENTS MAY BE: |  |  |  | DEPOSITED IN THE TENDER BOX AT:
Southern Region
Southern Region Office, 10 Prince Alfred Street
Pietermarizburg
3200
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data
X

## T1.2_PA04.1 (hidden)
PA-04.1: SUMMARY FOR TENDER OPENING
Project title: |  | KZN Public Works: 191 Prince Alfred Street
Tender / Bid no: |  | ZNTM012345W | WIMS no: |  | 012345
To facilitate announcing details of an Offer at the opening of Tenders at the stated venue as recorded in this document, the Tenderer shall provide by way of summary below the following information.
Name of Tendering Entity: _______________________________________________________________
Tender Sum
R | ____________________________________ |  | (as stated in the Form of Offer, inclusive of VAT)
Amount in Words
______________________________________________________________________________________
______________________________________________________________________________________
I, ____________________________________________(name of person authorised to sign on behalf of Tenderer) certify that the offer is fully in accordance with this Tender Document and specifications.
Duly signed at _________________________________ on this day of _______of ___________. 200___
________________________________________ |  |  |  | ___________________________________
Signature |  |  |  | Date
(of person authorised to sign Tender)
NB: THIS IS ONLY FOR TENDER OPENING PURPOSES AND DOES NOT REPLACE THE OFFER AND ACCEPTANCE FORM (DOW-07 KZN)
Tenderers attention is drawn to the fact that Offer and Acceptance Form (DOW-07 KZN) should be completed in full and signed as the official Offer to the Employer. Failure to submit the DOW-07 KZN could lead to the Tenderer's offer being disqualified and non-responsive
Back to Main Menu
Print

## 1.2_Tender Data-fly
KZN Public Works: 191 Prince Alfred Street
Please do a print preview before printing
T1.2 - TENDER DATA
Back to Main Menu
Print
Print Preview
Enter Data

## T1.2_Tender Data
T1.2 TENDER DATA
Project title: |  | KZN Public Works: 191 Prince Alfred Street
Project Code: |  | 012345
Tender no: |  | ZNTM012345W |  |  | Closing date: |  |  | As Per Tender Advert
Closing time: |  | 11:00 |  |  | Validity period: |  |  | 84 | Calender Days
Clause number:
The conditions of Tender are the Standard Conditions of Tender as contained in Annexure C of the CIDB Standard for Uniformity in Engineering and Construction Works Contracts as per Board Notice 423 of 2019 in Government Gazette 42622 of 8 August 2019 as amended from time to time. (see www.cidb.org.za) Refer to Conditions of Tender as bound into this document.
The Standard Conditions of Tender make several references to the Tender Data for details that apply specifically to this tender. The Tender Data shall have precedence in the interpretation of any ambiguity or inconsistency between it and the Standard Conditions of Tender.
Each item of data given below is cross-referenced to the clause marked “C” in the above mentioned Standard Conditions of Tender.
C.1.1 | The Employer is the Head: Public Works (KZN Department of Public Works-Province of KwaZulu-Natal)
For this contract the single volume approach is adopted.
This procurement document has been formatted and compiled under the headings for a single volume approach as contained in table 5 of the CIDB’s “Standard for Uniformity in Engineering and Construction Works Contracts.”
The list of Returnable Documents identifies which of the documents a Tenderder must complete when submitting a Tender. The Tenderder must submit his Tender by completing the Returnable Documents including the priced Final Summary of the Bills of Quantities, signing the “Offer” section in the “Form of Offer and Acceptance” and delivering the whole of the procurement document back to the Department bound up as it was when it was received.
C.1.2 | The single volume procurement document issued by the Employer comprises the following:
TENDER
Part T1: Tendering procedures
| T1.1 - | Tender Notice and Invitation to Tender
| T1.2 - | Tender Data
| T1.3 - | Annexure C - Standard Conditions of Tender
Part T2: Returnable documents
| T2.1 - | List of returnable documents
| T2.2 - | Returnable schedules (See different forms listed in T2.1 - Returnable Schedule)
CONTRACT
Part C1: Agreements and Contract Data
| C1.1 - | Form of Offer and Acceptance
| C1.2 - | Contract Data
| C1.3 - | Form of Guarantee (C1.3)
Part C2: Pricing data
| C2.1 - | Pricing Instructions
| C2.2 - | Bills of Quantities
Part C3: Scope of works
| C3.1 - | Scope of Works
| C3.2 - | Specification for HIV/AIDS awareness
| C3.3 - | HIV/STI Compliance report
| C3.4 - | Project Specific Construction Safety, Health and Environmental Specification
| C3.5 - | Supplementary Preambles
Part C4: Site information
| C4.1 - | Site Information
| C4.2 - | Builders Lien Agreement
Part 5: List of Drawings/Annexure's
| C5.1 - | List of Drawings
| C5.2 - | Standard Preambles for all Trades (Rev 3) - DOH 2009
| C5.3 - | General Electrical Specifications
| C5.4 - | Lightning Protection Specifications
| C5.5 - | Map of Tender submission location
| C5.6 - | Joint Venture Agreement
| C5.7 - | Health and Safety Specification
| C5.8 - | Health and Safety Bill of Quantities
| C5.9 - | Builders Lien Agreement
| C5.10 | Geotechnical Investigation Report (If applicable)
| C5.11 | EPWP Employment Contract
| C5.12 | Attendance Register - Infrastructure and Other projects
| C5.13 | EPWP Data Collection tool for Phase 3 system
C.1.4 | The Employer’s agent (Engineer/Principal Agent) is:
| Name: |  |  | [Identify the Company or person]
| Capacity: |  |  | Principal Agent/Engineer
| Address: |  |  | [P.O. Box number] , [Name of town] , [Name of City] , [Code]
| Tel: |  |  | [Telephone Number including Area Code]
| Fax: |  |  | [Fax Number including Area Code]
| E-mail: |  |  | [Email Address]
| Responsible person: |  |  | Mr. Brightspark Knowitall
The second sentence shall read "Communications can be in any of the official languages recognised in KwaZulu-Natal which is English, Afrikaans or Zulu but writing is preferred in English as this is generally accepted as a business language"
C.1.6 | PP2-Competitive Selection Procedure |  |  |  |  | Design and Build
PP2B-Open Procedure
Tenderers must meet the minimum qualifying score for functionality criteria first before they can be considered for price and preference.
C.2.1 | For eligibility refer to T1.1 Tender Notice and Invitation to Tender
This is not an EPWP project
Only those tenderers who are registered with the CIDB, or are capable of being so prior to the evaluation of submissions, in a contractor grading designation equal to or higher than a contractor grading designation determined in accordance with the sum tendered, or a value determined in accordance with Regulation 25(1B) or 25(7A) of the Construction Industry Development Regulations for a :
| 6SF | or higher class of construction work, are eligible to have their tenders evaluated.
Joint ventures are eligible to submit tenders provided that:
| 1 | every member of the joint venture is registered with the CIDB;
| 2 | the lead partner has a contractor grading designation in the 6SF or higher, class of construction work; or
not lower than one level below the required the required grading designation in the class of works construction works under considerations and possess the required recognition status
| 3 | the combined contractor grading designation calculated in accordance with the Construction Industry Development Regulations is equal to or higher than a contractor grading designation determined in accordance with the sum tendered for a :
|  | 6SF | or a value determined in accordance with Regulation 25 (1B) or 25 (7A) of the Construction Industry Development Regulations.
See end of T2.3 AUTHORITY FOR CONSORTIA OR JOINT VENTURES TO SIGN TENDER for combinations of JV's arrangements.
C.2.7 | For particulars regarding a pre-tender site inspection meeting (clarification meeting), see T1.1 Tender Notice and Invitation to Tender.
C.2.12 | Alternative tender offer permitted: |  |  |  |  | Yes | X | No
If a tenderer wishes to submit an own alternative tender offer, the only criteria permitted for such alternative tender offer is that it demonstrably satisfies the Employer’s standards and requirements. A tenderer may submit alternative tender offers only if a main tender offer, strictly in accordance with all the requirements of the tender documents, is also submitted. Provided that the tenderer’s main tender offer is according to specification and would under normal circumstances be recommended for acceptance, his alternative tender offer may also be considered for the purpose of the award of the contract.
Calculations, drawings and all other pertinent technical information and characteristics as well as modified or proposed Pricing Data must be submitted with the alternative tender offer to enable the Employer to evaluate the efficacy of the alternative and its principal elements, to take a view on the degree to which the alternative complies with the Employer’s standards and requirements and to evaluate the acceptability of the pricing proposals. Calculations must be set out in a clear and logical sequence and must clearly reflect all design assumptions. Pricing Data must reflect all assumptions in the development of the pricing proposal.
Acceptance of an alternative tender offer will mean acceptance in principle of the offer. It will be an obligation of the contract for the tenderer, in the event that the alternative is accepted, to accept full responsibility and liability that the alternative offer complies in all respects with the Employer’s standards and requirements.
The modified Pricing Data must include an amount equal to 5% of the amount tendered for the alternative offer to cover the Employer’s costs of confirming the acceptability of the detailed design before it is constructed.
F.2.13.1 | Tenderders may offer to provide any of the following parts or combinations thereof, of the works, services or supply identified in the contract data:
Only the complete Service as per the Bills of Quantities
C.2.13.2 | Tenderers are to ensure that their company details appear on the entire relevant Tender documentation and must be legible.
C.2.13.3 | Part of each tender offer communicated on paper shall be submitted as an original, plus ONE copy of the tender document including supporting documents and priced Bill of Quantities where applicable, scanned onto a readable compact disk (CD) in pdf format, at the Tenderders own cost. The CD must be clearly marked with the tender information and company details.
C.2.13.4 | The second sentence shall read as follows "The Employer will hold all authorised signatories jointly and severally liable on behalf of the tenderer". Tenderders proposing to contract as a Joint Venture shall submit a valid Joint Venture Agreement before the Joint Venture's offer could be accepted. Individuals, Partnerships and Companies proposing to contract as a party to a Joint Venture shall be jointly and severally liable on behalf of the Joint Venture.
C.2.13.5 | The Employer’s address for delivery of tender offers and identification details to be shown on each tender offer package are as per T1.1 Tender Notice and Invitation to Tender.
A Open Procedure will be followed
C.2.15 | The closing time for submission of tender offers is as per T1.1 Tender Notice and Invitation to Tender.
C.2.16 | The tender offer validity period is as per T1.1 Tender Notice and Invitation to Tender.
C.2.17 | Sub-clause C2.17 does not preclude the negotiation of the final terms of the contract with the preferred tenderer, following a competitive selection process, should the Employer elect to do so and provided that the competitive position of the preferred tenderer is not affected.
The tenderer is to submit the Priced Bills of Quantities with the Returnable's at the closing of the tender.
This is not an EPWP project
C.2.19 | Access shall be provided for inspections, tests and analysis as may be required by the Employer.
C.2.22 | Tenderers do not have to return all retained tender documents within 28 days after expiry of the Tender validity period.
Tenderers are to refer to List of Returnable Schedules and Scope of Works to establish what is required to be submitted with this tender.
C.3.4 | The location for opening of the tender offers, immediately after the closing time thereof shall be at:
KZN Department of Public Works, Southern Region Office, 10 Prince Alfred Street, Pietermaritzburg, 3200 at the time indicated on T1.1 Notice and Invitation to Bid
C.3.8 | The employer must determine, on opening and before detailed valuation, whether each Tender offer properly received: a) complies with the requirements of the Conditions of Tender. b) has been properly and fully completed and signed, and c) is responsive to the other requirements of the Tender documents.
A responsive tender is one that conforms to all the terms, conditions and specifications of the tender documents without material deviation or qualification. A material deviation or qualification is one which, in the Employer's opinion, would:
a) detrimentally affect the scope, quality, or performance of the Works, services or supply identified in the Scope of Work or b) significantly change the Employers or the Tenderers risks and responsibilities under the contract, or c) affect the competitive position of other Tenderers presenting responsive tenders, if it were to be rectified.
Reject a non-responsive tender offer, and not allow it to be subsequently made responsive by correction or withdrawal of the non-conforming deviation or reservation.
C.3.13 | Tender offers will only be accepted if:
| (a) | Tenderders must be registered on Government's Central Supplier Database (CSD) and include their master registration number (MAAA number) on the cover page of the tender document in order to enable the institution to verify the tenderers tax status on the CSD
| (b) | the Tenderder is registered with the Construction Industry Development Board in an appropriate contractor grading designation is required for this tender and the Tenderder has submitted a CIDB certificate of registration which clearly indicates the status "Active"
| (c) | the Tenderder has completed the Compulsory Enterprise Questionnaire and there are no conflicts of interest which may impact on the Tenderder's ability to perform to the contract in the best interests of the employer or potentially compromise the Tender process.
| (d) | the tenderer or any of its directors is not listed on the Register of Tender Defaulters in terms of the Prevention and Combating of Corrupt Activities Act, 2004 (Act No. 12 of 2004) as a person prohibited from doing business with the public sector; and
| (e) | the Tenderder has not:
|  | i) | abused the Employer’s Supply Chain Management System; or
|  | ii) | failed to perform on any previous contract and has been given a written notice to this effect.
| (f) | the Tenderder is registered with:
|  | i) | the Unemployment Insurance Fund (UIF); and
|  | ii) | the Workmen's Compensation Fund
| (g) | the Tenderder submitted Authority to Sign the tender.
| (h) | the Tenderder submitted Financial standing & other resources of Business Declaration.
| (i) | the Tenderder submitted Equipment Schedules, if applicable.
| (j) | the Tenderder signed the Form of Offer that is part of the Form of Offer and Acceptance.
| (k) | the Tenderder submitted Preference Certificate, if applicable.
| (l) | the Tenderder submit Final Summary of Bill of Quantities at tender closing.
| (m) | the Tenderder submitted Bidder's Disclosure.
| (n) | the Tenderder submitted Site Inspection Certificate from the Compulsory Briefing Meeting
| (o) | All information required to assess ‘Functionality” as per Tender Data scheduled requirements
Providing the form of offer and acceptance does not contain any qualifying statements, it will constitute the formation of a contract between the employer and the successful Tenderder as described in the form of offer and acceptance.
C.3.15 | Tenderders are informed that any formal dispute shall be resolved by being referred to Arbitration only.
C.3.17 | Provide to the successful Tenderder one copy of the signed contract document and one copy of an unpriced bills of quantities
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T1.3_Annexure F-fly
KZN Public Works: 191 Prince Alfred Street
T1.3 - Annexure C - Standard Conditions of Tender
Please do a print preview before printing
Back to Main Menu
Print
Print Preview
Enter Data

## T1.3_Conditions of Tender
T1.3 - Annexure C - Standard Conditions of Tender
Note: Where this document refers to Bid or Bidder it shall be read as tender or tenderer
C.1 | General
| C.1.1 | Actions
| C.1.1.1 | The employer and each tenderer submitting a tender offer shall comply with these conditions of tender. In their dealings with each other, they shall discharge their duties and obligations as set out in C.2 and C.3, timeously and with integrity, and behave equitably, honestly and transparently and comply with all legal obligations and not engage in anticompetitive practices.
| C.1.1.2 | The employer and the tenderer and all their agents and employees involved in the tender process shall avoid conflicts of interest and where a conflict of interest is perceived or known, declare any such conflict of interest, indicating the nature of such conflict. Tenderer's shall declare any potential conflict of interest in their tender submissions. Employees, agents and advisors of the employer shall declare any conflict of interest to whoever is responsible for overseeing the procurement process or as soon as they become aware of such conflict, and abstain from any decisions where such conflict exists or recuse themselves from the procurement process, as appropriate.
|  | Note: | 1) |  | A conflict of interest may arise due to a conflict of roles which might provide an incentive for improper acts in some circumstances. A conflict of interest can create an appearance of impropriety that can undermine confidence in the ability of that person to act properly in his or her position even if no improper acts result.
|  |  | 2) |  | Conflicts of interest in respect of those engaged in the procurement process include direct, indirect or family interests in the tender or outcome of the procurement process and any personal bias, inclination, obligation, allegiance or loyalty which would in any way affect any decisions taken.
| C.1.1.3 | The employer shall not seek and the tenderer shall not submit a tender without having a firm intention and the capacity to proceed with the contract.
| C.1.2 | Tender Documents
The documents issued by the employer for the purpose of a tender offer are listed in the tender data.
| C.1.3 | Interpretation
|  | C.1.3.1 | The tender data and additional requirements contained in the tender schedules that are included in the returnable documents are deemed to be part of these conditions of tender.
|  | C.1.3.2 | These conditions of tender, the tender data and tender schedules which are required for tender evaluation purposes, shall form part of any contract arising from the invitation to tender.
|  | C.1.3.3 | For the purposes of these conditions of tender, the following definitions apply:
|  |  | a) | conflict of interest means any situation in which:
|  |  |  | i) | someone in a position of trust has competing professional or personal interests which make it difficult to fulfil his or her duties impartially;
|  |  |  | ii) | an individual or tenderer is in a position to exploit a professional or official capacity in some way for their personal or corporate benefit; or
|  |  |  | iii) | incompatibility or contradictory interests exist between an employee and the tenderer who employs that employee.
|  |  | b) | comparative offer means the price after the factors of a non-firm price and all unconditional discounts it can be utilised to have been taken into consideration;
|  |  | c) | corrupt practice means the offering, giving, receiving or soliciting of anything of value to influence the action of the employer or his staff or agents in the tender process;
|  |  | d) | fraudulent practice means the misrepresentation of the facts in order to influence the tender process or the award of a contract arising from a tender offer to the detriment of the employer, including collusive practices intended to establish prices at artificial levels.
| C.1.4 | Communication and employer’s agent
Each communication between the employer and a tenderer shall be to or from the employer's agent only, and in a form that can be read, copied and recorded. Communication shall be in the English language. The employer shall not take any responsibility for non-receipt of communications from or by a tenderer. The name and contact details of the employer’s agent are stated in the tender data.
|  | C.1.5 | Cancellation and Re-Invitation of Tenders
|  |  | C.1.5.1 |  | An employer may, prior to the award of the tender, cancel a tender if-
|  |  |  | a) | due to changed circumstances, there is no longer a need for the engineering and construction works specified in the inviteation;
|  |  |  | b) | funds are no longer available to cover the total envisaged expenditure; or
|  |  |  | c) | no acceptable tenders are received.
|  |  |  | d) | there is a material irregularity in the tender process.
|  |  | C.1.5.2 | The decision to cancel a tender invitation must be published in the same manner in which the original tender invitation was advertised.
|  |  | C.1.5.3 | An Employer may only with the prior approval of the relevant treasury cancel a tender invitation for the second time.
|  | C.1.6 | Procurement procedures
|  |  | C.1.6.1 | General
Unless otherwise stated in the tender data, a contract will, subject to C.3.13, be concluded with the tenderer who in terms of C.3.11 is the highest ranked or the tenderer scoring the highest number of tender evaluation points, as relevant, based on the tender submissions that are received at the closing time for tenders.
|  | C.1.6.2 | Competitive negotiation procedure
|  |  | C.1.6.2.1 |  |  | Where the tender data requires that the competitive negotiation procedure is to be followed, tenderers shall submit tender offers in response to the proposed contract in the first round of submissions. Notwithstanding the requirements of C.3.4, the employer shall announce only the names of the tenderers who make a submission. The requirements of C.3.8 relating to the material deviations or qualifications which affect the competitive position of tenderers shall not apply.
|  |  | C.1.6.2.2 |  |  | All responsive tenderers, or at least a minimum of not less than three responsive tenderers that are highest ranked in terms of the evaluation criteria stated in the tender data, shall be invited to enter into competitive negotiations based on the principle of equal treatment, keeping confidential the proposed solutions and associated information. Notwithstanding the provisions of C.2.17, the employer may request that tenders be clarified, specified and fine-tuned in order to improve a tenderer's competitive position provided that such clarification, specification, fine-tuning or additional information does not alter any fundamental aspects of the offers or impose substantial new requirements which restrict or distort competition or have a discriminatory effect.
|  |  | C.1.6.2.3 |  |  | At the conclusion of each round of negotiations, tenderers shall be invited by the employer to revise their tender offer based on the same evaluation criteria, with or without adjusted weightings. Tenderers shall be advised when they are to submit their best and final offer.
|  |  | C.1.6.2.4 |  |  | The contract shall be awarded in accordance with the provisions of C.3.11 and C.3.13 after tenderers have been requested to submit their best and final offer.
|  | C.1.6.3 | Proposal procedure using the two stage-system
|  |  | C.1.6.3.1 |  |  | Option 1
Tenderers shall in the first stage submit technical proposals and, if required, cost parameters around which a contract may be negotiated. The employer shall evaluate each responsive submission in terms of the method of evaluation stated in the tender data, and in the second stage negotiate a contract with the tenderer scoring the highest number of evaluation points and award the contract in terms of these conditions of tender.
|  |  | F.1.6.3.2 |  |  | Option 2
[5 empty] | C.1.6.3.2.1 |  | Tenderers shall submit in the first stage only technical proposals. The employer shall invite all responsive tenderes to submit tender offers in the second stage, following the issuing of procurement documents.
[5 empty] | C.1.6.3.2.2 |  | The employer shall evaluate tenders received during the second stage in terms of the method of evaluation stated in the tender data, and award the contract in terms of these conditions of tender.
C.2 | Tenderer’s obligations
| C.2.1 | Eligibility
|  | C.2.1.1 | Submit a tender offer only if the tenderer satisfies the criteria stated in the tender data and the tenderer, or any of his principals, is not under any restriction to do business with employer.
|  | C.2.1.2 | Notify the employer of any proposed material change in the capabilities or formation of the tendering entity (or both) or any other criteria which formed part of the qualifying requirements used by the employer as the basis in a prior process to invite the tenderer to submit a tender offer and obtain the employer's written approval to do so prior to the closing time for tenders.
| C.2.2 | Cost of tendering
|  | C.2.2.1 | Accept that, unless otherwise stated in the tender data, the employer will not compensate the tenderer for any costs incurred in the preparation and submission of a tender offer, including the costs of any testing necessary to demonstrate that aspects of the offer complies with requirements.
|  | C.2.2.2 | The cost of the tender documents charged by the employer shall be limited to the actual cost incurred by the employer for printing the documents. Employers must attempt to make available the tender documents on its website so as not to incur any costs pertaining to the printing of the tender documents.
| C.2.3 | Check documents
Check the tender documents on receipt for completeness and notify the employer of any discrepancy or omission.
| C.2.4 | Confidentiality and copyright of documents
Treat as confidential all matters arising in connection with the tender. Use and copy the documents issued by the employer only for the purpose of preparing and submitting a tender offer in response to the invitation.
| C.2.5 | Reference documents
Obtain, as necessary for submitting a tender offer, copies of the latest versions of standards, specifications, conditions of contract and other publications, which are not attached but which are incorporated into the tender documents by reference.
| C.2.6 | Acknowledge addenda
Acknowledge receipt of addenda to the tender documents, which the employer may issue, and if necessary apply for an extension to the closing time stated in the tender data, in order to take the addenda into account.
| C.2.7 | Clarification meeting
Attend, where required, a clarification meeting at which tenderers may familiarize themselves with aspects of the proposed work, services or supply and raise questions. Details of the meeting(s) are stated in the tender data.
| C.2.8 | Seek clarification
Request clarification of the tender documents, if necessary, by notifying the employer at least five (5) working days before the closing time stated in the tender data.
| C.2.9 | Insurance
Be aware that the extent of insurance to be provided by the employer (if any) might not be for the full cover required in terms of the conditions of contract identified in the contract data. The tenderer is advised to seek qualified advice regarding insurance.
| C.2.10 | Pricing the tender offer
|  | C.2.10.1 | Include in the rates, prices, and the tendered total of the prices (if any) all duties, taxes (except Value Added Tax (VAT)), and other levies payable by the successful tenderer, such duties, taxes and levies being those applicable 14 days before the closing time stated in the tender data.
|  | C.2.10.2 | Show VAT payable by the employer separately as an addition to the tendered total of the prices.
|  | C.2.10.3 | Provide rates and prices that are fixed for the duration of the contract and not subject to adjustment except as provided for in the conditions of contract identified in the contract data.
|  | C.2.10.4 | State the rates and prices in Rand unless instructed otherwise in the tender data. The conditions of contract identified in the contract data may provide for part payment in other currencies.
| C.2.11 | Alterations to documents
Do not make any alterations or additions to the tender documents, except to comply with instructions issued by the employer, or necessary to correct errors made by the tenderer. All signatories to the tender offer shall initial all such alterations.
| C.2.12 | Alternative tender offers
|  | C.2.12.1 | Unless otherwise stated in the tender data, submit alternative tender offers only if a main tender offer, strictly in accordance with all the requirements of the tender documents, is also submitted as well as a schedule that compares the requirements of the tender documents with the alternative requirements that are proposed.
|  | C.2.12.2 | Accept that an alternative tender offer must be based only on the criteria stated in the tender data or criteria otherwise acceptable to the employer.
|  | C.2.12.3 | An alternative tender offer must only be considered if the main tender offer is the winning tender.
| C.2.13 | Submitting a tender offer
|  | C.2.13.1 | Submit one tender offer only, either as single tendering entity or as a member in a joint venture to provide the whole of the works, services or supply identified in the contract data and described in the scope of works, unless stated otherwise in the tender data.
|  | C.2.13.2 | Return all returnable documents to the employer after completing them in their entirety, either electronically (if they were issued in electronic format) or by writing legibly in non-erasable ink.
|  | C.2.13.3 | Submit the parts of the tender offer communicated on paper as an original plus the number of copies stated in the tender data, with an English translation of any documentation in a language other than English, and the parts communicated electronically in the same format as they were issued by the employer.
|  | C.2.13.4 | Sign the original and all copies of the tender offer where required in terms of the tender data. The employer will hold all authorized signatories liable on behalf of the tenderer. Signatories for tenderers proposing to contract as joint ventures shall state which of the signatories is the lead partner whom the employer shall hold liable for the purpose of the tender offer.
|  | C.2.13.5 | Seal the original and each copy of the tender offer as separate packages marking the packages as "ORIGINAL" and "COPY". Each package shall state on the outside the employer's address and identification details stated in the tender data, as well as the tenderer's name and contact address.
|  | C.2.13.6 | Where a two-envelope system is required in terms of the tender data, place and seal the returnable documents listed in the tender data in an envelope marked “financial proposal” and place the remaining returnable documents in an envelope marked “technical proposal”. Each envelope shall state on the outside the employer’s address and identification details stated in the tender data, as well as the tenderer's name and contact address.
|  | C.2.13.7 | Seal the original tender offer and copy packages together in an outer package that states on the outside only the employer's address and identification details as stated in the tender data.
|  | C.2.13.8 | Accept that the employer will not assume any responsibility for the misplacement or premature opening of the tender offer if the outer package is not sealed and marked as stated.
|  | C.2.13.9 | Accept that tender offers submitted by facsimile or e-mail will be rejected by the employer, unless stated otherwise in the tender data.
| C.2.14 | Information and data to be completed in all respects
Accept that tender offers, which do not provide all the data or information requested completely and in the form required, may be regarded by the employer as non-responsive.
| C.2.15 | Closing time
|  | C.2.15.1 | Ensure that the employer receives the tender offer at the address specified in the tender data not later than the closing time stated in the tender data. Accept that proof of posting shall not be accepted as proof of delivery.
|  | C.2.15.2 | Accept that, if the employer extends the closing time stated in the tender data for any reason, the requirements of these conditions of tender apply equally to the extended deadline.
| C.2.16 | Tender offer validity
|  | C.2.16.1 | Hold the tender offer(s) valid for acceptance by the employer at any time during the validity period stated in the tender data after the closing time stated in the tender data.
|  | C.2.16.2 | If requested by the employer, consider extending the validity period stated in the tender data for an agreed additional period with or without any conditions attached to such extension.
|  | C.2.16.3 | Accept that a tender submission that has been submitted to the employer may only be withdrawn or substitutes by giving the employer's agent written notice before the closing time for tenders that a tender is to be withdrawn or substituted. If the validity period lapses before the employer evaluating the tender offer(s), the contractor reserves the right to review the price based on Consumer Price Index (CPI)
|  | C.2.16.4 | Where a tender submission is to be substituted, a tenderer must submit a substitute tender in accordance with the requirements of C.2.13 with the packages clearly marked as "SUBSTITUTE".
| C.2.17 | Clarification of tender offer after submission
Provide clarification of a tender offer in response to a request to do so from the employer during the evaluation of tender offers. This may include providing a breakdown of rates or prices and correction of arithmetical errors by the adjustment of certain rates or item prices (or both). No change in the competitive position of tenderers or substance of the tender offer is sought, offered, or permitted.
|  | Note: | Sub-clause C.2.17 does not preclude the negotiation of the final terms of the contract with a preferred tenderer following a competitive selection process, should the Employer elect to do so.
| C.2.18 | Provide other material
|  | C.2.18.1 | Provide, on request by the employer, any other material that has a bearing on the tender offer, the tenderer’s commercial position (including notarized joint venture agreements), preferencing arrangements, or samples of materials, considered necessary by the employer for the purpose of a full and fair risk assessment. Should the tenderer not provide the material, or a satisfactory reason as to why it cannot be provided, by the time for submission stated in the employers request, the employer may regard the tender offer as non-responsive.
|  | C.2.18.2 | Dispose of samples of materials provided for evaluation by the employer, where required.
| C.2.19 | Inspections, tests and analysis
Provide access during working hours to premises for inspections, tests and analysis as provided for in the tender data.
| C.2.20 | Submit securities, bonds and policies
If requested, submit for the employer’s acceptance before formation of the contract, all securities, bonds, guarantees, policies and certificates of insurance required in terms of the conditions of contract identified in the contract data.
| C.2.21 | Check final draft
Check the final draft of the contract provided by the employer within the time available for the employer to issue the contract.
| C.2.22 | Return of other tender documents
If so instructed by the employer, return all retained tender documents within 28 days after the expiry of the validity period stated in the tender data.
| C.2.23 | Certificates
Include in the tender submission or provide the employer with any certificates as stated in the tender data.
C.3 | The employer’s undertakings
| C.3.1 | Respond to request from the tenderer
|  | C.3.1.1 | Unless otherwise stated in the tender data, respond to a request for clarification received up to five (5) working days before the tender closing time stated in the tender data and notify all tenderers who collected tender documents.
|  | C.3.1.2 | Consider any request to make a material change in the capabilities or formation of the tendering entity (or both) or any other criteria which formed part of the qualifying requirements used to prequalify a tenderer to submit a tender offer in terms of a previous procurement process and deny any such request if as a consequence:
|  |  | a) | an individual firm, or a joint venture as a whole, or any individual member of the joint venture fails to meet any of the collective or individual qualifying requirements;
|  |  | b) | the new partners to a joint venture were not prequalified in the first instance, either as individual firms or as another joint venture; or
|  |  | c) | in the opinion of the Employer, acceptance of the material change would compromise the outcome of the prequalification process.
| C.3.2 | Issue Addenda
If necessary, issue addenda that may amend or amplify the tender documents to each tenderer during the period from the date that tender documents are available until three (3) days before the tender closing time stated in the tender data. If, as a result a tenderer applies for an extension to the closing time stated in the tender data, the Employer may grant such extension and, shall then notify all tenderers who collected tender documents.
| C.3.3 | Return late tender offers
Return tender offers received after the closing time stated in the tender data, unopened, (unless it is necessary to open a tender submission to obtain a forwarding address), to the tenderer concerned.
| C.3.4 | Opening of tender submissions
|  | C.3.4.1 | Unless the two-envelope system is to be followed, open valid tender submissions in the presence of tenderers’ agents who choose to attend at the time and place stated in the tender data. Tender submissions for which acceptable reasons for withdrawal have been submitted will not be opened.
|  | C.3.4.2 | Announce at the meeting held immediately after the opening of tender submissions, at a venue indicated in the tender data, the name of each tenderer whose tender offer is opened and, where applicable, the total of his prices, number of points claimed for its BBBEE status level and time for completion for the main tender offer only.
|  | C.3.4.3 | Make available the record outlined in C.3.4.2 to all interested persons upon request.
| C.3.5 | Two-envelope system
|  | C.3.5.1 | Where stated in the tender data that a two-envelope system is to be followed, open only the technical proposal of valid tenders in the presence of tenderer's’ agents who choose to attend at the time and place stated in the tender data and announce the name of each tenderer whose technical proposal is opened.
|  | C.3.5.2 | Evaluate the functionality of the technical proposals offered by tenderers, then advise tenderers who remain in contention for the award of the contract of the time and place when the financial proposals will be opened. Open only the financial proposals of tenderers, who score in the functionality evaluation more than the minimum number of points for functionality stated in the tender data, and announce the score obtained for the technical proposals and the total price and any points claimed on BBBEE status level. Return unopened financial proposals to tenderers whose technical proposals failed to achieve the minimum number of points for functionality.
| C.3.6 | Non-disclosure
Not disclose to tenderers, or to any other person not officially concerned with such processes, information relating to the evaluation and comparison of tender offers, the final evaluation price and recommendations for the award of a contract, until after the award of the contract to the successful tenderer.
| C.3.7 | Grounds for rejection and disqualification
Determine whether there has been any effort by a tenderer to influence the processing of tender offers and instantly disqualify a tenderer (and his tender offer) if it is established that he engaged in corrupt or fraudulent practices.
| C.3.8 | Test for responsiveness
|  | C.3.8.1 | Determine, after opening and before detailed evaluation, whether each tender offer properly received:
|  |  | a) | complies with the requirements of these Conditions of Tender,
|  |  | b) | has been properly and fully completed and signed, and
|  |  | c) | is responsive to the other requirements of the tender documents.
|  | C.3.8.2 | A responsive tender is one that conforms to all the terms, conditions, and specifications of the tender documents without material deviation or qualification. A material deviation or qualification is one which, in the Employer's opinion, would:
|  |  | a) | detrimentally affect the scope, quality, or performance of the works, services or supply identified in the Scope of Work,
|  |  | b) | significantly change the Employer's or the tenderer's risks and responsibilities under the contract, or
|  |  | c) | affect the competitive position of other tenderers presenting responsive tenders, if it were to be rectified.
Reject a non-responsive tender offer, and not allow it to be subsequently made responsive by correction or withdrawal of the non-conforming deviation or reservation.
| C.3.9 | Arithmetical errors, omissions and discrepancies
|  | C.3.9.1 | Check Responsive tenders for discrepancies between amounts in words and amounts in figures.Where there is a discrepancy between the amounts in figures and the amount in words, the amount in words shall govern.
|  | C.3.9.2 | Check the highest ranked tender or tenderer with the highest number of tender evaluation points after the evaluation of tender offers in accordance with C.3.11 for:
|  |  | a) | the gross misplacement of the decimal point in any unit rate;
|  |  | b) | omissions made in completing the pricing schedule or bills of quantities; or
|  |  | c) | arithmetic errors in:
|  |  |  | i) | line items totals resulting from the product of a unit rate and a quantity in bills of quantities or schedules of prices; or
|  |  |  | ii) | the summation of the prices.
|  | C.3.9.3 | Notify the tenderer of all errors or omissions that are identified in the tender offer and either confirm the tender offer as tendered of accept the corrected total of prices
|  | C.3.9.4 | Where the tenderer elects to confirm the tender offer as tendered, correct the errors as follows:
|  |  | a) | If bills of quantities or pricing schedules apply and there is an error in the line item total resulting from the product of the unit rate and the quantity, the line item total shall govern and the rate shall be corrected. Where there is an obviously gross misplacement of the decimal point in the unit rate, the line item total as quoted shall govern, and the unit rate shall be corrected.
|  |  | b) | Where there is an error in the total of the prices either as a result of other corrections required by this checking process or in the tenderer's addition of prices, the total of the prices shall govern and the tenderer will be asked to revise selected item prices (and their rates if bills of quantities apply) to achieve the tendered total of the prices.
| C.3.10 | Clarification of a tender offer
Obtain clarification from a tenderer on any matter that could give rise to ambiguity in a contract arising from the tender offer.
| C.3.11 | Evaluation of tender offers
The Standard Conditions of Tender standardize the procurement processes, methods and procedures from the time that tenders are invited to the time that a contract is awarded. They are generic in nature and are made project specific through choices that are made in developing the Tender Data associated with a specific project. Conditions of tender are by definition the document that establishes a tenderer’s obligations in submitting a tender and the employer’s undertakings in soliciting and evaluating tender offers. Such conditions establish the rules from the time a tender is advertised to the time that a contract is awarded and require employers to conduct the process of offer and acceptance in terms of a set of standard procedures
The activities associated with evaluating tender offers are as follows:
a) Open and record tender offers received b) Determine whether or not tender offers are complete c) Determine whether or not tender offers are responsive d) Evaluate tender offers e) Determine if there are any grounds for disqualification f) Determine acceptability of preferred tenderer g) Prepare a tender evaluation report h) Confirm the recommendation contained in the tender evaluation report
|  | C.3.11.1 | General
The employer must appoint an evaluation panel of not less than three persons conversant with the proposed scope of works to evaluate each responsive tender offer using the tender evaluation methods and associated evaluation criteria and weightings that are specified in the tender data.
|  | C.3.12 | Insurance provided by the employer
If requested by the proposed successful tenderer, submit for the tenderer's information the policies and / or certificates of insurance which the conditions of contract identified in the contract data, require the employer to provide.
|  | C.3.13 | Acceptance of tender offer
Accept tender offer, if in the opinion of the employer, it does not present any risk and only if the tenderer:
|  |  | a) | Is not under restrictions, or has principals who are under restrictions, preventing participating in the employer's procurement,
|  |  | b) | can, as necessary and in relation to the proposed contract, demonstrate that he or she possesses the professional and technical qualifications, professional and technical competence, financial resources, equipment and other physical facilities, managerial capability, reliability, experience and reputation, expertise and the personnel, to perform the contract,
|  |  | c) | has the legal capacity to enter into the contract,
|  |  | d) | is not; insolvent, in receivership, under Business Rescue as provided for in chapter 6 of the Companies Act No. 2008, bankrupt or being wound up, has his/her affairs administered by a court or a judicial officer, has suspended his/her business activities or is subject to legal proceedings in respect of any of the foregoing;
|  |  | e) | complies with the legal requirements, if any, stated in the tender data, and
|  |  | f) | is able, in the opinion of the employer, to perform the contract free of conflicts of interest.
|  | C.3.14 | Prepare contract documents
|  |  | C.3.14.1 | If necessary, revise documents that shall form part of the contract and that were issued by the employer as part of the tender documents to take account of:
|  |  |  | a) | addenda issued during the tender period,
|  |  |  | b) | inclusion of some of the returnable documents, and
|  |  |  | c) | other revisions agreed between the employer and the successful tenderer.
|  |  | C.3.14.2 | Complete the schedule of deviations attached to the form of offer and acceptance, if any.
|  | C.3.15 | Complete Adjudicator's Contract
Unless alternative arrangements have been agreed or otherwise provided for in the contract, arrange for both parties to complete formalities for appointing the selected adjudicator at the same time as the main contract is signed.
|  | C.3.16 | Registration of the Award
An Employer must, within twenty-one (21) working days from the date on which a contractor's offer to perform a construction works contract is accepted in writing by the employer, register and publish the award on the cidb Register of Projects.
|  | C.3.17 | Provide copies of the contracts
Provide to the successful tenderer the number of copies stated in the tender data of the signed copy of the contract as soon as possible after completion and signing of the form of offer and acceptance.
|  | C.3.18 | Provide written reasons for actions taken
Provide upon request written reasons to tenderers for any action that is taken in applying these conditions of tender but withhold information which is not in the public interest to be divulged, which is considered to prejudice the legitimate commercial interests of tenderers or might prejudice fair competition between tenderers.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2_Returnable Docs-fly
KZN Public Works: 191 Prince Alfred Street
PART T2 - RETURNABLE DOCUMENTS
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.1_Returnable Docs
T2.1 LIST OF RETURNABLE DOCUMENTS
Project title: | KZN Public Works: 191 Prince Alfred Street
Project Manager: | Mr. Khumalo |  | Tender no: |  | ZNTM012345W
1. RETURNABLE SCHEDULES REQUIRED FOR TENDER EVALUATION PURPOSES
(Tenderer to Insert a tick (√ ) in the “Returnable document” column to check which documents he/she returned with the tender) | [6 empty] | (Insert a tick in the “Returnable document” column to indicate which documents must be returned with the tender)
Tender document name |  |  |  |  | Returnable document
Bidder's Disclosure - SBD 4 (T2.11) |  |  |  |  | Yes |  |  |  | Yes
Authority to Sign Tender (T2.2) |  |  |  |  | Yes |  |  |  | Yes
Authority for Consortia or Joint Venture’s to Sign Tender (T2.3) |  |  |  |  | Yes |  |  |  | Yes
Special Resolution of Consortia or Joint Venture’s (T2.4) |  |  |  |  | Yes |  |  |  | Yes
Schedule of Proposed Sub-Contractors (T2.6) |  |  |  |  | Yes |  |  |  | Yes
Joint Venture Involvement Declaration (T2.5) |  |  |  |  | Yes |  |  |  | Yes
Capacity of Tenderer (T2.7) |  |  |  |  | Yes |  |  |  | Yes
Annual Financial Statement for past financial year (2.15) |  |  |  |  | Yes |  |  |  | Yes
Site Inspection Certificate as proof for attendance of compulsory briefing meeting (T2.10) |  |  |  |  | Yes |  |  |  | Yes
Preference Points Claim Form (T2.9) |  |  |  |  | Yes |  |  |  | Yes
Compulsory Enterprise Questionnaire (T2.18) |  |  |  |  | Yes |  |  |  | #REF! | #REF!
Financial Standing and other resources of Business Declaration (T2.8) |  |  |  |  | Yes |  |  |  | Yes
Contractor's Safety, Health and Environmental Declaration (T2.17) |  |  |  |  | Yes |  |  |  | Yes
Complete Priced Bill of Quantities |  | (T2.22) |  |  | Yes |  |  |  | Yes
Certified Proof of CIDB Registration Number (T2.27) |  |  |  |  | Yes |  |  |  | Yes
Contract Form - Purchase of Goods/Works - Part 1 (T2.29) |  |  |  |  | Yes |  |  |  | Yes
Contract Form - Purchase of Goods/Works - Part 2 (T2.30) |  |  |  |  | Yes |  |  |  | Yes
Functionality Criteria (T2.34) |  |  |  |  | Yes |  |  |  | Yes
CIDB B U I L D Programme Undertaking (T2.36) |  |  |  |  | Yes |  |  |  | Yes
2. RETURNABLE SCHEDULES REQUIRED FOR TENDER EVALUATION PURPOSES BUT TO BE SUPPLIED BY THE TENDERER
(Tenderer to Insert a tick (√ ) in the “Returnable document” column to check which documents he/she returned with the tender)
Tender document name |  |  |  |  | Returnable document
Tax Compliance Status (TCS) PIN to verify on line Compliance Supplier Status via e-Filing (T2.19) |  |  |  |  | Yes |  |  |  | Yes
Certified Proof of Good Standing with the Compensation Commissioner (Attach) (T2.20) |  |  |  |  | Yes |  |  |  | Yes
Proof of payment of Tender deposit (T2.28) |  |  |  |  | Yes |  |  |  | Yes
Certified Proof of Paid Municipal Rates and Taxes (Attach) (T2.23) |  |  |  |  | Yes |  |  |  | Yes
Certified Proof of UIF Registration (Attach) (T2.24) |  |  |  |  | Yes |  |  |  | Yes
Certified Proof of Registration Number on the Central Suppliers Database (T2.26) |  |  |  |  | Yes |  |  |  | Yes
Annual Financial Statement for past financial year (2.15) |  |  |  |  | Yes |  |  |  | Yes
Entire tender document including returnable and supporting documents, scanned as PDF onto a CD, clearly marked with the Tender information. |  |  |  |  | Yes |  |  |  | Yes
3. RETURNABLE SCHEDULES THAT WILL BE INCORPORATED INTO THE CONTRACT
(Tenderder to Insert a tick (√ ) in the “Returnable document” column to check which documents he/she returned with the Tender)
Tender document name |  |  |  |  | Returnable document
Form of Offer and Acceptance (Bound into Section 1 of 2) (T2.21) |  |  |  |  | Yes |  |  |  | Yes
Record of Addenda to Tender Documents (T2.12) |  |  |  |  | Yes |  |  |  | Yes
Particulars of Electrical Contractor (T2.13) |  |  |  |  | Yes |  |  |  | Yes
Equipment Schedules-Mechanical / Electrical / Security Material (T2.16) |  |  |  |  | Yes |  |  |  | Yes
Schedule of Imported Materials and Equipment (T2.14) |  |  |  |  | Yes |  |  |  | Yes
Confirm Receipt of Offer and Acceptance (T2.21a) |  |  |  |  | Yes |  |  |  | Yes
4. OTHER DOCUMENTS THAT WILL BE INCORPORATED INTO THE CONTRACT
(Tenderder to Insert a tick (√ ) in the “Returnable document” column to check which documents he/she returned with the Tender)
Tender document name |  |  |  |  | Returnable document
Bill of Quantities (T2.22) |  |  |  |  | Yes |  |  |  | Yes
Form of Guarantee (C1.3) |  |  | 2 | Pages | Yes |  |  |  | Yes
List of Drawings/Annexure's (C5.1) |  |  | 2 | Pages | Yes |  |  |  | Yes
The National Industrial Participation Programme (T2.25) |  |  |  |  | Yes |  |  | TRUE | Yes
Required Structure of Contractor's detailed OHSE Plan (T2.31) |  |  |  |  | Yes |  |  | TRUE | Yes
Client's specific requirements for the Contractor's detailed OHSE Plan (T2.32) |  |  |  |  | Yes |  |  |  | Yes
Base line Risk Assessment (T2.33) |  |  |  |  | Yes |  |  |  | Yes
5. DOCUMENTS REQUIRED FOR THE EVALUATION OF FUNCTIONALITY
(Tenderder to Insert a tick (√ ) in the “Returnable document” column to check which documents he/she returned with the Tender)
Tender document name |  |  |  |  | Returnable document
Proof of working capital of at least 25% of project value |  |  |  |  | Yes |  |  |  | Yes
Letters of credit reference from suppliers and credit limits to be stipulated with supporting documents |  |  |  |  | Yes |  |  |  | Yes
Annual/Audited Financial Statement/Management Account/income and Expenditure Statements |  |  |  |  | Yes |  |  |  | Yes
Detailed schedule of resources at all levels |  |  |  |  | Yes |  |  |  | Yes
Schedule of years of experience on similar projects |  |  |  |  | Yes |  |  |  | Yes
Schedule of experience on projects of similar value and duration (Past 3 years) – letters of award to be attached and practical completion certificate for all work completed in the preceding 3 years |  |  |  |  | Yes |  |  |  | Yes
Demonstrated ability to work on an accelerated programme |  |  |  |  | Yes |  |  |  | Yes
Experience in projects that have operational challenges i.e. public interface |  |  |  |  | Yes |  |  |  | Yes
Submission of a detailed organogram |  |  |  |  | Yes |  |  |  | Yes
All key project resources have more than (5) years’ experience in the construction industry. All key project resources have experience in projects of a similar value and nature |  |  |  |  | Yes |  |  |  | Yes
Detailed CV. Traceable reference. Certificates of qualified professionals in their full employment to be attached. |  |  |  |  | Yes |  |  |  | Yes
Detailed CV of each team member (Category) and Traceable references to be detailed |  |  |  |  | Yes |  |  |  | Yes
All key project resources are dedicated full time for the duration of the project including proof of UIF contributions |  |  |  |  | Yes |  |  |  | Yes
Tenderer to demonstrate key/resource deployment over the various work package |  |  |  |  | Yes |  |  |  | Yes
Letter from a registered financial institution confirming intention to issue a provision of a guarantee |  |  |  |  | Yes |  |  |  | Yes
Site establishment indicating proposed layout for all prescribed facilities, hoarding, etc. |  |  |  |  | Yes |  |  |  | Yes
Resourcing strategy for the various work breakdown structures including resource deployment plan (PS) |  |  |  |  | Yes |  |  |  | Yes
Material storage, handling and distribution |  |  |  |  | Yes |  |  |  | Yes
Productivity, programming, resource investment, progress tracking, corrective action plans, etc. |  |  |  |  | Yes |  |  |  | Yes
Programme and progress reporting, including tracking of long lead procurement items |  |  |  |  | Yes |  |  |  | Yes
OHS Management, compliance and reporting |  |  |  |  | Yes |  |  |  | Yes
Site documentation control, filing and archiving |  |  |  |  | Yes |  |  |  | Yes
Queries and information required approach |  |  |  |  | Yes |  |  |  | Yes
Procurement of outsourced resources e.g. sub-contractors |  |  |  |  | Yes |  |  |  | Yes
[5 empty] | No | N/A |  |  | No | N/A
[5 empty] | No | N/A |  |  | No | N/A
[5 empty] | No | N/A |  |  | No | N/A
[5 empty] | No | N/A |  |  | No | N/A
[5 empty] | No | N/A |  |  | No | N/A
[5 empty] | No | N/A |  |  | No | N/A
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.2_Authority to Sign
T2.2 AUTHORITY TO SIGN TENDER
RESOLUTION of a meeting of the Board of *Directors / Members / Partners of:
(Legally correct full name and registration number, if applicable, of the Enterprise)
held at (town): |  |  |  | on (date):
RESOLVED that:
1. The Enterprise submits a Tender to the KZN Department of Public Works in respect of the following project:
KZN Public Works: 191 Prince Alfred Street
Tender Number: |  | ZNTM012345W
2. *Mr./Mrs./Ms:
in *his/her capacity as: |  |  |  |  | (Position in the Enterprise)
and who will sign as follows: |  |  |  |  | (Authorised Signatory)
be, and is hereby, authorised to sign the Tender, and any and all other documents and/or correspondence in connection with and relating to this Tender, as well as to sign any Contract, and any and all documentation, resulting from the award of the Tender to the Enterprise mentioned above.
| Name |  | Capacity |  | Signature
1
2
3
4
5
6
7
8
Note: |  |  | ENTERPRISE STAMP (If Any)
1. * Delete which is not applicable. 2. NB. This resolution / Power of Attorney must be signed by all the Directors / Members / Partners of the Legal Tendering Enterprise authorising the Representative to make this Offer. 3. Should the number of Directors / Members/Partners exceed the space available above, additional names and signatures must be supplied on a separate page. 4. In the case of the tendering Enterprise being a Close Corporation, a certified copy of the Founding Statement of such corpora - tion must be attached to this tender.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.3_Consortia or JV to Sign
T2.3 AUTHORITY FOR CONSORTIA OR JOINT VENTURES TO SIGN TENDER
RESOLUTION of a meeting of the Board of *Directors / Members / Partners of:
(Legally correct full name and registration number, if applicable, of the Enterprise)
held at (town): |  |  |  |  | on (date):
RESOLVED that:
1. | The Enterprise submits a Tender, in consortium/Joint Venture with the following Enterprises:
(List all the legally correct full names and registration numbers, if applicable, of the Enterprises forming the Consortium/Joint Venture)
to the KZN Department of Public Works in respect of the following project:
KZN Public Works: 191 Prince Alfred Street
| Tender Number: | ZNTM012345W
2. | * Mr. / Mrs. / Ms.: | in
| *his/her Capacity as: | [5 empty] | (Position in the Enterprise)
and who will sign as follows:
be, and is hereby, authorised to sign a consortium/joint venture agreement with the parties listed under item 1 above, and any and all other documents and/or correspondence in connection with and relating to the consortium/joint venture, in respect of the project described under item 1 above.
3. | The Enterprise accepts joint and several liability with the parties listed under item 1 above for the due fulfilment of the obligations of the joint venture deriving from, and in any way connected with, the Contract to be entered into with the Department in respect of the project described under item 1 above.
4. | The Enterprise chooses as its domicilium citandi et executandi for all purposes arising from this joint venture agreement and the Contract with the Department in respect of the project under item 1 above:
Physical address:
(Postal Code)
Postal Address:
(Postal Code)
| Telephone number: | (Dialling Code followed by number)
| Fax number: | (Dialling Code followed by number)
Email Address :
*BOARD OF DIRECTORS / MEMBERS / PARTNERS in Consortium of Joint Venture
| Name |  | Capacity |  |  | Signature
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note: |  |  |  | ENTERPRISE STAMP (If Any)
1. * Delete which is not applicable. 2. NB. This resolution / Power of Attorney must be signed by all the Directors / Members / Partners of the Tendering Enterprise. 3. Should the number of Directors / Members/Partners ex- ceed the space available above, additional names and signatures must be supplied on a separate page.
Deemed to satisfy joint venture arrangements |  |  |  | Designation | Tenderers who envisage entering into a Joint Venture shall complete a submit a Joint Venture Agreement (see copy of CIDB's agreement elsewhere in this document) with this Tender. THE CIDB JOINT VENTURE GRADING DESIGNATION CALCULATOR sums the capacity of all joint venture partners and calculates a grading designation for the joint venture
Grading 2 + Grading 2 + Grading 2 |  |  |  | = 3
Grading 3 + Grading 3 + Grading 3 |  |  |  | = 4
Grading 4 + Grading 4 |  |  |  | = 5
Grading 4 + Grading 3 + Grading 3 |  |  |  | = 5
Grading 5 + Grading 5 |  |  |  | = 6
Grading 5 + Grading 4 + Grading 4 |  |  |  | = 6
Grading 6 + Grading 6 |  |  |  | = 7
Grading 6 + Grading 5 + Grading 5 |  |  |  | = 7
Grading 7 + Grading 7 + Grading 7 |  |  |  | = 8
Grading 8 + Grading 8 + Grading 8 |  |  |  | = 9
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.4_Resolutio Consortia JV
T2.4 SPECIAL RESOLUTION OF CONSORTIA OR JOINT VENTURES
RESOLUTION of a meeting of the duly authorised representatives of the following legal entities who have entered into a consortium/joint venture to jointly tender for the project mentioned below: (legally correct full names and registration numbers, of the Enterprises forming a Consortium/Joint Venture)
2.
3.
4.
5.
6.
7.
8.
| held at: |  |  | (place) on |  |  | (date)
RESOLVED that:
A. | The above-mentioned Enterprises submits a Tender in Consortium/Joint Venture to the KZN Department of Public Works in respect of the following project:
KZN Public Works: 191 Prince Alfred Street
| Tender Number: | ZNTM012345W
| Project Code: | 012345
B. | Mr/Mrs/Ms: _______________________________________________________________________________ | in
| *his/her Capacity as: |  |  |  |  | (Position in the Enterprise)
and who will sign as follows:
be, and is hereby, authorised to sign the Tender, and any and all other documents and/or correspondence in connection with and relating to the Tender, as well as to sign any Contract, and any and all documentation, resulting from the award of the Tender to the Enterprises in Consortium/Joint Venture mentioned above.
C. | The Enterprises constituting the Consortium/Joint Venture, notwithstanding its composition, shall conduct all business under the name and style of:
D. | The Enterprises to the Consortium/Joint Venture accept joint and several liability for the due fulfilment of the obligations of the Consortium/Joint Venture deriving from, and in any way connected with, the Contract entered into with the Department in respect of the project described under item A above.
E. | Any of the Enterprises to the Consortium/Joint Venture intending to terminate the consortium/joint venture agreement, for whatever reason, shall give the Department 30 days written notice of such intention. Notwithstanding such decision to terminate, the Enterprises shall remain jointly and severally liable to the Department for the due fulfilment of the obligations of the Consortium/Joint Venture as mentioned under item D above.
F. | No Enterprise to the Consortium/Joint venture shall, without the prior written consent of the other Enterprises to the Consortium/Joint Venture and of the Department, cede any of its rights or assign any of its obligations under the consortium/joint Venture and of the Department, cede any of its rights or assign any of its obligations under the consortium/joint venture agreement in relation to the Contract with the Department referred to herein.
G. | The Enterprises choose as the domicilium citandi et executandi of the consortium/joint venture for all purposes arising from the consortium/joint venture agreement and the Contract with the Department in respect of the project under item A above:
Physical address:
(Postal Code)
Postal Address:
(Postal Code)
Telephone number: |  | (Dialling Code followed by number)
Fax number: |  | (Dialling Code followed by number)
Email Address :
*BOARD OF DIRECTORS / MEMBERS / PARTNERS in Consortium of Joint Venture
| Name |  | Capacity |  | Signature
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Note:
1. * Delete which is not applicable. 2. NB. This resolution / Power of Attorney must be signed by all the Duly Authorised Representatives of the Legal Entities to the Consortium/Joint Venture submitting this Tender. 3. Should the number of Duly Authorised Representatives of the Legal Entities joining forces in this Tender exceed the space available above, additional names and signatures must be supplied on a separate page. 4. Resolutions, duly completed and signed, from the separate Enterprises who participate in this Consortium/Joint Venture must be attached to the Special Resolution.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.5_JV Declaration
T2.5 JOINT VENTURES INVOLVEMENT DECLARATION
Project title: | KZN Public Works: 191 Prince Alfred Street
Tender no: | ZNTM012345W |  | Project Code: | 012345
DECLARATION RELATING TO A TENDER SUBMITTED BY A JOINT VENTURE :
I/We the undersigned parties do hereby declare that our respective involvement in the Works, of which I/we tender by Joint Venture, would be as follows :-
Party No. 1
CENTRAL SUPPLIERS DATABASE REGISTRATION NO:
TenderDERS CIDB REGISTRATION NUMBER:
Name
Address
Percentage involvement |  | %
Party No. 2
CENTRAL SUPPLIERS DATABASE REGISTRATION NO:
TENDERERS CIDB REGISTRATION NUMBER:
Name
Address
Percentage involvement |  | %
Party No. 3
CENTRAL SUPPLIERS DATABASE REGISTRATION NO:
TenderDERS CIDB REGISTRATION NUMBER:
Name
Address
Percentage involvement |  | %
Signed - Party No. 1
I/We (Full Name)
duly authorised in my capacity as
of (Enterprise name):
do jointly and severally accept responsibility for the due performance of the Works contained in the above project should such Tender submitted by the Joint Venture be accepted.
Signed by Authorised Representative |  |  | Date
Signed - Party No. 2
I/We (Full Name)
duly authorised in my capacity as
of (Enterprise name):
do jointly and severally accept responsibility for the due performance of the Works contained in the above project should such tender submitted by the Joint Venture be accepted.
Signed by Authorised Representative |  |  | Date
Signed - Party No. 3
I/We (Full Name)
duly authorised in my capacity as
of (Enterprise name):
do jointly and severally accept responsibility for the due performance of the Works contained in the above project should such tender submitted by the Joint Venture be accepted.
Signed by Authorised Representative |  |  | Date
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.6_Proposed Subcontractors
T2.6 SCHEDULE OF PROPOSED SUBCONTRACTORS
Project title: |  | KZN Public Works: 191 Prince Alfred Street
Tender no: |  | ZNTM012345W |  |  | Project Code: |  | 012345
We notify you that it is our intention to employ the following Subcontractors for work in this contract. The Subcontractors will all be CIDB registered and their CIDB Registration number shall be submitted below.
If we are awarded a contract we agree that this notification does not change the requirement for us to submit the names of proposed subcontractors in accordance with requirements in the contract for such appointments. If there are no such requirements in the contract, then your written acceptance of this list shall be binding between us.
We confirm that all subcontractors who are contracted to construct a house are registered as home builders with the National Home Builders Registration Council.
No | Name and address of proposed Subcontractor |  | Nature and extent of work | Year Completed | Value (R): | Contact Tel No: | Previous experience with Subcontractor
1
CIDB Registration Number:
2
CIDB Registration Number:
3
CIDB Registration Number:
4
CIDB Registration Number:
5
CIDB Registration Number:
Name of authorised representative |  |  | Signature |  | Capacity |  | Date
Name of Enterprise:
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.7_ Capacity of Tenderer
T2.7 CAPACITY OF TENDERER
Project title: |  | KZN Public Works: 191 Prince Alfred Street
Tender no: |  | ZNTM012345W |  |  |  | Project Code: |  | 012345
|  |  | To be determined |  |  | Validity period: |  | 84 | (days)
1. | WORK CAPACITY: (The Tenderer is requested to furnish the following capacity particulars and to attach additional pages if more space is required. Failure to furnish the particulars may result in the Tender being disregarded.)
| 1.1. | Artisans and Employees: (Artisans and Employees to be ,or are ,employed for this project )
Categories of Employee - Key Personnel (part of Business Enterprise) |  |  |  |  | Professional Registration No. | Date of Employment |  |  | Number
Site Agent
Project Manager
Foreman
Quality Control & Safety Officer-Construction Supervisor
Artisans
Unskilled employees
Financial Manager | [5 empty] | Attach company profile if convenient
Administrative Employees | [5 empty] | Attach company profile if convenient
Others
| 1.2. | Provide full particulars of the following Assets: (Assets owned and to be hired - Indicate owned assets )
Machinery |  |  | Plant |  | Equipment |  |  | Vehicles
| 1.3. | Workshops:
Address of Main Workshop: |  |  |  |  | Address of Regional Workshop (If Applicable):
| 1.4. | Other offers submitted at time of this tender for which results are pending:
(Any other client's tender must also be included)
Tender No. |  | Project Name |  | Client Name & Contact No. | Value Tendered in R's | Date Tender submitted |  | Contact Detail
2. | PARTICULARS OF THE TENDERERS CURRENT AND PREVIOUSLY COMPLETED COMMITMENTS:
| 2.1. | Current private sector projects: (List the 5 projects closest to the contractor grading designation of this project)
1 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Scheduled date of completion
2 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Scheduled date of completion
3 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Scheduled date of completion
4 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Scheduled date of completion
5 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Scheduled date of completion
| 2.2. | Current Government sector projects: (List the 5 projects closest to the contractor grading designation of this project)
1 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Scheduled date of completion
2 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Scheduled date of completion
3 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Scheduled date of completion
4 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Scheduled date of completion
5 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Scheduled date of completion
| 2.3. | Previously completed projects: (List the 5 projects closest to the contractor grading designation of this project)
1 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Date completed
2 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Date completed
3 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Date completed
4 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Date completed
5 | Project Name |  |  |  |  | Date of commencement
| Place (town) |  |  |  |  | Contract Amount (R)
| Reference / Contact person |  |  |  |  | Contract period
| Contact Tel. No. |  |  |  |  | Date completed
Name of Tenderer |  |  |  | Signature of authorised representative |  |  | Date
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.8_Financial Standing
T2.8 FINANCIAL STANDING AND OTHER RESOURCES OF BUSINESS DECLARATION
Project title: |  |  | KZN Public Works: 191 Prince Alfred Street
Tender no: |  |  | ZNTM012345W | Project Code: | 012345
(a) |  | Based on the track record determined on the Minimum Average Annual Turnover coupled to the assessed Works Capabilities of Contracting Enterprises, the Construction Industry Development Board (CIDB) awards Grading Designations and accordingly registers it on the system. This confirms that a Contractor has, at the time of registration, in the absence of any supply side interventions, sufficient working capital to commence the Works for a single contract and render due performance.
(b) |  | However, it regularly occurs that a Contractor will at the same time submit tenders for a number of projects that are advertised during an overlapping period. Moreover, the Contractor may be busy with a Contract that is of the registered CIDB Grading Designation (value) or is even attending to a number of smaller valued Contracts.
(c) |  | It therefore becomes the prerogative of a Tenderer in such instances to prove to the Department that the Enterprise has the capacity in every respect to attend to more than one (1) contract at a time.
(d) |  | A Tenderer who wishes to be considered for this tender Contract award, over and above other tenders that they have submitted, shall submit when requested by the DoPW the necessary proof that:
| (i) | he/she has access to additional finance (inclusive of a PERFORMANCE GUARANTEE BY A REGISTERED FINANCIAL INSTITUTION),
| (ii) | he/she has additional Human Resources available to successfully complete this project.
| (iii) | he/she has adequate Equipment, Plant and Machinery that all of the above can, undoubtedly, be sourced for this tender. (Please submit to the DoPW the name and contact details of the supplier if the Tenderer is going to hire Equipment, Plant or Machinery, when requested.)
(e) |  | Tenderer to submit their latest 12 months audited financial statements with the returnable documents.
I, the undersigned,
(name of person authorized to sign on behalf of the Tenderer
understand that it is the responsibility of the Tenderer to prove and provide when requested by the DoPW, evidence of the good Financial Standing of the Business to complete the Contract successfully. Furthermore, it is understood that failure to provide when requested by DoPW, at least the information as stated in paragraphs (d)(i)(ii) AND (iii) above will not enable the Evaluation Team to assess the CURRENT financial standing of the Business and the failure to provide said information when requested will, therefore, invalidate the Tender.
I accept and understand that the KZN Department of Public Works, as representative of the Provincial Administration of KwaZulu-Natal in this tender, may act against me and the Tenderer, jointly and severally, should this declaration and/or any information provided be found to be false.
Duly signed at…………………………………………………………. on this the…... day of……………………………. 20..
Full Name of Signatory |  |  |  | Name of Enterprise
Capacity of Signatory |  |  |  | Signature of authorised representative

## Goals for T2.9 (hidden)
Goals as Defined in the Preferential Procurment Policy 2022
No | Specific Goal
1 | Ownership by Black People
2 | Ownership by People who are Women
3 | Ownership by People who are Youth
4 | Ownership by People living with Disabilities
5 | 51% Ownership by People who are Military Veterans
6 | Exempted Micro-Enterprise (EME)
7 | Promotion of enterprises located in a specific municipal area for work to be done or services to be rendered
8 | Promotion of enterprises located in rural areas

## Goals and Docs for T1.1
Goals as Defined in the Preferential Procurment Policy 2022
No | Specific Goal | HIDE THIS SHEET
1 | Ownership by Black People Documentary Proof Required: 1) EME or QSE Sworn Affidavit; signed and dated by Commissioner of Oaths | DO NOT PRINT (data sheet ONLY)
2 | Ownership by People who are Women Documentary Proof Required: 1) Certified copy of Identity Document/s 2) A Central Supplier Database (CSD) Full Report OR 3) EME or QSE Sworn Affidavit; signed and dated by Commissioner of Oaths
3 | Ownership by People who are Youth Documentary Proof Required: 1) Certified copy of Identity Document/s 2) EME or QSE Sworn Affidavit; signed and dated by Commissioner of Oaths OR 3) SANAS approved B-BBEE Certificate OR 4) Certified copy of the original SANAS approved B-BBEE approved certificate
4 | Ownership by People living with Disabilities Documentary Proof Required: 1) Original or Certified copy of an original medical certificate from a registered medical practitioner 2) Certified copy of Identity document/s
5 | 51% Ownership by People who are Military Veterans Documentary Proof Required: 1) Military Veteran Certificate OR 2) Certificate from the Military Veterans Department indicating that the entity is registered on their database
6 | Exempted Micro-Enterprise (EME) Documentary Proof Required: 1) EME or QSE Sworn Affidavit; signed and dated by Commissioner of Oaths
7 | Promotion of enterprises located in (a specific municipal area) --------------List the municipality for work to be done or services to be rendered Documentary Proof Required: 1) Proof of Municipal Account depicting Physical Address of the business, which is less than 3 months old OR 2) Lease Agreement
8 | Promotion of enterprises located in rural areas Documentary Proof Required: 1) Original or Certified copy of the original letter from the Ward Councillor, which is less than 3 months old OR 2) Certified copy of Permission To Occupy OR 3) Lease agreement from the Tribal Council

## T2.9_Preference Points Claim
T2.9 PREFERENCE POINTS CLAIM FORM IN TERMS OF THE PREFERENTIAL PROCUREMENT REGULATIONS 2022
Project Title: |  |  |  | KZN Public Works: 191 Prince Alfred Street
Tender Number: |  |  |  | ZNTM012345W
Project Code: |  |  |  | 012345
SBD 6.1
PREFERENCE POINTS CLAIM FORM IN TERMS OF THE PREFERENTIAL
PROCUREMENT REGULATIONS 2022
This preference form must form part of all tenders invited. It contains general information and serves as a claim form for preference points for specific goals.
NB: BEFORE COMPLETING THIS FORM, TENDERERS MUST STUDY THE GENERAL CONDITIONS, DEFINITIONS AND DIRECTIVES APPLICABLE IN RESPECT OF THE TENDER AND PREFERENTIAL PROCUREMENT REGULATIONS, 2022
1. GENERAL CONDITIONS
1.1 The following preference point systems are applicable to invitations to tender:
- the 80/20 system for requirements with a Rand value of up to R50 000 000 (all applicable taxes included); and
- the 90/10 system for requirements with a Rand value above R50 000 000 (all applicable taxes included).
1.2 To be completed by the organ of state
(delete whichever is not applicable for this tender).
a) The applicable preference point system for this tender is the 90/10 preference point system.
b) The applicable preference point system for this tender is the 80/20 preference point system.
c) Either the 90/10 or 80/20 preference point system will be applicable in this tender. The lowest/ highest acceptable tender will be used to determine the accurate system once tenders are received.
1.3 Points for this tender (even in the case of a tender for income-generating contracts) shall be awarded for:
(a) Price; and
(b) Specific Goals.
1.4 To be completed by the organ of state:
The maximum points for this tender are allocated as follows:
POINTS
PRICE |  |  | 80
SPECIFIC GOALS |  |  | 20
Total points for Price and SPECIFIC GOALS |  |  | 100
1.5 Failure on the part of a tenderer to submit proof or documentation required in terms of this tender to claim points for specific goals with the tender, will be interpreted to mean that preference points for specific goals are not claimed.
1.6 The organ of state reserves the right to require of a tenderer, either before a tender is adjudicated or at any time subsequently, to substantiate any claim in regard to preferences, in any manner required by the organ of state.
2. DEFINITIONS
(a) “tender” means a written offer in the form determined by an organ of state in response to an invitation to provide goods or services through price quotations, competitive tendering process or any other method envisaged in legislation;
(b) “price” means an amount of money tendered for goods or services, and includes all applicable taxes less all unconditional discounts;
(c) “rand value” means the total estimated value of a contract in Rand, calculated at the time of bid invitation, and includes all applicable taxes;
(d) “tender for income-generating contracts” means a written offer in the form determined by an organ of state in response to an invitation for the origination of income-generating contracts through any method envisaged in legislation that will result in a legal agreement between the organ of state and a third party that produces revenue for the organ of state, and includes, but is not limited to, leasing and disposal of assets and concession contracts, excluding direct sales and disposal of assets through public auctions; and
(e) “the Act” means the Preferential Procurement Policy Framework Act, 2000 (Act No. 5 of 2000).
3. FORMULAE FOR PROCUREMENT OF GOODS AND SERVICES
3.1. POINTS AWARDED FOR PRICE
3.1.1 THE 80/20 OR 90/10 PREFERENCE POINT SYSTEMS
A maximum of 80 or 90 points is allocated for price on the following basis:
80/20 or 90/10
Ps=80(1-(Pt-P min⁡ )/(P min⁡ ) or Ps=90(1-(Pt-P min⁡ )/(P min⁡ )
Where
Ps = Points scored for price of tender under consideration
Pt = Price of tender under consideration
Pmin = Price of lowest acceptable tender
3.2. FORMULAE FOR DISPOSAL OR LEASING OF STATE ASSETS AND INCOME GENERATING PROCUREMENT
3.2.1. POINTS AWARDED FOR PRICE
A maximum of 80 or 90 points is allocated for price on the following basis:
80/20 or 90/10
Ps=80(1+(Pt-P max⁡ )/(P max⁡ ) or Ps=90(1+(Pt-P max⁡ )/Pmax)
Where
Ps = Points scored for price of tender under consideration
Pt = Price of tender under consideration
Pmax = Price of highest acceptable tender
4. POINTS AWARDED FOR SPECIFIC GOALS
4.1. In terms of Regulation 4(2); 5(2); 6(2) and 7(2) of the Preferential Procurement Regulations, preference points must be awarded for specific goals stated in the tender. For the purposes of this tender the tenderer will be allocated points based on the goals stated in table 1 below as may be supported by proof/ documentation stated in the conditions of this tender:
4.2. In cases where organs of state intend to use Regulation 3(2) of the Regulations, which states that, if it is unclear whether the 80/20 or 90/10 preference point system applies, an organ of state must, in the tender documents, stipulate in the case of—
(a) an invitation for tender for income-generating contracts, that either the 80/20 or 90/10 preference point system will apply and that the highest acceptable tender will be used to determine the applicable preference point system; or
(b) any other invitation for tender, that either the 80/20 or 90/10 preference point system will apply and that the lowest acceptable tender will be used to determine the applicable preference point system,
then the organ of state must indicate the points allocated for specific goals for both the 90/10 and 80/20 preference point system.
Table 1: Specific goals for the tender and points claimed are indicated per the table below.
(Note to organs of state: Where either the 90/10 or 80/20 preference point system is applicable, corresponding points must also be indicated as such.
Note to tenderers: The tenderer must indicate how they claim points for each preference point system.)
The specific goals allocated points in terms of this tender | Number of points allocated (90/10 system) (To be completed by the organ of state) | Number of points allocated (80/20 system) (To be completed by the organ of state) |  | Number of Points allocated (90/10 system) (to be completed by the Organ of State) | Number of Points allocated (80/20 system) (to be completed by the Organ of State) | Number of points claimed (90/10 system) (To be completed by the tenderer) | Number of points claimed (80/20 system) (To be completed by the tenderer)
DECLARATION WITH REGARD TO COMPANY/FIRM
4.3. Name of company/firm…………………………………………………………………….
4.4. Company Registration Number :…………………………………………………………
4.5. TYPE OF COMPANY/ FIRM
Partnership/Joint Venture / Consortium
One-person business/sole propriety
Close corporation
Public Company
Personal Liability Company
(Pty) Limited
Non-Profit Company
State Owned Company
[TICK APPLICABLE BOX]
4.6. I, the undersigned, who is duly authorised to do so on behalf of the company/firm, certify that the points claimed, based on the specific goals as advised in the tender, qualifies the company/ firm for the preference(s) shown and I acknowledge that:
i) The information furnished is true and correct;
ii) The preference points claimed are in accordance with the General Conditions as indicated in paragraph 1 of this form;
iii) In the event of a contract being awarded as a result of points claimed as shown in paragraphs 1.4 and 4.2, the contractor may be required to furnish documentary proof to the satisfaction of the organ of state that the claims are correct;
iv) If the specific goals have been claimed or obtained on a fraudulent basis or any of the conditions of contract have not been fulfilled, the organ of state may, in addition to any other remedy it may have –
(a) disqualify the person from the tendering process;
(b) recover costs, losses or damages it has incurred or suffered as a result of that person’s conduct;
(c) cancel the contract and claim any damages which it has suffered as a result of having to make less favourable arrangements due to such cancellation;
(d) recommend that the tenderer or contractor, its shareholders and directors, or only the shareholders and directors who acted on a fraudulent basis, be restricted from obtaining business from any organ of state for a period not exceeding 10 years, after the audi alteram partem (hear the other side) rule has been applied; and
(e) forward the matter for criminal prosecution, if deemed necessary.
………………………………………. SIGNATURE(S) OF TENDERER(S) SURNAME AND NAME: ………………………………………………………. DATE: ……………………………………………………… ADDRESS: ……………………………………………………… ……………………………………………………… ……………………………………………………… ………………………………………………………

## T2.10_Site Inspection Cert
T2.10 SITE INSPECTION MEETING CERTIFICATE
Project title: | KZN Public Works: 191 Prince Alfred Street
Tender no: | ZNTM012345W |  | Project Code: | 012345
Site Inspection Date: |  |  | As per Tender Advertisement
This is to certify that I,
(Name of authorised Representative)
representing
(Name of Enterprise)
visited the site on: |  |  |  |  | (Date)
I have made myself familiar with all local conditions likely to influence the work and the cost thereof. I further certify that I am satisfied with the description of the work and explanations given at the site inspection meeting and that I understand the work to be done, as specified and implied, in the execution of this contract.
I declare that the representative, named above, is my authorised representative and not a third party agent and that my representative's attending of this site meeting, shall be deemed conclusive proof that my Enterprise are fully aware of what was said and discussed at this meeting.
Name of Tenderer |  | Signature |  | Date
Name of DOPW Representative |  | Signature |  | Date
This form is only to be completed when applicable to the tender and if a Compulsory Briefing meeting has been called.
Departmental Stamp:
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.11_Bidder's Disclosure(SBD4)
T2.11 BIDDER'S DISCLOSURE - SBD 4
NOTE TO THE COMPILER OF THIS DOCUMENT : PLEASE PRINT THE PDF VERSION OF THE BIDDER'S DISCLOSURE - SBD4 AND ATTACH TO THE BID DOCUMENT. NO CHANGES / AMENDMENTS MUST BE MADE TO THE SBD4 NATIONAL TREASURY FORM.
The pdf version of the SBD4 can be found on the KZN Public Works website: https://www.kznworks.gov.za/index.php/tender-documents under the heading FORMS PERTAINING TO TENDERS
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.12_Adenda of Tender Docs
T2.12 RECORD OF ADDENDA TO TENDER DOCUMENTS
Project title: |  | KZN Public Works: 191 Prince Alfred Street
Tender no: |  | ZNTM012345W |  | Project Code: | 012345
The undersigned confirm that the following communications received from the employer before the submission of this tender offer, amending the tender documents, have been taken into account in this tender offer:
| Date | Title or Details |  |  | No. of Pages
1
2
3
4
5
6
7
8
9
10
11
12
13
Attach Additional Pages if more space is required
Tenderer to attach proof of receipt of above listed addenda
Signed |  |  | Date
Name |  |  | Position
Tenderer
This document must form part of the returnable schedules as it is referenced in the offer portion of the Form of Offer and Acceptance DOW-07 KZN
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.13_Particulars of Elec Cont
T2.13 PARTICULARS OF ELECTRICAL CONTRACTOR
Project title: | KZN Public Works: 191 Prince Alfred Street
Tender no: | ZNTM012345W |  |  | Project Code: | 012345
Name of Electrical Contractor:
Address:
Telephone Number:
(Area Code)(Number)
Fax Number:
(Area Code)(Number)
Registration number at the Department of Labour:
Name of authorised representative |  | Signature |  |  | Date
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.14_Imported Material
T2.14 SCHEDULE FOR IMPORTED MATERIALS AND EQUIPMENT
Project title: |  | KZN Public Works: 191 Prince Alfred Street
Tender no: |  | ZNTM012345W |  | Project Code: | 012345
This schedule should be completed by the tenderer. (Attach additional page(s) if more space is required)
Item | Material / Equipment |  |  |  | Quotation (Excluding VAT)
1 |  |  |  |  | R
2 |  |  |  |  | R
3 |  |  |  |  | R
4 |  |  |  |  | R
5 |  |  |  |  | R
6 |  |  |  |  | R
The Contractor shall list imported items, materials and/or equipment which shall be excluded from the Contract Price Adjustment Provisions (if applicable) and shall be adjusted in terms of currency fluctuations only. Copies of the supplier’s quotations for the items, materials or equipment (provided that such costs shall not be higher than the relevant contract rate as listed above) should be lodged with the Principal Agent / Engineer of the Department of Public Works within 60 (sixty) days from the date of acceptance of the tender. No adjustment of the local VAT amount, nor the contractor’s profit, discount, mark-up, handling costs, etc. shall be allowed. (See P&G E16)
These net amounts will be adjusted as follows: |  |  |  |  | * A bill of lading (sometimes abbreviated as B/L or BoL) is a document issued by a carrier which details a shipment of merchandise and gives title of that shipment to a specified party. Bills of lading are one of three important documents used in international trade to help guarantee that exporters receive payment and importers receive merchandise. A straight bill of lading, which is referred to above, is used when payment has been made in advance of shipment and requires a carrier to deliver the merchandise to the appropriate party. It is therefore the date of the paid up invoice when the shipment leaves the exporter's location. [http://en.wikipedia.org/wiki/Bill_of_lading]
FORMULA:
The net amount to be added to or deducted from the contract sum:
A = V ( Z -1)
Y
A = the amount (R) of adjustment
V = the net amount (supplier’s quotation) (R) of the imported item
Y = exchange rate 14 days prior to closing date of tender submission
Z = exchange rate on the date of the Bill of Lading* of exporters invoice.
Name of authorised representative |  |  | Signature |  | Date
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.15a_AFS
T2.15a LATEST 12 MONTH ANNUAL FINANCIAL STATEMENT
Project title: | KZN Public Works: 191 Prince Alfred Street
Tender no: | ZNTM012345W | Project Code: | 012345
ATTACH A CERTIFIED COPY OF THE ANNUAL FINANCIAL STATEMENT OF THE COMPANY FOR THE PAST FINANCIAL YEAR TO THIS PAGE FOR ADJUDICATION PURPOSES
NOTE
In the case of a Tender by a Joint Venture, certified copies of the annual financial statements of the past financial year in respect of each party to the Joint Venture must be attached to this page
ATTACH COMPANY LATEST 12 MONTHS ANNUAL FINANCIAL STATEMENTS TO THIS PAGE
Please do a print preview before printing
Back to Main Menu
Print
Print Preview
Enter Data

## T2.16_Equipment Schedules
T2.16 EQUIPMENT SCHEDULES
Project title: | KZN Public Works: 191 Prince Alfred Street
Tender no: | ZNTM012345W |  |  | Project Code: | 012345
The Tenderer shall complete the following schedules giving details of the various items of materials or equipment that he includes in his offer.
TECHNICAL DATA: | STANDBY GENERATOR
Manufacturer:
Model number:
Serial number:
Voltage
KVA
Frequency
RPM
Cylinder/stroke
Fuel capacity and consumption
Sound pressure level
Condenser air flow rate
Attenuation type
Battery Type
AMF Change Over Panel Type
Starter Motor Type and Voltage
Standard Compliance
Project Code: | 012345
EQUIPMENT SCHEDULES
TECHNICAL DATA: | UNINTERRUPTABLE POWER SUPPLY UPS
Manufacturer
Model
Frequency
Harmonic Distortion Reduction
Operating Temperature
Range of Protection – Lightning Strike
KVA
Maximum current, cooling mode
Agent
Telephone number of Agent
Brochure enclosed |  |  | Yes/No
TECHNICAL DATA: |  | PARCEL X-RAY UNITS
Manufacturer
Model
Dimension /Size
Resolution
Zoom ranges
External Radiation Levels
Standard Compliance
Electrical nominal voltage |  |  | Volts
Monitor Type and size
Agent
Telephone no of Agent
Brochure enclosed |  |  | Yes/No
Project Code: | 012345
EQUIPMENT SCHEDULES
TECHNICAL DATA: |  | WALK THROUGH DETECTOR
Manufacturer
Model
Timer mode
No of sequential settings per time switch
No of N/O and N/C contacts per setting
Adjustable time lapse between settings
Operating voltage
Operating current
Agent
Telephone number
Brochure enclosed |  |  | Yes/No
TECHNICAL DATA: |  | TURNSTILE
Manufacturer
Size
Range
Voltage
Battery Back Up Time
Finish
Agent
Telephone number
Brochure enclosed |  |  | Yes/No
Project Code: | 012345
EQUIPMENT SCHEDULES
TECHNICAL DATA: |  | PARAPLEGIC LIFT
Manufacturer
Panel thickness
Load
Stops
Car Size
Door Opening
Door Type
Speed
Type of Drive
Speed Control
Type of Car and Landing Buttons
Type of Landing Door Frames
Type of Door
Internal Finishes
Pit
Head Room
Battery Type
Method of joining panels
Floor construction
Standard Compliance
Agent
Telephone number of Agent
Brochure enclosed |  |  | Yes/No
Project Code: | 012345
EQUIPMENT SCHEDULES
TECHNICAL DATA: |  | AIR-CONDITIONING AND VENTILATION INSTALLATION
Area:
Manufacturer:
Model number: | WCPU
Cooling Tower
Serial number: | WCPU
Cooling Tower
Voltage |  |  | V
Starting amps |  |  | A
Running amps |  |  | A
System supply gauge pressure |  |  | kPA
System return gauge pressure |  |  | kPA
Condenser water inlet temperature |  |  | °C
Condenser water outlet temperature |  |  | °C
Condenser water flow rate |  |  | l/s
Blower unit air inlet temperature |  |  | °C
Blower unit air outlet temperature |  |  | °C
Blower unit air flow rate |  |  | m³/s
Conditioned room air temperature after 1 hour, Design |  |  | °C
Conditioned room air temperature after 1 hour, Actual |  |  | °C
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.17_SHE Declaration
T2.17 CONTRACTOR'S SAFETY, HEALTH AND ENVIRONMENTAL DECLARATION
Project title: |  |  | KZN Public Works: 191 Prince Alfred Street
Tender no: |  |  | ZNTM012345W | Project Code: | 012345
In terms of Regulation 5(1)(h) of the Construction Regulations of February 2014 a Contractor may only be appointed to perform construction work if the Client is satisfied that the Contractor has the necessary competencies and resources to carry out the work safely in accordance with the Occupational Health and Safety Act, Act 85 of 1993 and the Construction Regulations of February 2014. In line with this requirement the Contractor is required to read through this document carefully, sign it and submit it with his/her Tender.
DECLARATION |  | However, it regularly occurs that a Contractor will at the same time submit tenders for a number of projects that are advertised during an overlapping period. Moreover, the Contractor may be busy with a Contract that is of the registered CIDB Grading Desi
1. | I, the undersigned hereby declare and confirm that I am fully conversant with the Occupational Health and Safety Act, Act 85 of 1993 and the Construction Regulations of February 2014 and the Construction Safety, Health and Environmental Specifications attached to this document. |  |  |  |  | 1. All construction works where physical construction started after the 7th of February 2014 must comply with the Construction Regulations 2003, and such construction works are exempted to comply with the Construction Regulations 2014 until the 7th August 2014, 6 months after the commencement of these Regulations, thereafter the Construction Regulations 2014 shall apply with the exception of Regulation 3 and 5 (7)(b) which will come into effect on the 7th August 2015, 18 months after the commencement of these Regulations.
2. | I hereby declare that my company and its employees has the necessary competency and resources to safely carry out the construction works under this contract in compliance with the Occupational Health and Safety Act, Act 85 of 1993, the Construction Regulations of February 2014 and the Construction Safety, Health and Environmental Specifications.
3. | I hereby confirm that adequate provisions has been made in my Tender to cover the cost of all Safety, Health and Environmental duties and responsibilities imposed on me by the Occupational Health and Safety Act, Act 85 of 1993, the Construction Regulations of February 2014 and the Construction Safety, Health and Environmental Specifications.
4. | I hereby undertake that if my Tender is accepted, to provide before commencement of the Works under the contract or as required by the Conditions of the Contract, a suitable and sufficiently documented Construction Safety, Health and Environmental Management Plan in accordance with Regulation 7(1)(a) of the Construction Regulations of February 2014, which shall be subject for approval by the Client. |  |  |  |  | 2. All construction works where physical construction had started on or before the 7th of February 2014 must comply with the Construction Regulations 2003, and such construction works are exempted to comply with Construction Regulations 2014 until the 6th August 2015 and thereafter the Construction Regulations 2014 shall apply
5. | I confirm that I may not commence with any part of construction work under the contract until my Construction Safety Health and Environmental Management Plan has been approved in writing by the Client.
6. | I hereby confirm that copies of the following documentation will be kept on site for viewing and inspection purposes for the duration of the construction work:
| a) | Client's Construction Safety, Health and Environmental Specification.
| b) | Approved Construction Safety, Health and Environmental Plan.
| c) | Occupational Health and Safety Act, Act 85 of 1993.
| d) | Construction Regulations of February 2014.
7. | I agree that my failure to complete and execute this declaration to the satisfaction of the Client will mean that I am unable to comply with the requirements of the Occupational Health and Safety Act, Act 85 of 1993 and the Construction Regulations of February 2014, and accept that my Tender will be rejected.
Duly signed at…………………………………………………………. on this the…... day of……………………………. 20.…..
Full Name of Signatory |  |  |  | Name of Enterprise
Capacity of Signatory |  |  |  | Signature of authorised representative of Tenderer
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.18_Comp Enterprise Question
T2.18 Compulsory Enterprise Questionnaire
Project title: | KZN Public Works: 191 Prince Alfred Street
Tender no: | ZNTM012345W |  | Project Code: | 012345
The following particulars must be furnished. In the case of a joint venture, separate enterprise questionnaires in respect of each partner must be completed and submitted.
Section 1: Name of enterprise:
Section 2: VAT registration number, if any:
Section 3: CIDB registration number, if any:
Section 4: CSD Number:
Section 5: Particulars of sole proprietors and partners in partnerships
Name* |  | Identity number* |  | Personal income tax number*
* Complete only if sole proprietor or partnership and attach separate page if more than 6 partners
Section 6: Particulars of companies and close corporations
Company registration number
Close corporation number
Tax reference number
Section 7: SBD4 issued by National Treasury must be completed for each tender and be attached as a tender requirement
The undersigned, who warrants that he/she is duly authorised to do so on behalf of the enterprise:
i) authorizes the Employer to verify the tenderers tax clearance status from the South African Revenue Services that it is in order;
ii) confirms that neither the name of the enterprise or the name of any partner, manager, director or other person, who wholly or partly exercises, or may exercise, control over the enterprise appears on the Register of Tender Defaulters established in terms of the Prevention and Combating of Corrupt Activities Act of 2004;
iii) confirms that no partner, member, director or other person, who wholly or partly exercises, or may exercise, control over the enterprise appears, has within the last five years been convicted of fraud or corruption;
iv) confirms that I / we are not associated, linked or involved with any other tendering entities submitting tender offers and have no other relationship with any of the tenderers or those responsible for compiling the scope of work that could cause or be interpreted as a conflict of interest; and
iv) confirms that the contents of this questionnaire are within my personal knowledge and are to the best of my belief both true and correct.
Signed |  |  |  | Date
Name
Position
Enterprise name
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.19_TCS
T2.19 TAX COMPLIANCE STATUS (TCS) PIN TO VERIFY ON LINE COMPLIANCE SUPPLIER STATUS VIA SARS e-FILING
| Project title: | KZN Public Works: 191 Prince Alfred Street
| Tender no: | ZNTM012345W | Project Code: | 012345
TAX CLEARANCE REQUIREMENTS
It is a condition of Tender that the taxes of the successful tenderer must be in order, or that satisfactory arrangements have been made with South African Revenue Service (SARS) to meet the tenderer's tax obligations. It is a condition of this Offer of Commission that your practice remains in good standing with SARS (South African Revenue Services) in terms of its tax clearance.
1. | In order to meet this requirement Tenderders are required to apply via e-filing at any SARS branch office nationally. The Tax Complance Status (TCS) requirements are also applicable to foreign Tenderders / individuals who wish to submit tenders.
2. | SARS will then furnish the tenderer with a Tax Compliance Status (TCS) PIN that will be valid for a period of 1 (one) year from the date of approval.
3. | In tenders where Consortia / Joint Ventures / Sub-contractors are involved, each party must submit a separate Tax Compliance Status (TCS) PIN.
4. | Application for Tax Compliance Status (TCS) PIN can be done via e-filing at any SARS branch office nationally or on the website www.sars.gov.za.
5. | Tax Clearance Certificates may be printed via eFiling. In order to use this provision, taxpayers will need to register with SARS as eFilers through the website www.sars.gov.za.
IMPORTANT NOTICE
1. | The South African Revinue Services (SARS) has phased out the issuing of paper Tax Clearance Certificates.
2. | From 18 April 2016 SARS introduced an enhanced Tax Compliance (TCS) system.
3. | The new system allows taxpayers to obtain a Tax Compliance Status (PIN), which can be utilised by authorised third parties to varify taxpayers compliance status online via SARS e-filing.
4. | Tenderers are required to fill in clearly, legibly, in bold print and black ink the SARS (TCS) PIN number and Tax Reference number in the space hereunder:
Tax Compliance Status(TCS) PIN Number
Company / Tendering Entity Tax Reference Number
Name of Tenderer: ......................................................................................................................................
Signature of tenderer: ................................................................................................................................
Date: .........................................................................................................................................................
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.20_Good Standing with Comsnr
T2.20 CERTIFIED PROOF OF GOOD STANDING WITH THE COMPENSATION COMMISSIONER
Project title: | KZN Public Works: 191 Prince Alfred Street
Tender no: | ZNTM012345W | Project Code: | 012345
ATTACH A CERTIFIED COPY OF PROOF, THAT THE TENDERER IS IN GOOD STANDING WITH THE COMPENSATION COMMISSIONER, TO THIS PAGE FOR ADJUDICATION PURPOSES
NOTE
In the case of a Tender by a Joint Venture, certified copies of proof of Good Standing with the Compensation Commissioner in respect of each party to the Joint Venture must be attached to this page
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.21_Offer and Acceptance
T2.21 - FORM OF OFFER AND ACCEPTANCE
Tender no: ZNTM012345W
OFFER
The Employer, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of :
KZN Public Works: 191 Prince Alfred Street
The Tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and Addenda thereto as listed in the Returnable Schedules, and by submitting this Offer has accepted the Conditions of Tender.
By the representative of the Tenderer, deemed to be duly authorized, signing this part of this Form of Offer and Acceptance, the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the Conditions of Contract identified in the Contract Data.
THE OFFERED TOTAL OF THE PRICES INCLUSIVE OF VALUE ADDED TAX IS:
Amount (in words):
Amount in figures: | R
This Offer may be accepted by the Employer by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document to the Tenderer before the end of the period of validity stated in the Tender Data, whereupon the Tenderer becomes the party named as the Contractor in the Conditions of Contract identified in the Contract Data.
Signature (s)
Name (s)
Capacity
For the tenderer
(Name and address of tenderer)
Name and signature of witness |  | Date
ACCEPTANCE
By signing this part of this Form of Offer and Acceptance, the Employer identified below, accepts the Tenderer’s offer. In consideration thereof, the Employer shall pay the Contractor the amount due in accordance with the Conditions of Contract identified in the Contract Data. Acceptance of the Tenderer’s offer shall form an agreement between the Employer and the Tenderer upon the terms and conditions contained in this Agreement and in the contract that is the subject of this Agreement.
The terms of the contract, are contained in:
Part C1 | Agreement and Contract Data, (which includes this agreement)
Part C2 | Pricing data
Part C3 | Scope of work.
Part C4 | Site information and drawings and documents or parts thereof, which may be incorporated by reference into the above listed Parts.
Deviations from and amendments to the documents listed in the tender data and any addenda thereto as listed in the returnable schedules as well as any changes to the terms of the offer agreed by the tenderer and the employer during this process of offer and acceptance, are contained in the schedule of deviations attached to and forming part of this form of offer and acceptance. No amendments to or deviations from said documents are valid unless contained in this schedule.
The tenderer shall within two weeks after receiving a completed copy of this agreement, including the schedule of deviations (if any), contact the employer’s agent (whose details are given in the contract data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the contract data. Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.
Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed original copy of this document, including the schedule of deviations (if any). Unless the tenderer (now contractor) within five (5) working days of the date of such receipt notifies the employer in writing of any reason why he/she cannot accept the contents of this agreement, this agreement shall constitute a binding contract between the parties.
Signature (s)
Name (s)
Capacity
For the employer
(Name and address of employer)
Name and signature of witness
Schedule of Deviations
Notes:
1. The extent of deviations from the tender documents issued by the employer before the tender closing date is limited to those permitted in terms of the conditions of tender.
2. A tenderer’s covering letter shall not be included in the final contract document. Should any matter in such letter, which constitutes a deviation as aforesaid, become the subject of agreements reached during the process of offer and acceptance, the outcome of such agreement shall be recorded here.
3. Any other matter arising from the process of offer and acceptance either as a confirmation, clarification or change to the tender documents and which it is agreed by the Parties becomes an obligation of the contract shall also be recorded here.
4. Any change or addition to the tender documents arising from the above agreements and recorded here, shall also be incorporated into the final draft of the Contract.
1.1.1. Subject:
Details:
1.1.2. Subject:
Details:
1.1.3. Subject:
Details:
1.1.4. Subject:
Details:
By the duly authorised representatives signing this agreement, the employer and the tenderer agree to and accept the foregoing schedule of deviations as the only deviations from and amendments to the documents listed in the tender data and addenda thereto as listed in the returnable schedules, as well as any confirmation, clarification or changes to the terms of the offer agreed by the tenderer and the employer during this process of offer and acceptance.
It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Agreement shall have any meaning or effect in the contract between the parties arising from this agreement.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.21a_Confirmation of Receipt
T2.21a CONFIRMATION OF RECEIPT
KZN Public Works: 191 Prince Alfred Street
Tender no.: | ZNTM012345W | Project Code: | 012345
The Tenderer (now Contractor), identified in the Offer part of this Agreement hereby confirms receipt from the Employer, identified in the Acceptance part of this Agreement, of one fully completed original copy of this Agreement, including the Schedule of Deviations (if any) today:
the |  |  | (day)
of |  |  | (month)
(year)
at |  |  | (Place)
For the Contractor:
Signature
Name
Capacity
Signature and name of witness:
Signature
Name
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.22_Final BOQ
T2.22 - FINAL BILL OF QUANTITY SUMMARY
Project title: | KZN Public Works: 191 Prince Alfred Street
Tender no: | ZNTM012345W | Project Code: | 012345
ATTACH SUMMARY PAGE OF THE BILL OF QUANTITIES
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.23_PROOF OF MUN R&T
T2.23 - PROOF OF PAID MUNICIPAL RATES & TAXES
Project title: | KZN Public Works: 191 Prince Alfred Street
Tender no: | ZNTM012345W | Project Code: | 012345
ATTACH PROOF OF PAID MUNICIPAL RATES & TAXES TO THIS PAGE FOR ADJUDICATION PURPOSES
NOTE
In the case of a Quotation by a Joint Venture, proof of paid municipal rates and taxes for each member of the Joint Venture should be attached to this form.
Please do a print preview before printing
Back to Main Menu
Print
Print Preview
Enter Data

## T2.24_PROOF OF UIF
T2.24 - CERTIFIED PROOF OF VALID UIF REGISTRATION
| Project title: | KZN Public Works: 191 Prince Alfred Street
| Tender no: | ZNTM012345W | Project Code: | 012345
ATTACH A CERTIFIED COPY OF PROOF, THAT THE TENDERER IS IN GOOD STANDING WITH THE UIF TO THIS PAGE FOR ADJUDICATION PURPOSES
NOTE
1. | In the case of a Tender by a Joint Venture, certified copies of proof of Good Standing with the UIF in respect of each party to the Joint Venture must be attached to this page
2. | The contractor must submit proof of UIF Contributions made to the fund to the Principal Agent on a monthly basis for the duration of the contract. Should the contractor default on his monthly payments, the Employer will pay the outstanding payments due and the contractor will be liable for payments made by the Employer on behalf of the contractor, plus any additional cost associated with this process.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.25_NIPD
T2.25 THE NATIONAL INDUSTRIAL PARTICIPATION PROGRAMME
This document must be signed and submitted together with your tender
INTRODUCTION
The National Industrial Participation (NIP) Programme, which is applicable to all government procurement contracts that have an imported content, became effective on the 1 September 1996. The NIP policy and guidelines were fully endorsed by Cabinet on 30 April 1997. In terms of the Cabinet decision, all state and parastatal purchases / lease contracts (for goods, works and services) entered into after this date, are subject to the NIP requirements. NIP is obligatory and therefore must be complied with. The Industrial Participation Secretariat (IPS) of the Department of Trade and Industry (DTI) is charged with the responsibility of administering the programme.
1 |  | PILLARS OF THE PROGRAMME
1.1 |  | The NIP obligation is benchmarked on the imported content of the contract. Any contract having an imported content equal to or exceeding US$ 10 million or other currency equivalent to US$ 10 million will have a NIP obligation. This threshold of US$ 10 million can be reached as follows:
| (a) | Any single contract with imported content exceeding US$10 million.
or
| (b) | Multiple contracts for the same goods, works or services each with imported content exceeding US$3 million awarded to one seller over a 2 year period which in total exceeds US$10 million.
or
| (c) | A contract with a renewable option clause, where should the option be exercised the total value of the imported content will exceed US$10 million.
or
| (d) | Multiple suppliers of the same goods, works or services under the same contract, where the value of the imported content of each allocation is equal to or exceeds US$ 3 million worth of goods, works or services to the same government institution, which in total over a two (2) year period exceeds US$10 million.
1.2 |  | The NIP obligation applicable to suppliers in respect of sub-paragraphs 1.1 (a) to 1.1 (c) above will amount to 30 % of the imported content whilst suppliers in respect of paragraph 1.1 (d) shall incur 30% of the total NIP obligation on a pro-rata basis.
1.3 |  | To satisfy the NIP obligation, the DTI would negotiate and conclude agreements such as investments, joint ventures, sub-contracting, licensee production, export promotion, sourcing arrangements and research and development (R&D) with partners or suppliers.
1.4 |  | A period of seven years has been identified as the time frame within which to discharge the obligation.
2 |  | REQUIREMENTS OF THE DEPARTMENT OF TRADE AND INDUSTRY
2.1 |  | In order to ensure effective implementation of the programme, successful tenderers (contractors) are required to, immediately after the award of a contract that is in excess of R10 million (ten million Rands), submit details of such a contract to the DTI for reporting purposes.
2.2 |  | The purpose for reporting details of contracts in excess of the amount of R10 million (ten million Rands) is to cater for multiple contracts for the same goods, works or services; renewable contracts and multiple suppliers for the same goods, works or services under the same contract as provided for in paragraphs 1.1.(b) to 1.1. (d) above.
3 |  | Tender SUBMISSION AND CONTRACT REPORTING REQUIREMENTS OF TenderDERS AND SUCCESSFUL TenderDERS (CONTRACTORS)
3.1 |  | Tenderders are required to sign and submit this Standard Tenderding Document (SBD 5) together with the Tender on the closing date and time.
3.2 |  | In order to accommodate multiple contracts for the same goods, works or services; renewable contracts and multiple suppliers for the same goods, works or services under the same contract as indicated in sub-paragraphs 1.1 (b) to 1.1 (d) above and to enable the DTI in determining the NIP obligation, successful Tenderders (contractors) are required, immediately after being officially notified about any successful Tender with a value in excess of R10 million (ten million Rands), to contact and furnish the DTI with the following information:
• Tender / contract number.
• Description of the goods, works or services.
• Date on which the contract was accepted.
• Name, address and contact details of the government institution.
• Value of the contract.
• Imported content of the contract, if possible.
3.3 |  | The information required in paragraph 3.2 above must be sent to the Department of Trade and Industry, Private Bag X 84, Pretoria, 0001 for the attention of Mr. Elias Malapane within five (5) working days after award of the contract. Mr. Malapane may be contacted on telephone (012) 394 1401, facsimile (012) 394 2401 or e-mail at Elias@thedti.gov.za for further details about the programme.
4 |  | PROCESS TO SATISFY THE NIP OBLIGATION
4.1 |  | Once the successful Tenderder (contractor) has made contact with and furnished the DTI with the information required, the following steps will be followed:
a. the contractor and the DTI will determine the NIP obligation;
b. the contractor and the DTI will sign the NIP obligation agreement;
c. the contractor will submit a performance guarantee to the DTI;
d. the contractor will submit a business concept for consideration and approval by the DTI;
e. upon approval of the business concept by the DTI, the contractor will submit detailed business plans outlining the business concepts;
f. the contractor will implement the business plans; and
g. the contractor will submit bi-annual progress reports on approved plans to the DTI.
4.2 |  | The NIP obligation agreement is between the DTI and the successful Tenderder (contractor) and, therefore, does not involve the purchasing institution.
Tender number: |  |  |  | Closing date:
Name of tenderer:
Postal address:
Signature: |  |  |  | Name (in print):
Date:
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.26_CSD
T2.26 - CERTIFIED PROOF OF REGISTRATION ON CENTRAL SUPPLIERS DATABASE
| Project title: | KZN Public Works: 191 Prince Alfred Street
| Bid no: | ZNTM012345W | Project Code: | 012345
ATTACH A CERTIFIED COPY OF PROOF, THAT THE BIDDER IS REGISTERED ON THE CENTRAL SUPPLIERS DATABASE TO THIS PAGE FOR ADJUDICATION PURPOSES
NOTE
1. | In the case of a Tender by a Joint Venture, certified copies of proof of registration on the Central Suppliers Data Base in respect of each party to the Joint Venture must be attached to this page
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.27_CIDB Reg Number
T2.27 - CERTIFIED PROOF OF CIDB REGISTRATION NUMBER
| Project title: | KZN Public Works: 191 Prince Alfred Street
| Tender no: | ZNTM012345W | Project Code: | 012345
ATTACH A CERTIFIED COPY OF PROOF, THAT THE TENDERER IS REGISTERED WITH THE CONSTRUCTION INDUSTRY DEVELOPMENT BOARD (CIDB) TO THIS PAGE FOR ADJUDICATION PURPOSES
NOTE
1. | In the case of a Tender by a Joint Venture, certified copies of proof of registration with the CIDB in respect of each party to the Joint Venture must be attached to this page
2. | Only those tenderers who are registered with the CIDB, or are capable of being so prior to the evaluation of submissions, in a contractor grading designation equal to or higher than a contractor grading designation determined in accordance with the sum tendered, or a value determined in accordance with Regulation 25(1B) or 25(7A) of the Construction Industry Development Regulations for a :
6SF or higher, class of construction work, are eligible to have their Tenders evaluated.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.28_Deposit paid
T2.28 - PROOF OF PAYMENT OF TENDER DEPOSIT
| Project title: | KZN Public Works: 191 Prince Alfred Street
| Tender no: | ZNTM012345W | Project Code: | 012345
ATTACH A COPY OF PROOF OF PAYMENT WHERE AVAILABLE OF THE TENDER DEPOSIT BY THE TENDERER, TO THIS PAGE FOR ADJUDICATION PURPOSES
NOTE
1. | In the case of a Tender by a Joint Venture a certified copy of proof of payment where available of the tender deposit is only necessary in respect of any one party to the Joint Venture and must be attached to this page
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.29_Contract Forms-Part 1
T2.29 CONTRACT FORM - PURCHASE OF GOODS/WORKS-Part 1
THIS FORM MUST BE FILLED IN DUPLICATE BY BOTH THE SUCCESSFUL TENDERER (PART 1) AND THE PURCHASER (PART 2). BOTH FORMS MUST BE SIGNED IN THE ORIGINAL SO THAT THE SUCCESSFUL TENDERER AND THE PURCHASER WOULD BE IN POSSESSION OF ORIGINALLY SIGNED CONTRACTS FOR THEIR RESPECTIVE RECORDS.
PART 1 (TO BE FILLED IN BY THE TENDERER)
1. | I hereby undertake to supply all or any of the goods and/or works described in the attached tendering documents to Head: Public Works (Department of Public Works: Province of KwaZulu-Natal) in accordance
with the requirements and specifications stipulated in tender number ZNTM012345W at the price/s quoted.
2. | The following documents shall be deemed to form and be read and construed as part of this agreement:
(i) Tendering documents, viz
| - | Invitation to tender;
| - | Tax Compliance Status (TCS) PIN;
| - | Pricing schedule(s);
| - | Technical Specification(s);
| - | Preference claims for SPECIFIC GOAL/S, for this tender in terms of the Preferential Procurement Regulations 2022;
| - | Bidder's Disclosure;
| - | Special Conditions of Contract;
(ii) General Conditions of Contract for construction works Edition 2 - GCC2010; and
3. | (iii) Other (specify)
4. | I confirm that I have satisfied myself as to the correctness and validity of my Tender; that the price(s) and rate(s) quoted cover all the goods and/or works specified in the Tenderding documents; that the price(s) and rate(s) cover all my obligations and I accept that any mistakes regarding price(s) and rate(s) and calculations will be at my own risk.
5. | I accept full responsibility for the proper execution and fulfilment of all obligations and conditions devolving on me under this agreement as the principal liable for the due fulfilment of this contract.
6. | I declare that I have no participation in any collusive practices with any Tenderder or any other person regarding this or any other Tender.
I confirm that I am duly authorised to sign this contract.
| NAME (PRINT): |  | Witnesses:
| CAPACITY: |  | 1.
SIGNATURE:
| NAME OF FIRM: |  | 2.
| DATE: |  | Date:
Please do a print preview before printing
Back to Main Menu
Print
Print Preview
Enter Data

## T2.30_Contract Forms-Part 2
T2.30 CONTRACT FORM - PURCHASE OF GOODS/WORKS-Part 2
PART 2 (TO BE FILLED IN BY THE PURCHASER)
1. | I ______________________________________________________________________ in my capacity as
accepts your tender under reference ZNTM012345W dated _________________________for the supply of
goods/works indicated hereunder and/or further specified in the annexure(s).
2. | An official order indicating delivery instructions is forthcoming.
3. | I undertake to make payment for the goods/works delivered in accordance with the terms and conditions of the contract, within 30 (thirty) days after receipt of an invoice accompanied by the delivery note.
| ITEM NO. | PRICE (ALL APPLICABLE TAXES INCLUDED) |  | BRAND | DELIVERY PERIOD | B-BBEE STATUS LEVEL OF CONTRIBUTION |  | MINIMUM THRESHOLD FOR LOCAL PRODUCTION AND CONTENT (if applicable)
4. | I confirm that I am duly authorised to sign this contract.
SIGNED AT _____________________________________________ON____________________________
|  |  | [Place] |  |  |  | [Date]
| NAME (PRINT): |  |  |  |  | Witnesses:
| SIGNATURE: |  |  |  |  | 1.
2.
Date:
OFFICIAL STAMP:
Please do a print preview before printing
Please do a print preview before printing
Back to Main Menu
Print
Print Preview
Enter Data

## T2.31 OHSE Plan Structure
T2.31 - OHSE PLAN STRUCTURE
Project title: |  | KZN Public Works: 191 Prince Alfred Street
Tender no: |  | ZNTM012345W | Project Code: | 012345
A detailed OHSE Plan is to be submitted by the successful tenderer as per Construction Regulation 7(1)(a). The following are the minimum standard legal documentation that must form part of the OHSE Plan based on the risks attached in executing this project titled;
KZN Public Works: 191 Prince Alfred Street | However, it regularly occurs that a Contractor will at the same time submit tenders for a number of projects that are advertised during an overlapping period. Moreover, the Contractor may be busy with a Contract that is of the registered CIDB Grading Desi
NOTE TO THE COMPILER OF THIS DOCUMENT : PLEASE INSERT PROJECT SPECIFIC OHSE PLAN STRUCTURE AS RECEIVED FROM THE KZN DoPW OFFICIAL APPOINTED TO THE PROJECT OR AN APPOINTED PROFESSIONAL CONSTRUCTION HEALTH AND SAFETY AGENT.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.32 OHSE Client Requirements
T2.32 - OHSE CLIENT SPECIFIC REQUIREMENTS
Project title: | KZN Public Works: 191 Prince Alfred Street
Tender no: | ZNTM012345W
Project Code: | 012345
NOTE TO THE COMPILER OF THIS DOCUMENT : PLEASE INSERT PROJECT SPECIFIC OHSE CLIENT SPECIFIC REQUIREMENTS AS RECEIVED FROM THE KZN DoPW OFFICIAL APPOINTED TO THE PROJECT OR AN APPOINTED PROFESSIONAL CONSTRUCTION HEALTH AND SAFETY AGENT.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.33_Basline Rsk Ass
T2.33 - BASELINE RISK ASSESSMENT
Project title: | KZN Public Works: 191 Prince Alfred Street
Tender no: | ZNTM012345W | Project Code: | 012345
NOTE TO THE COMPILER OF THIS DOCUMENT : PLEASE INSERT PROJECT SPECIFIC BASELINE RISK ASSESSMENT AS RECEIVED FROM THE KZN DoPW OFFICIAL APPOINTED TO THE PROJECT OR AN APPOINTED PROFESSIONAL CONSTRUCTION HEALTH AND SAFETY AGENT.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## T2.34_Functionality Criteria
T2.34 - Functionality Criteria
The threshold score, below which tenderers are eliminated from further consideration, should be between 50% and 60%
Note to the Compiler : THIS IS MERELY AN EXAMPLE OF FUNCTIONALITY CRITERIA; FUNCTIONALITY CRITERIA MUST BE PROJECT SPECIFIC AND FORMULATED IN CONJUNCTION WITH THE DPW PROJECT LEADER
TENDER EVALUATION CRITERIA AND SCORING
| The weighting for Functionality ? out of 100 sub-points is as follows: | [8 empty] | Please do a print preview before printing
| Evaluation Criteria | Deliverables | Points |  | Minimum Sub-Points | Sub-Points |  | Sub-Criteria
1. | Financial Standing | The submission of all financial requirements stipulated in the tender | 30 | Points | 21 Sub-Points | 10 | Sub-points | Proof of working capital of at least 25% of project value
[6 empty] | 10 | Sub-points | Letters of credit reference from suppliers and credit limits to be stipulated with supporting documents
[6 empty] | 10 | Sub-points | Annual/Audited Financial Statement/Management Account/income and Expenditure Statements
Sub-points
Sub-points
Sub-points
2. | Competency, Experience and Resource Capacity | Tenderer to demonstrate their technical competency, human resource capacity and relevant project experience | 25 | Points | 17 Sub-Points | 5 | Sub-points | Detailed schedule of resources at all levels
[6 empty] | 5 | Sub-points | Schedule of years of experience on similar projects
[6 empty] | 5 | Sub-points | Schedule of experience on projects of similar value and duration (Past 3 years) – letters of award to be attached and practical completion certificate for all work completed in the preceding 3 years
[6 empty] | 5 | Sub-points | Demonstrated ability to work on an accelerated programme
[6 empty] | 5 | Sub-points | Experience in projects that have operational challenges i.e. public interface
Sub-points
Sub-points
Sub-points
3. | Tenderer’s Project Management Structure and Organogram and Experience of Resources Proposed for the Project | A tenderer that submits a detailed project organogram that sets out the roles and responsibilities of each proposed team member, which is backed up By their curriculum vitae that demonstrate extensive experience, together with a project implementation structure shall be allocated maximum sub-points. In all other instances zero (0) sub-points shall be allocated. | 10 | Points | 6 Sub-Points | 2 | Sub-points | Submission of a detailed organogram
[6 empty] | 1 | Sub-points | All key project resources have more than (5) years’ experience in the construction industry. All key project resources have experience in projects of a similar value and nature
[6 empty] | 1 | Sub-points | Detailed CV. Traceable reference. Certificates of qualified professionals in their full employment to be attached.
[6 empty] | 2 | Sub-points | Detailed CV of each team member (Category) and Traceable references to be detailed
[6 empty] | 2 | Sub-points | All key project resources are dedicated full time for the duration of the project including proof of UIF contributions
[6 empty] | 2 | Sub-points | Tenderer to demonstrate key/resource deployment over the various work package
Sub-points
Sub-points
4. | Tenderers ability to provide a Letter of Intent for the provision of a guarantee | Original letter of intent on a bank’s letterhead. | 5 | Points | 5 Sub-Points | 5 | Sub-points | Letter from a registered financial institution confirming intention to issue a provision of a guarantee
Sub-points
Sub-points
5. | Methodology and Approach | Detailed method statement and programme to be submitted. | 20 | Points | 16 Sub-Points | 3 | Sub-points | Site establishment indicating proposed layout for all prescribed facilities, hoarding, etc.
[6 empty] | 5 | Sub-points | Resourcing strategy for the various work breakdown structures including resource deployment plan (PS)
[6 empty] | 1 | Sub-points | Material storage, handling and distribution
[6 empty] | 3 | Sub-points | Productivity, programming, resource investment, progress tracking, corrective action plans, etc.
[6 empty] | 3 | Sub-points | Programme and progress reporting, including tracking of long lead procurement items
[6 empty] | 1 | Sub-points | OHS Management, compliance and reporting
[6 empty] | 1 | Sub-points | Site documentation control, filing and archiving
[6 empty] | 1 | Sub-points | Queries and information required approach
[6 empty] | 2 | Sub-points | Procurement of outsourced resources e.g. sub-contractors
Sub-points
Sub-points
Sub-points
6. | Enterprise Development (Targeting of Youth Owned Contractors) | Contract Participation Goal (CPG) to meet specified Enterprise Development target of 50% (fifty Percent) | 10 | Points | 5 Sub-Points | 0 ≤ 5 |  | Tendered CPG less than 50% pro-rata to minimum target
[6 empty] | 5 |  | Tendered CPG is 50%
[6 empty] | ≥ 5 ≥ 10 |  | Tendered CPG is greater than 50% pro-rata to minimum target
TENDER EVALUATION CRITERIA AND SCORING PRICE AND SPECIFIC GOALS
| Evaluation Criteria | Deliverables / Goal |  |  | Sub-Criteria |  |  | Points
| Price | A maximum of 80 or 90 Points is allocated for Price. | [5 empty] | Points
| Specific Goal 1 | 0 | [5 empty] | Points | Note to the Compiler of this Document: Preference Points must be awarded for specific goals. The Specific Goals and Number of Points allocated Per Goal indicated on this form must correspond exactly with Table 1 of SBD 6.1 (T2.9)
| Specific Goal 2 | 0 | [5 empty] | Points
| Specific Goal 3 | 0 | [5 empty] | Points
| Specific Goal 4 | 0 | [5 empty] | Points
| Specific Goal 5 | 0 | [5 empty] | Points
| Specific Goal 6 | 0 | [5 empty] | Points
| Specific Goal 7 | 0 | [5 empty] | Points
| Specific Goal 8 | 0 | [5 empty] | Points
Please do a print preview before printing
Back to Main Menu
Print
Print Preview
Enter Data

## T2.35_ SBD 1
PART A
INVITATION TO TENDER - SBD 1
YOU ARE HEREBY INVITED TO TENDER FOR REQUIREMENTS OF THE KWA-ZULU NATAL DEPARTMENT OF WORKS | [13 empty] | NOTE TO COMPILER : this is a standard tender document - please complete the parts highlighted in blue only
TENDER NUMBER: | ZNTM012345W |  | CLOSING DATE: |  | As Per Tender Advert | [5 empty] | CLOSING TIME: |  | 11:00
DESCRIPTION
THE SUCCESSFUL TENDERER WILL BE REQUIRED TO FILL IN AND SIGN A WRITTEN CONTRACT
TENDER RESPONSE DOCUMENTS MAY BE DEPOSITED IN THE TENDER BOX SITUATED AT (STREET ADDRESS)
SUPPLIER INFORMATION
NAME OF TENDERER
POSTAL ADDRESS
STREET ADDRESS
TELEPHONE NUMBER |  | CODE | [6 empty] | NUMBER
CELLPHONE NUMBER
FACSIMILE NUMBER |  | CODE | [6 empty] | NUMBER
E-MAIL ADDRESS
VAT REGISTRATION NUMBER
|  | TCS PIN: |  |  |  |  | CSD No:
B-BBEE STATUS LEVEL VERIFICATION CERTIFICATE (Tick YES or NO) |  | Yes |  |  |  |  | B-BBEE STATUS LEVEL SWORN AFFIDAVIT (Tick YES or NO) |  |  |  |  | Yes
|  | No | [9 empty] | No
If YES, State the name of the verification agency accredited by SANAS
ARE YOU THE ACCREDITED REPRESENTATIVE IN SOUTH AFRICA FOR THE GOODS /SERVICES /WORKS OFFERED? |  | Yes |  | NO |  |  |  | ARE YOU A FOREIGN BASED SUPPLIER FOR THE GOODS /SERVICES /WORKS OFFERED? |  | YES |  | NO
|  | [IF YES ENCLOSE PROOF] | [5 empty] | (IF YES ANSWER PART B:3 BELOW)
SIGNATURE OF TENDERER | [7 empty] | DATE
CAPACITY UNDER WHICH THIS TENDER IS SIGNED (Attach proof of authority to sign this tender; e.g. resolution of directors, etc.)
TOTAL NUMBER OF ITEMS OFFERED | [7 empty] | TOTAL TENDER PRICE (ALL INCLUSIVE)
TENDERING PROCEDURE ENQUIRIES MAY BE DIRECTED TO: | [5 empty] | TECHNICAL INFORMATION MAY BE DIRECTED TO:
DEPARTMENT/ PUBLIC ENTITY | [5 empty] | CONTACT PERSON
CONTACT PERSON | [5 empty] | TELEPHONE NUMBER
TELEPHONE NUMBER | [5 empty] | FACSIMILE NUMBER
FACSIMILE NUMBER | [5 empty] | E-MAIL ADDRESS
E-MAIL ADDRESS
PART B
TERMS AND CONDITIONS FOR TENDERING - SBD 1
1. TENDER SUBMISSION:
1.1. TENDERS MUST BE DELIVERED BY THE STIPULATED TIME TO THE CORRECT ADDRESS. LATE TENDERS WILL NOT BE ACCEPTED FOR CONSIDERATION.
1.2. ALL TENDERS MUST BE SUBMITTED ON THE OFFICIAL FORMS PROVIDED (NOT TO BE RE-TYPED) OR ONLINE
1.3. TENDERERS MUST REGISTER ON THE CENTRAL SUPPLIER DATABASE (CSD) TO UPLOAD MANDATORY INFORMATION NAMELY: ( BUSINESS REGISTRATION/ DIRECTORSHIP/ MEMBERSHIP/IDENTITY NUMBERS; TAX COMPLIANCE STATUS; AND BANKING INFORMATION FOR VERIFICATION PURPOSES). B-BBEE CERTIFICATE OR SWORN AFFIDAVIT FOR B-BBEE MUST BE SUBMITTED TO TENDERING INSTITUTION.
1.4. WHERE A TENDERER IS NOT REGISTERED ON THE CSD, MANDATORY INFORMATION NAMELY: (BUSINESS REGISTRATION/ DIRECTORSHIP/ MEMBERSHIP/IDENTITY NUMBERS; TAX COMPLIANCE STATUS MAY NOT BE SUBMITTED WITH THE TENDER DOCUMENTATION. B-BBEE CERTIFICATE OR SWORN AFFIDAVIT FOR B-BBEE MUST BE SUBMITTED TO TENDERING INSTITUTION.
1.5. THIS TENDER IS SUBJECT TO THE PREFERENTIAL PROCUREMENT POLICY FRAMEWORK ACT 2000 AND THE PREFERENTIAL PROCUREMENT REGULATIONS, 2022, THE GENERAL CONDITIONS OF CONTRACT ARE THE CLAUSES CONTAINED IN THE GENERAL CONDITIONS OF CONTRACT (2010) (SECOND EDITION) PUBLISHED BY THE SOUTH AFRICAN INSTITUTION OF CIVIL ENGINEERING. COPIES OF THESE CONDITIONS OF CONTRACT MAY BE OBTAINED THROUGH MOST REGIONAL OFFICES OF THE SOUTH AFRICAN INSTITUTION OF CIVIL ENGINEERING, OR BY VISITING THEIR WEBSITE AT WWW.SAICE.ORG.ZA; AND, IF APPLICABLE, ANY OTHER LEGISLATION OR SPECIAL CONDITIONS OF CONTRACT.
2. TAX COMPLIANCE REQUIREMENTS
2.1 TENDERERS MUST ENSURE COMPLIANCE WITH THEIR TAX OBLIGATIONS.
2.2 TENDERERS ARE REQUIRED TO SUBMIT THEIR UNIQUE PERSONAL IDENTIFICATION NUMBER (PIN) ISSUED BY SARS TO ENABLE THE ORGAN OF STATE TO VIEW THE TAXPAYER’S PROFILE AND TAX STATUS.
2.3 APPLICATION FOR TAX COMPLIANCE STATUS (TCS) OR PIN MAY ALSO BE MADE VIA E-FILING. IN ORDER TO USE THIS PROVISION, TAXPAYERS WILL NEED TO REGISTER WITH SARS AS E-FILERS THROUGH THE WEBSITE WWW.SARS.GOV.ZA.
2.4 TENDERERS MAY ALSO SUBMIT A PRINTED TCS TOGETHER WITH THE TENDER.
2.5 IN TENDERS WHERE CONSORTIA / JOINT VENTURES / SUB-CONTRACTORS ARE INVOLVED, EACH PARTY MUST SUBMIT A SEPARATE PROOF OF TCS / PIN / CSD NUMBER.
2.6 WHERE NO TCS IS AVAILABLE BUT THE TENDERER IS REGISTERED ON THE CENTRAL SUPPLIER DATABASE (CSD), A CSD NUMBER MUST BE PROVIDED.
2.7 NO BIDS WILL BE CONSIDERED FROM PERSONS IN THE SERVICE OF THE STATE, COMPANIES WITH DIRECTORS WHO ARE PERSONS IN THE SERVICE OF THE STATE, OR CLOSE CORPORATIONS WITH MEMBERS PERSONS IN THE SERVICE OF THE STATE.
3. QUESTIONNAIRE TO TENDERING FOREIGN SUPPLIERS
3.1. IS THE TENDERER A RESIDENT OF THE REPUBLIC OF SOUTH AFRICA (RSA)? | [6 empty] | YES |  |  |  | NO
3.2. DOES THE TENDERER HAVE A BRANCH IN THE RSA? | [6 empty] | YES |  |  |  | NO
3.3. DOES THE TENDERER HAVE A PERMANENT ESTABLISHMENT IN THE RSA? | [6 empty] | YES |  |  |  | NO
3.4. DOES THE TENDERER HAVE ANY SOURCE OF INCOME IN THE RSA? | [6 empty] | YES |  |  |  | NO
IF THE ANSWER IS “NO” TO ALL OF THE ABOVE, THEN, IT IS NOT A REQUIREMENT TO OBTAIN A TAX COMPLIANCE STATUS / TAX COMPLIANCE SYSTEM PIN CODE FROM THE SOUTH AFRICAN REVENUE SERVICE (SARS) AND IF NOT REGISTER AS PER 2.3 ABOVE.
NB: FAILURE TO PROVIDE ANY OF THE ABOVE PARTICULARS MAY RENDER THE TENDER INVALID.

## T2.36_CIBD B U I L D
T2.36 THE CIDB B U I L D PROGRAMME
This document must be signed and submitted together with your tender
INTRODUCTION
In terms of sections 5(2) of the Construction Industry Development Board Act, 2000 (Act no.38 of 2000) (the Act), the Construction Industry Development Board is empowered to promote best practice Standards. This best practice Standard for developing skills through infrastructure contracts, establishes the minimum contract skills development goals to be achieved in the performance of such contracts relating to the provision of workplace opportunities, linked to or leading to: a) a part- or full occupational qualification registered on the National Qualification Framework; b) a trade qualification leading to a listed trade (GG No. 35625, 31 August 2012); c) a national diploma registered on the National Qualification Framework; and d) registration in a professional category by one of the professional bodies listed in the standard
The contractor shall achieve in the execution of this contract the Contract Participation Goals (CPG) relating to the engagement of targeted enterprises as established in the CIDB Standard for Indirect Targeting for Enterprise Development through Construction works Contracts Published in Government Gazette No 48491)
Requirements Contract skills development goal (CSDG) 1. The contractor shall attain or exceed the contract skills development goal in the performance of the contract or the execution of an order. 2. The contract skills development goal shall be expressed as in 3 for engineering and construction works and design and build and services contracts. 3. In the case of engineering and construction works contracts, design and build contracts and services contracts the contract skills participation goals, expressed in Rand, shall be no less than the sub-total multiplied by a percentage (%) factor given in Table 1 for the applicable class of construction works used in the application of the Construction Industry Development Regulations, issued in terms of the Construction Industry Development Board Act of 2000.
The Contractor undertakes to submit the following Enterprise Development Forms: Form ED 105P: Project Interim Report Form ED 104P: Enterprise Development Declaration Form ED 101P: Project Completion Report ; and the Professional Project Leader is required to approve these forms. The Contractor undertakes to submit the following Skills Development Forms: Form SD 101P: Project Completion Report Form SD 102P: Notification of the Issue of Cancellation / Termination of Contract Form SD 104P: Project Training Plan; and the Professional Project Leader is required to approve these forms.
NOTE TO THE COMPILER: Delete whichever Forms are NOT APPLICABLE
TABLE 1
Class of construction works as identified in terms of Regulation 25(3) of the Construction Industry Regulations 2004 |  | Construction skills Development Goal (CSDG) %
Designation | Description
CE | Civil Engineering | 0.25
EE | Electrical Engineering works (buildings) | 0.25
EP | Electrical Engineering Works (Infrastructure) | 0.25
GB | General Building | 0.50
ME | Mechanical Engineering Works | 0.25
SB | Specialist | 0.25
The Standard for developing skills through infrastructure contracts obligation agreement is between the KwaZulu Natal Department of Public Works and Infrastructure and the successful Tenderer (contractor)
Tender number: |  |  | Closing date:
Name of tenderer:
Postal address:
Signature: |  |  | Name (in print):
Date:

## Cover Page- Section 2 of 2
PROVINCIAL ADMINISTRATION OF KWAZULU-NATAL
DEPARTMENT OF PUBLIC WORKS
Please do a print preview before printing
BILLS OF QUANTITIES
with GCC for Construction Works - Second Edition 2010
CONTRACTUAL SECTION
ONE VOLUME APPROACH
KZN Public Works: 191 Prince Alfred Street
Engineer/Principal Agent | [Identify Agent's Service, eg. Engineer]
[Identify the Company or person] | [Agents Name]
[P.O. Box number] | [P.O. Box number]
[Name of town] | [Name of town]
[Name of City]
[Code] | [Code]
[Telephone Number including Area Code] - Tel Number | [Tel Number including Area Code] - Tel Number
[Fax Number including Area Code] - Fax Number | [Fax Number including Area Code] - Fax Number
[Email Address] | [Email Address]
Employer: | Region:
Head: Public Works | Regional Manager
KZN Department of Public Works | KZN Department of Public Works
Private Bag X 9041 | X9041
PIETERMARITZBURG | Pietermarizburg
3200 | 3200
Tel Number: 033 - 8971300 | Tel Number: | 033-897 1421/1422
Fax Number: 033 - 8971399 | Fax Number: | 033-897 1399
Tender Number: ZNTM012345W | Project Code: | 012345
CIDB Grading: 6SF | Document Date: | As Per Tender Advert
ECDP Number: N/A
Contracting Party: __________________________________________________________________________
CIDB Registration number: | ______________________________________
Central Suppliers Database Registration Number: | ______________________________________
Back to Main Menu
Print
Print Preview
Enter Data

## The Contract - Fly
KZN Public Works: 191 Prince Alfred Street
THE CONTRACT
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C1_Agrment & Contract Data-fly
KZN Public Works: 191 Prince Alfred Street
C1 - AGREEMENT AND CONTRACT DATA
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## Form offer & Accpt - fly
KZN Public Works: 191 Prince Alfred Street
FORM OF OFFER AND ACCEPTANCE
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C1.1_Offer & Acceptance
FORM OF OFFER AND ACCEPTANCE
Tender No - ZNTM012345W
KZN Public Works: 191 Prince Alfred Street
C.1.1 - FORM OF OFFER AND ACCEPTANCE
THE OFFER AND ACCEPTANCE FORM IS BOUND INTO SECTION 1 (See end of Returnable Documents) OF THIS DOCUMENT AS PART OF THE RETURNABLE DOCUMENTS. ONCE A CONTRACT IS CONCLUDED WITH A SUCCESSFUL TENDERER, THIS PAGE WILL BE REPLACED WITH THE FILLED AND SIGNED OFFER AND SIGN ACCEPTANCE BY THE EMPLOYER AND IT WILL BECOME PART OF THE CONTRACT. PLEASE SUBMIT THE OFFER AND ACCEPTANCE FORM WITH THE OTHER RETURNABLE DOCUMENTS.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C1.2_Contract Data-fly
KZN Public Works: 191 Prince Alfred Street
C1.2 - CONTRACT DATA
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C1.2_Contract Data
C 1.2 CONTRACT DATA:
with GCC for Construction Works - Second Edition 2010
CONTRACT DATA FOR:
KZN Public Works: 191 Prince Alfred Street
Tender no: | ZNTM012345W
The General Conditions of Contract are the clauses contained in the General Conditions of Contract (2010) (Second Edition) published by the South African Institution of Civil Engineering. Copies of these conditions of contract may be obtained through most regional offices of the South African Institution of Civil Engineering, telephone number 011 805 5947 or by visiting their website at www.saice.org.za.
The contractor shall achieve in the execution of this contract the Contract Participation Goals (CPG) relating to the engagement of targeted enterprises as established in the CIDB Standard for Indirect Targeting for Enterprise Development through Construction works Contracts Published in Government Gazette No 48491)
CONTRACT SPECIFIC DATA The following contract specific data are applicable to this contract:
CONTRACT VARIABLES This schedule contains all variables specific to this document and is divided into pre-tender and post-tender categories. The pre-tender category must be completed in full and included in the tender documents. Both the pre-tender and post-tender categories form part of this agreement. Spaces requiring information must be filled in, shown as ‘not applicable’ or deleted but not left blank. Where choices are offered, the non-applicable items are to be deleted. Where insufficient space is provided the information should be annexed hereto and cross referenced to the applicable clause of the schedule. Key cross reference clauses are italicised in [ ] brackets. The Engineer/Principal Agent, in accordance with Clause 1.1.1.16, shall obtain the specific approval from the Employer before executing any of his functions according to the "Conditions under which Consultants are appointed", or in the event where an employee of the Employer represents the Employer, the relevant General Delegations applicable at the time of executing his/her duties as described in Clause 3.1.2.
Part 1: CONTRACT DATA PROVIDED BY THE EMPLOYER:
PRE-TENDER INFORMATION
CONTRACTING AND OTHER PARTIES
[1.1.1.15] | Employer:
Head: Public Works (KZN Department of Public Works: Province of KwaZulu-Natal)
Postal address:
Private Bag X 9041
PIETERMARITZBURG
3200
| Tel: | 033 - 8971399 |  |  |  | Fax: | 033 - 8971300
[1.2.1.2] | Physical address:
191 Prince Alfred Street
PIETERMARITZBURG
3200
Quantity Surveyor
[1.1.15] | [Identify the Company or person]
Postal address:
[P.O. Box number]
[Name of town]
[Code]
| Tel: | [Telephone Number including Area Code] |  |  |  | Fax: | [Fax Number including Area Code]
[1.2.2] | Physical address:
ABC Street
[Name of town]
[Code]
[1.1.1.16] | Employers Agent 1
[Agents Name]
Agent’s service:
[Identify Agent's Service, eg. Engineer]
Postal address:
[P.O. Box number]
[Name of town]
[Code]
| Tel: | [Tel Number including Area Code] |  |  |  | Fax: | [Fax Number including Area Code]
Employers Agent 2
[Agents Name]
Agent’s service:
[Identify Agent's Service, eg. Engineer]
Postal address:
[P.O. Box number]
[Name of town]
[Code]
| Tel: | [Tel Number including Area Code] |  |  |  | Fax: | [Fax Number including Area Code]
Employers Agent 3
[Agents Name]
Agent’s service:
[Identify Agent's Service, eg. Engineer]
Postal address:
[P.O. Box number]
[Name of town]
[Code]
| Tel: | [Tel Number including Area Code] |  |  |  | Fax: | [Fax Number including Area Code]
Employers Agent 4
[Agents Name]
Agent’s service:
[Identify Agent's Service, eg. Engineer]
Postal address:
[P.O. Box number]
[Name of town]
[Code]
| Tel: | [Tel Number including Area Code] |  |  |  | Fax: | [Fax Number including Area Code]
Tender no: | ZNTM012345W
Employers Agent 5
[Agents Name]
Agent’s service:
[Identify Agent's Service, eg. Engineer]
Postal address:
[P.O. Box number]
[Name of town]
[Code]
| Tel: insert tel no insert fax no | [Tel Number including Area Code] |  |  |  | Fax: | [Fax Number including Area Code]
Employers Agent 6
[Agents Name]
Agent’s service:
[Identify Agent's Service, eg. Engineer]
Postal address:
[P.O. Box number]
[Name of town]
[Code]
| Tel: insert tel no insert fax no | [Tel Number including Area Code] |  |  |  | Fax: | [Fax Number including Area Code]
Employers Agent 7
[Agents Name]
Agent’s service:
[Identify Agent's Service, eg. Engineer]
Postal address:
[P.O. Box number]
[Name of town]
[Code]
| Tel: insert tel no insert fax no | [Tel Number including Area Code] |  |  |  | Fax: | [Fax Number including Area Code]
Employers Agent 8
[Agents Name]
Agent’s service:
[Identify Agent's Service, eg. Engineer]
Postal address:
[P.O. Box number]
[Name of town]
[Code]
| Tel: insert tel no insert fax no | [Tel Number including Area Code] |  |  |  | Fax: | [Fax Number including Area Code]
PART 1: DATA PROVIDED BY THE EMPLOYER
[1.1.1.13] | Defects Liability Period
| The defects liability period is: |  |  | A time measured from the date of the Certificate of Completion.
Defects Liability Period is 12 Months for the whole of the Works
Latent Defect Period
[5.16.3] | The latent defect period is: |  |  | 5 years after the Final Approval Certificate
Documentation required before Commencement of the Works:
[5.3.1] | The documentation required before commencement with the Works execution are;
[4.3] | Health and Safety Plan |  |  | The Contractor shall deliver his Health and Safety Plan of the Works within 14 calendar days after notice from the Employer, prior to the Commencement Date.
[5.6] | Initial Programme |  |  | The Contractor shall deliver his programme of work within 10 calendar days after notice from the Employer, prior to the Commencement Date.
[6.2] | Guarantee |  |  | The Contractor shall deliver his chosen Guarantee (security) for this Works within 14 calendar days after notice from the Employer, prior to the Commencement Date.
[8.6] | Insurance |  |  | The Contractor shall deliver his insurance for the Works within 14 calendar days after notice from the Employer, prior to the Commencement Date.
| Cash flow by contractor |  |  | The Contractor shall deliver his Cash flow for the Works within 14 calendar days after notice from the Employer, prior to the Commencement Date.
| Priced Bill of Quantity |  |  | The Contractor shall deliver his Priced Bill of Quantity within 14 calendar days after notice from the Employer, prior to the Commencement Date.
| Programme |  |  | The Contractor is required to submit his Programme of Works in terms of Clause 5.6.1 and 5.3.1 and the Principal Agent is required to approve this within 7 days in terms of Clause 5.6.3
Other requirements
[5.3.2] | The time to submit the documentation required before commencement with Works execution is: | [6 empty] | 14 | calendar days
Non-Working days
[5.8.1] | Non-Working days |  |  |  | Sundays
| Special non- working days |  |  |  | All Nationally Recognized Public Holidays and the year end break | [7 empty] | 2013-01-16
[5.8.1] | First Year end break - commences |  |  |  | 2016-12-16 | [7 empty] | 2013-01-16
| ends on |  |  |  | 2017-01-09
| Second Year end break - commences |  |  |  | N/A
| ends on |  |  |  | N/A
| Third Year end break - commences |  |  |  | N/A
| ends on |  |  |  | N/A
| Fourth Year end break - commences |  |  |  | N/A
| ends on |  |  |  | N/A
Engineer/Principal Agent to consult with Employer
[3.1.3] | The Engineer shall obtain the specific approval from the Employer before executing any of his functions according to the "Conditions under which Consultants are appointed", or in the event where an employee of the Employer represents the Employer, the relevant General Delegations applicable at the time of executing his/her duties.
Security
[6.2.1] | The time to deliver the deed of guarantee is Prior to site hand over in terms of clause 5.3.1 and 5.3.2.
Clause 7: in contract data variables
[6.2.1] | Please see CONTRACT DATA - below to select Guarantee Option
The liability of the guarantee shall be for … A percentage of the Tender Sum usually decided in conjunction with the limit of the retention money required in terms of Clause 49.3. For financially stronger contractors the liability for the guarantee is usually a higher percentage with the limit of retention money at a lower amount.
Commencement Date
Commencement date means the date of Site Hand over that should not occur prior to the tenderer receiving one fully signed copy of the Offer and Acceptance in terms of the Form of Offer and Acceptance.
The Agreement comes into effect on the date when; The tenderer receives one fully completed original copy of this document, including the Schedule of Deviations (if any) The agreement (“this document”) consists of; 1. Agreement and Conditions of Contract. 2. Form of Offer and Acceptance. 3. Contract Data. 4. Scope of Works. 5. Site Information. 6. Drawings & documents referred to in the 1 to 4 above. (See Form of Offer and Acceptance)
[5.3.1] | The contractor shall commence executing the Works within 7 calendar days from the Commencement Date.
[5.4.1] | Possession of the site will be given within 10 calendar days after the contractor has fulfilled the conditions (4.3, 5.6, 6.2, 8.6) and received the notification from the Employer of Site Hand Over where the contractor will receive one fully signed copy of the Form of Offer and Acceptance from the employer. | [9 empty] | 2013-01-16
[5.6.1] | The Contractor shall deliver his programme of work within 10 calendar days after notice from the Employer, prior to the Commencement Date.
CONTRACT DETAILS
[1.1.1.33] | Works description: Refer to document C3 – Scope of Work.
[1.1.1.30] | Site description: Refer to document C4 – Site Information.
Specific options that are applicable to a State organ only
Where so :
1) Interest rate legislation:
[6.10.6.2] | (a) in respect of interest owed by the employer, the interest rate as determined by the Minister of Justice and Constitutional Development from time to time, in terms of section 1(2) of the Prescribed Rate of Interest Act, 1975 (Act No. 55 of 1975), will apply; and
(b) in respect of interest owed to the employer, the interest rate as determined by the Minister of Finance, from time to time, in terms of section 80(1)(b) of the Public Finance Management Act, 1999 (Act No. 1 of 1999), will apply
| 2) Lateral support insurance to be effected by the contractor: | [7 empty] | Yes X | No
| 3) Payment will be made for materials and goods | [7 empty] | Yes X | No
| 4) Dispute resolution by litigation | [7 empty] | Yes | No X
| 5) Extended defects liability period applicable to the following elements: | [7 empty] | Electrical, Mechanical and Civil work
[8.6.1.1.2] | The Value of material, supplied by the Employer, and not included in the Contract Price, is: | [6 empty] | 0
[8.6.1.1.3] | The amount to cover Professional Fees, not included in the Contract Price, for repairing damage and loss to be included in the insurance:
30% of the Contract Price
[8.6.1.3] | The limit for indemnity for liable insurance is: |  |  |  |  | Unlimited
[6.5.1.2.3] | The percentage allowance to cover overhead charges for contractor and subcontractors, is: | [6 empty] | 33.3%
[1.1.1.14] | Practical Completion Date
| The Practical Completion date is: |  |  | A time measured from the Commencement date.
For the works as a whole:
| The whole of the works shall be completed within: |  |  |  |  | 19 | Months (which shall be deemed to include all Non – Working Days, Special Non – Working Days and the year-end Builders Annual Industry Holiday Periods).
[5.5.1] | The date for practical completion shall be |  |  |  |  | To be determined
[5.13.1] | The penalty per calendar day shall be : |  |  |  |  | 0.04% of the Contract Price, rounded to the nearest R10
For the works in sections:
The date for practical completion from the commencement date and the penalty per calendar day:
Portion 1:
[5.5.1] | 3 Calendar Months
[5.13.1] | 0.04% of the Contract Price, rounded to the nearest R10
Portion 2:
[5.5.1] | N/A
[5.13.1] | 0.04% of the Contract Price, rounded to the nearest R10
Portion 3:
[5.5.1] | N/A
[5.13.1] | 0.04% of the Contract Price, rounded to the nearest R10
Portion 4:
[5.5.1] | N/A
[5.13.1] | 0.04% of the Contract Price, rounded to the nearest R10
Portion 5:
[5.5.1] | N/A
[5.13.1] | 0.04% of the Contract Price, rounded to the nearest R10
Portion 6:
[5.5.1] | N/A
[5.13.1] | 0.04% of the Contract Price, rounded to the nearest R10
[1.3.2] | The law applicable to this agreement shall be that of the: Republic of South Africa
[6.10.1.5] | The percentage advance on materials not yet built into the Permanent Works is: | [6 empty] | 80%
[6.10.3] | Percentage retention on amounts due to contractor is: |  |  |  |  | The Percentage retention is nil. The only security required by the Employer will be such as selected by the Contractor on the Form of Offer and Acceptance and Part 2: CONTRACT DATA PROVIDED BY THE CONTRACTOR, point 2 - Documents, of the Contract Data.
Amended 13/6/2014 - Also see SCM Circ No 8 of 2013
| Maximum retention is: |  |  | 0% | of the Contract Price | [6 empty] | Amended 13/6/2014
[6.8.1] | Notwithstanding anything to the contrary contained in the General conditions of Contract and Preliminaries, this contract could only, when the construction period exceeds 6 months and the contract exceeds R1,000,000.00, be subject to a Contract Price Adjustment Factor. | [10 empty] | ?
[6.8.2] [6.8.3] | Clause 6.8.2 the last part of the sentence saying "calculated according to the formula and the conditions set out in the Contract Price Adjustment Schedule." must be replaced by "calculated according to the Contract Price Adjustment Provisions (CPAP) Indices Application Manual for use with P0151 indices (Revised 1 January 2013)" as published by Statistics South Africa. The Contract Price Adjustment Provision (CPAP) will be subject to the most recently released indices by Statistic South Africa. Tenderers are advised that with reference to Clause 3.4.6 of the Contract Price Adjustment Provisions (CPAP) Indices Applications Manual, the Head: Public Works will not accept the submission by Tenderers of lists of additional items."
[6.8.2] [6.8.3] | Where this contract is a Lump Sum contract, the contract will only be subject to Contract Price Adjustment Provisions (CPAP)(Revised 1 January 2013) where the contract period equals or exceeds 6 calendar months. The applicable work group shall be WG 180 for domestic buildings or WG 181 for commercial and industrial buildings only.
[5.14.5] | The following clause must be added to clause 5.14.5:
|  | [5.14.5.6] | The employers agent shall submit the final account within 3 calendar months to the principal agent. | [8 empty] | Requested by Tholang Chakana Acting Regional Manager Midlands Region
[10.5] | The determinations of disputes shall be by ARBITRATION ONLY.
[10.5.3] | The number of Adjudication Board Members to be appointed is: | [5 empty] | One
[10.9.1] | Replace the last part of the clause with the following: "..on the application of either party, by the Chairman, or his nominee of the Association of Arbitrators."
Where CPAP is applicable, the contract sum will be adjusted in accordance with the Contract Price Adjustment Provisions (CPAP) as set out in the CPAP Indices Application Manual as published by Statistics South Africa, dated 1 January 2013 and any amendments thereto:
1) Glass etc. measured in specialist section Metalwork, will be adjusted in terms of the index for that work group unless specifically stated otherwise in the bills of quantities.
2) In case of uninterruptible power supplies, elevators, escalators and hoists, generating sets, motor-alternator sets and intercommunication systems shall be adjusted in accordance with Work Group 170.
3) Further to clause 3.4.6 of the CPAP Indices Application Manual, the listing of additional items for exclusion by Tenderer's, will not be permitted.
Alternative Indices: Not Applicable
Details of changes made to the General Conditions of Contract for construction works (2010) Second Edition
Clause
[1.1] | [1.1.1.5] | COMMENCEMENT DATE – means the actual date of Site Hand over that should not occur prior to the Tenderer receiving one fully signed copy of the Offer and Acceptance in terms of the Form of Offer and Acceptance. | [9 empty] | 2013-01-16
| [5.12.2.2] | ABNORMAL CLIMATIC CONDITIONS - means conditions over and above what could reasonably be expected for the specific locality where the Works are being executed and include inter alia exessive rain, heat, cold, wind and any other climatic condition that would not normally be experienced during the season that the Works are executed in that area. The South African Weather Service's (http://www.weathersa.co.za) 10 year average climatic conditions statistics would be what could be reasonably expected for the specific locality where the Works are executed.
| [6.2.1] | CONSTRUCTION GUARANTEE – means an on demand guarantee at call obtained by the contractor from an institution approved by the employer in terms of the employer's construction guarantee form as selected in the Offer and Acceptance Form and the contract data.
CONSTRUCTION PERIOD – means the period commencing on the commencement date and ending on the date of due completion date. This period will be deemed to commence on actual site hand over date to the contractor and end on the date of practical completion and shall include all annual industrial holiday periods, Sundays and public holidays.
CORRUPT PRACTICE – means the offer, giving, receiving, or soliciting of anything of value to influence the action of a public official in the procurement process or in contract execution.
FINAL ACCOUNT - The document prepared by the principal agent, which reflects the contract value of the works at final approval or termination.
FRAUDULENT PRACTICE – means a misrepresentation of facts in order to influence a procurement process or the execution of a contract to the detriment of any tenderer and includes collusive practise among tenderers (prior to or after the tender submission) designed to establish tender prices at artificial non-competitive levels and to deprive the tenderer of the benefits of free and open competition.
INTEREST – the interest rates applicable on this contract, whether specifically indicated in the relevant clauses or not, will be in terms of the legislation of the Republic of South Africa, and in particular:
| (a) | in respect of interest owed by the employer, the interest rate as determined by the Minister of Justice and Constitutional Development from time to time, in terms of section 1(2) of the Prescribed Rate of Interest Act, 1975 (Act No. 55 of 1975), will apply; and
| (b) | in respect of interest owed to the employer, the interest rate as determined by the Minister of Finance, from time to time, in terms of section 80(1)(b) of the Public Finance Management Act, 1999 (Act No. 1 of 1999), will apply
| [1.1.1.16] | ENGINEER/PRINCIPAL AGENT – means the person or entity appointed by the Employer and named in the Contract Data as the Engineer /Principal Agent to act as agent of the Employer. In the event of an Engineer/Principal Agent not being appointed, then all the duties and obligations of an Engineer/Principal Agent as detailed in the Contract shall be fulfilled by a representative of the Employer as named in the Contract Data. (Hereafter referred to as Engineer)
| [1.1.1.21] | GENERAL ITEMS - or preliminaries means items stipulated in the Pricing Data relating to general obligations, site services, facilities and/or items that cover elements of the cost of the work which are not considered as proportional to the quantities of the Permanent Works.
| [4.4.1] | Add the following to the clause 4.4.1: "The Contract shall only use subcontractors who are duly registered with the CIDB and who has an ACTIVE status at the time of submitting the tender"
| [6.2.1] | Refer to Offer and Acceptance form for the various options that the contractor may choose from in providing a form of Guarantee under "GUARATEE OPTIONS".
| [6.10.6.2] | Replace "at the prime overdraft rate, as charged by the Contractor's Bank," with "..at the interest rate as determined by the Minister of Justice and Constitutional Development from time to time, in terms of section 1(2) of the Prescribed Rate of Interest Act, 1975 (Act No. 55 of 1975)." Omit ",on all overdue payments from the date on which the same should have been paid..." and replace with " only after 30 calendar days from receiving written notice from the Contractor that the amount is overdue,.."
2013-01-16
SPECIAL CONDITIONS OF CONTRACT
[5.12.3] |  | Omit clause 5.12.3 and add the following:
"5.12.3. If an extension of time is granted, the Contractor shall be paid such additional time-related General Items, including for special non-working days, if applicable as are appropriate regarding to any other compensation which may already have been granted in respect of the circumstances concerned.The reasons for extension of time that would invoke payment of time related General Items are inter alia;
|  | 5.12.3.1 | Failure to give possession of the site to the contractor.
|  | 5.12.3.2 | Making good physical loss and repairing damage to the works where the contractor is not at risk.
|  | 5.12.3.3 | Contract instructions not occasioned by default by the contractor.
|  | 5.12.3.4 | Failure to issue construction information timeously or the late issue of a contract instruction following a request from the contractor.
|  | 5.12.3.5 | Late acceptance by the principal agent of a design undertaken by a selected subcontractor where the contractor’s obligations have been met.
|  | 5.12.3.6 | Suspension or cancellation termination invoked by a nominated or selected n/s subcontractor due to default by the employer or the principal agent.
|  | 5.12.3.7 | Insolvency of a nominated subcontractor.
|  | 5.12.3.8 | A direct contractor.
|  | 5.12.3.9 | Opening up and testing of work and materials and goods where such work is according to in accordance with the contract documents.
|  | 5.12.3.10 | The execution of additional work for which the quantity included in the bills of quantities is not sufficiently accurate.
|  | 5.12.3.11 | Late or failure to supply materials and goods for which the employer is responsible.
|  | 5.12.3.12 | Suspension of the works."
[5.14.5.1] |  | Omit entire clause 5.14.5.1 | [11 empty] | 14.1. The circumstances for which the contractor is entitled to a revision of the date for practical completion and for which revision the principal agent shall adjust the contract value [32.12] in terms of 32.12 are delays to practical completion caused by one or more of the following:
[5.16.4] |  | Add the following new clause "5.16.4. Upon the issue of a Final Approval Certificate, unless otherwise provided in the Contract: 5.16.4.1. The performance Guarantee (if any) shall be returned within 14 days to the guarantor in terms of Clause 7."
[6.2.2] |  | Replace the following "..it shall be deemed that the Contractor has selected a security of ten percent retention of the value of the Works." with "..it shall be deemed that the Contractor has selected a security of a bank or insurance guarantee of 5% of the value of the Works and a payment reduction of 5% of the value certified in the payment certificate excluding value added tax."
[6.2.3] |  | Add to clause 6.2.3 the following "The Contractor shall provide proof of paid-up premium payments to accompany his payment certificate as proof that his performance guarantee has not expired yet. The Contractor will not receive payment without proof of the validity of their performance guarantee.
[9.3.2.2] |  | Omit "without prejudice to the exercise of any lien the Contractor may have acquired over the Employer’s property." | [11 empty] | 14.1.1. Failure to give possession of the site to the contractor [15.2.1] in terms of 15.2.1
Duties and functions of the Engineer requiring the specific approval of the Employer BEFORE execution of any part of these duties are as follows:
| (a) | Determinations of contractors claims for extension of time (revision of the contract completion date). All claims for extension of time shall be submitted by the Engineer, together with the Engineer's recommendations, to the Employer for determination. Omit "Engineer" in clause 42.2 and replace with "Employer". | [10 empty] | 2013-01-16 | 14.1.2. Making good physical loss and repairing damage to the works [8.0] in terms of 8.0 where the contractor is not at risk
| (b) | Drawings, instructions or communications of any kind requiring variations of the works and involving EXTRA's shall NOT be given effect by the Contractor UNTIL BOTH the "Official Variation Order" and the "Financial Request for Variation Order and Additional Funds" form, as issued by the Department of Public Works, have been approved and signed by the Employer. | [11 empty] | 14.1.3. Contract instructions [17.0] not occasioned by default by the contractor
| (c) | Insurance policies to be approved by the Employer within 21 days of the date of the Commencement of the Works.
| (d) | Any notice of disagreement raised by the Contractor or written Dispute Notice given by the Contractor to the Engineer shall be submitted by the Engineer, together with the Engineer's recommendations, to the Employer for determination. | [11 empty] | 14.1.4. Failure to issue construction information timeously [15.6] or the late issue of a contract instruction following a request from the contractor
| (e) | The issue of the certificate of practical completion, certificate of completion and the final approval certificate shall be signed and submitted by the Engineer, to the Employer for final approval and signature. The certificates shall not be considered as officially issued until signed by the Employer. | [11 empty] | 14.1.5. Late acceptance by the principal agent of a design undertaken by a selected subcontractor where the contractor’s obligations [4.3] in terms of 4.3 have been met
| MANAGING PROJECT DURATION | [10 empty] | Kevin McCarthy request 19/11/2014
| (a) | The Contractor shall co-ordinate his programme with all other contractors whose work may precede or be executed simultaneously to his own. The Contractor will be called upon to plan and control the project using the Project Evaluation and Review Technique (PERT) or other approved Critical Path Method (CPM) network analysis of his events and activities and those of the dub-contractors in his employ and must co-ordinate his planning with any other contractor employed on the project. A fortnightly project control report will be expected from the Contractor in writing, evaluating any gains or delays against the critical path and he should allow for all costs involved in planning reviewing and updating the programme to the satisfaction of the Principal Agent against this item. | [11 empty] | 14.1.6. Suspension or cancellation termination invoked by a nominated or selected n/s subcontractor due to default by the employer or the principal agent [38.1] in terms of 38.1
| (b) | Activity-and total float shall belong to the Employer. | [11 empty] | 14.1.7. Insolvency of a nominated subcontractor
| (c) | The Contractor shall deliver his programme of work within 10 calendar days after notice from the Employer, prior to the Commencement Date.
|  | It is a condition of this contact that, the contracter submit to the Engineer/principal agent a detailed CPM Programme which shall be to the approval of the Engineer/principal agent. In this regard tenderers are advised to consult with the Engineer/Principal Agent as to the format and requirements of the programme as no claim whatsoever will entertained should the programme fail to meet the requirements of the Engineer/Principal Agent. Failure to submit the programme within the stipulated time may result in the contractor being held in breach of contract. | [11 empty] | 14.1.8. A direct contractor
The approved programme will form the basis of time management of the project and extension of time will not be guaranteed unless the Contractor has strictly complied with this provision.
|  | The programme shall make allowance for rain and the number of rain days allowed within the critical path shall be on the provisions of the clause dealing with inclement weather and claiming for delays in performance in this bill. | [11 empty] | 14.1.9. Opening up and testing of work and materials and goods [17.1.5–6] in terms of 17.1.5 and 17.1.6 where such work is according to in accordance with the contract documents
Allowance for the above must be made under this item as no claims for failing to comply with this precondition will later be entertained.
| INCLEMENT WEATHER AND CLAIMS FOR DELAYS IN PERFORMANCE | [12 empty] | 14.1.10. The execution of additional work for which the quantity included in the bills of quantities is not sufficiently accurate
| (a) | The Contract Sum includes a monthly allowance of 3 working days inclement weather during which rainfall exceeds 10mm per day for months | [11 empty] | 14.1.11. Late or failure to supply materials and goods for which the employer is responsible
|  | as indicated in the Scope of Works. These days shall be reflected on the critical path of the Contractor’s programme as specified in MANAGING PROJECT DURATION above. | [11 empty] | Suspension of the works [12.5, 31.15]
| (b) | Claims for delays in performance due to inclement weather shall be calculated separately for each calendar month and for the project as a whole. Delays or gains to the critical path shall be reflected in all revisions of the programme. An extension of time will only be granted where the following conditions are met:
|  | (i) | The criteria to be used for WORK stoppages shall be for safety hazards or poor quality of work.
|  | (ii) | The Employer’s site representative or the Employer’s Principal Agent, if the site representative is not available shall be notified when the Contractor stops the work and intends to claim performance delays. The Employer representative shall inspect the situation together with the Contractor and give an immediate decision.
|  |  | 1. | The stoppage claimed must cause a delay in the Completion Date of work. If the critical activities can proceed and a non-critical activity is delayed due to inclement weather no claims for delay shall be granted.
|  |  | 2. | No claims for stoppages less than 2(two) hours per day shall be considered.
|  |  | 3. | Claims granted for more than 2 (two) hours, but less than 10 (ten) hour (lunch included) day, shall be added together and expressed as full days.
|  |  | 4. | All claims shall be submitted in writing to the Principal Agent within one working day of the actual stoppage.
|  |  | 5. | The total delay in performance granted to the Contractor expressed in days shall be added to the contractual Completion Date of each section of the Works. The contractual penalty clause shall only come into effect after this newly arrived date.
|  |  | 6. | Total delays (in hours) will be rounded up or down to the nearest integer for the calculation of Working Days. The total hours (including lunch) per Working Day shall be 10 unless otherwise indicated on the Contractor’s programme.
|  |  | 7. | Where the programmed delays for inclement weather exceed the actual delays incurred the Completion Date(s) will not be adjusted.
|  |  | 8. | Where the project includes builder’s holidays the programmed durations for inclement weather shall be adjusted pro-rate to the actual Working Days.
|  |  | 9. | The total of all monthly delays due to inclement weather shall be calculated in accordance with the example given below:
|  |  | Description |  | Months |  |  |  |  | Total
[5 empty] | Sept | Oct | Nov | Dec | Jan
[5 empty] | Hours | Hours | Hours | Hours | Hours | Hours
|  |  | Programmed | Rain days | 0 | 30 | 30 | 15 | 15 | 90
|  |  | Actual | Rain days | 16 | 22 | 35 | 15 | 18 | 106
|  |  | Difference |  | -16 | 8 | -5 | 0 | -3 | -16
| 8 | hrs/day* | Estimated Extension of time - in working days | [6 empty] | 2
See point 5.2 in the Scope of Works for the specific days the tenderer must allow for in this contract.
Tender no: | ZNTM012345W |  | Part 2: CONTRACT DATA PROVIDED BY THE CONTRACTOR:
POST-TENDER INFORMATION
| Note: | All information for this section requires consultation with the Contractor. The Engineer/Principal Agent shall not pre-select any of the alternatives available to the Contractor.
1 | CONTRACT DETAILS
[1.1.1.9] [1.2.1.2] | Contractor Name:
Postal address:
| Tel no | [5 empty] | Fax no
| Tax / VAT Registration No: | [5 empty] | e-mail address
Physical address:
[1.1.1.10] | The accepted contract price inclusive of tax is R :
[Amount in words]
Payment Of Preliminaries (Clause 6.7, 6.8, 6.10 and 6.11)
| The preliminaries amounts shall be paid in terms of: | [5 empty] | *Alternative A | Yes
[7 empty] | **Alternative B | N/A
* Assessed by the Engineer/Principal Agent as an amount prorated to the value of the Work duly executed in the same ratio as the Preliminaries bears to the Contract Price excluding VAT, Preliminary amount, Contingencies and any CPAP.
** Calculated from the priced Bill of Quantity/Lump Sum document. The Contractor and the Engineer/Principal Agent shall agree on a division of the priced Preliminaries items into: initial establishment charge, monthly charge and final disestablishment charge.
| If the Contractor and the Engineer/Principal Agent can not agree, within 10 Working Days from the Commencement Date, on such a division then the Engineer/Principal Agent shall make a division of the Preliminaries to be incorporated in the valuations for each monthly payment certificate as follows; | [10 empty] | Note: In GCC 2010 "day" means a calendar day. Clause 5.12.3 deals with adjustment to General Items. Any adjustment shall be based on calendar days. Eg. General Items is R100,000. Contractor didn't agree GI with Engineer within 10 working days. The adjustment ratio of 10% Fixed, 15% variable with value and 75% time related applies. Contract period is 50 calendar days. R100,000/50 c/days = R2000/c/day for GI. The time related % is 75% x R2000, i.e. R1,500/c/day for time related GI. The extension is for 8c/days. Means time related cost for the extra days is R1,500 x 8 = R12,000.
10% of the General Items/Preliminaries amount shall not be varied
15% of the General Items/Preliminaries shall only be varied in proportion of the Contract Price to the Contract Sum
75% of the General Items/Preliminaries shall be varied in proportion to the revised Construction Period compared with the initial Construction Period.
Adjustment of Preliminaries (Clause 6.7, 6.8, 6.10 and 6.11)
For the adjustment of Preliminaries both the Contract Sum and the Contract Value (including tax) shall exclude the amount of Preliminaries, all Contingency Sum(s) and any provision for Cost Price Adjustment Provisions:-
Alternative A
- An amount which shall not be varied.
- An amount varied in proportion to the contract value as compared to the Contract Sum.
- An amount varied in proportion to the Construction Period as compared to the initial Construction Period (excluding revisions to the Construction Period to which the Contractor is not entitled) to adjustment of the Contract Value in terms of the agreement.
The Contractor shall provide a breakdown of charges (including tax) within 15 working days of the date of acceptance of tender and, where applicable, an apportionment of Preliminaries per section
If the Contractor and the Principal Agent cannot agree, within ten (10) Working Days from the Commencement Date, on such a division then the Principal Agent shall make a division of the Preliminaries to be incorporated in the valuations for each monthly payment certificate as follows;
0% of the amount shall not be varied
10% of the amount shall not be varied
15% varied in proportion of the Contract Value to the Contract Sum
75% varied in proportion to the revised Construction period compared with the initial Construction Period
Sectional Completion : Subdivision of Preliminaries Costs
For the adjustment of preliminaries for sections of the work the value of fixed, value, and time related amounts of the preliminaries for each section is required. The contractor is to provide such information within fifteen (15) working days of taking possession of the site, failing which the categorised preliminaries amounts shall be prorated to the value of each section.
The above shall apply equally for projects where sectional completion was not contemplated at tender stage but subsequently occurred on an adhoc basis during construction of the works as agreed between the client and the employer. The original priced categorised amounts for fixed, value, and time related amounts shall be prorated to the value of each section.
When an extension of time has been granted in terms of the GCC and the preliminaries require to be adjusted accordingly, the pertinent sectional (subdivided) categorised preliminaries amounts shall be utilised, where applicable and not the overall preliminary amounts.
Where sectional completion is required in terms of the agreement, the Contractor shall provide the Principal Agent with the division of the above categorized amounts into sections. Should the Contractor fail to provide such information within the period stipulated the categorized amounts shall be prorated to the value of each section.
[9 empty] | YES | yes / no
or
Alternative B | The Contractor shall within 15 working days of the date of possession of the site provide the Principal Agent with a detailed breakdown of Preliminaries amounts for the works as a whole, or per section where applicable, including administrative and supervisory staff charges and for the use of construction equipment in terms of the programme.
[9 empty] | NO | yes / no
The contractor is informed that only option 'A' shall apply
2 | DOCUMENTS
Contract documents marked and annexed hereto:
| Priced Bills of Quantities: |  |  |  |  | Yes |  | No
| Lump Sum document: : |  |  |  |  | Yes |  | No
Guarantee Options:
Not applicable
2.2 DESIGN BRIEF
|  | Not applicable | [7 empty] | YES or NO
|  | 2.3 DRAWINGS | [7 empty] | YES or NO
|  | See list of drawings/Annexure's attached to this document. | [7 empty] | YES or NO
|  | 2.4 DESIGN PROCEDURES | [7 empty] | YES or NO
|  | Not applicable | [7 empty] | YES or NO
| Contract drawings: |  |  |  |  | Yes |  | No
Other documents:
| Waiver of the Contractors lien or right of continuing possession is required. | [5 empty] | YES
GUARANTEE OPTIONS
The Tenderer agrees to provide a bank or insurance guarantee in accordance with clause 6.2.3 of the Conditions of the GCC2010 Contract within the period stated in the Contract Data. This guarantee shall be for a sum equal to an amount stated in the Contract Data.
Guarantees submitted must be issued by either an insurance company duly registered in terms of the Insurance Act (Long Term Insurance Act No 52 of 1998 or Short Term Insurance Act No 53 of 1998) or by a bank duly registered in terms of the Banks Act No 94 of 1990, on the pro-forma referred to above. No alterations or amendments of the wording of the pro-forma will be accepted.
(a) the tenderer accepts that in respect of contracts up to R1 million, a payment reduction of 5% of the contact value will be applicable and will be reduced by the Employer in terms of the applicable conditions of contract.
(b) in respect of contracts above R1 million, the Tenderer offers to provide security as indicated below: select one option
(i) cash deposit of 10 % of the Contract Price
(ii) bank or insurance Performance Guarantee of 10 % of the Contract Price
(iii) cash deposit of 5% of the Contract Price and a payment reduction of 5% of the value certified in the payment certificate (excluding VAT)
(iv) bank or insurance guarantee of 5% of the Contract Price and a payment reduction of 5% of the value certified in the payment certificate (excluding VAT)
NOTE: Where the Tenderer has not selected one of the guarantee options above, the default option will be as if the Tenderer has selected a security of a bank or insurance guarantee of 5% of the value of the Works and a payment reduction of 5% of the value certified in the payment certificate excluding value added tax. - See GCC2010 clause 6.2.2 as amended in Contract Data.
3 | SIGNATURES OF THE CONTRACTING PARTIES
Thus done and signed at…………………………………………………………….on …………..of………………………………………………………….20.….
| Name of signatory | [6 empty] | for and behalf of the Employer who by signature hereof warrants authorisation hereto.
| Capacity of signatory | [6 empty] | as Witness.
Thus done and signed at…………………………………………………………….on …………..of………………………………………………………….20.….
| Name of signatory | [6 empty] | for and behalf of the Contractor who by signature hereof warrants authorisation hereto.
| Capacity of signatory | [6 empty] | as Witness.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C1.3_Form of Guarantee-fly
KZN Public Works: 191 Prince Alfred Street
C1.3 - FORM OF GUARANTEE
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C1.3_Performance Guarantee
C1.3 PERFORMANCE GUARANTEE - GCC FOR CONSTRUCTION WORKS (2nd Edition - 2010)
Head: Public Works
KZN Department of Public Works:
Private Bag X 9041
PIETERMARITZBURG
3200
Sir,
ON DEMAND PERFORMANCE GUARANTEE
Tender Number ZNTM012345W |  |  |  | Project Code 012345
For use with the General Conditions of Contract for Construction Works, Second Edition, 2010.
GUARANTOR DETAILS AND DEFINITIONS
"Guarantor" means:
Physical Address:
"Employer" means: |  |  | The Provincial Administration of KwaZulu-Natal in its Department of Public Works
"Contractor" means:
"Engineer" means:
"Works" means: |  |  | KZN Public Works: 191 Prince Alfred Street
"Site" means:
"Contract" means: |  |  | The Agreement made in terms of the Form of Offer and Acceptance and such amendments or additions to the Contract as may be agreed in writing between the parties.
"Contract Sum" means: |  |  | The accepted amount inclusive of tax of:
Amount in Words:
"Guaranteed Sum" means: The maximum aggregate amount of: | [5 empty] | 10%
Of Contract Sum
Amount in Words:
"Expiry Date" means:
CONTRACT DETAILS
Engineer Issues: Interim Payment Certificates, Final Payment Certificates and the Certificate Completion of the Works as defined in the Contract.
PERFORMANCE GUARANTEE
1 | The Guarantor's liability shall be limited to the amount of the Guaranteed Sum.
2 | The Guarantor's period of liability shall be from and including the date of issue of this Performance Guarantee and up to and including the Expiry Date or the date of issue by the Engineer of the Certificate of Completion of the Works or the date of payment in full of the Guaranteed Sum, whichever occurs first. The Engineer and/or the Employer shall advise the Guarantor in writing of the date on which the Certificate of Completion of the Works has been issued.
3 | The Guarantor hereby acknowledges that:
| 3.1 | any reference in this Performance Guarantee to the Contract is made for the purpose of convenience and shall not be construed as any intention whatsoever to create an accessory obligation or any intention whatsoever to create a suretyship;
| 3.2 | its obligation under the Performance Guarantee is restricted to the payment of money.
4 | Subject to the Guarantor's maximum liability referred to in 1, the Guarantor hereby undertakes to pay the Employer the sum certified upon receipt of the documents identified in 4.1 to 4.3:
| 4.1 | A copy of a first written demand issued by the Employer to the Contractor stating that payment of a sum certified by the Engineer in an Interim or Final Payment Certificate has not been made in terms of the Contract and failing such payment within seven (7) calendar days, the Employer intends to call upon the Guarantor to make payment in terms of 4.2;
| 4.2 | A first written demand issued by the Employer to the Guarantor at the Guarantor's physical address with a copy to the Contractor stating that a period of seven (7) days has elapsed since the first written demand in terms of 4.1 and the sum certified has still not been paid;
| 4.3 | A copy of the aforesaid payment certificate which entitles the Employer to receive payment in terms of the Contract of the sum Certified in 4.
5 | Subject to the Guarantor's maximum liability referred to in 1, the Guarantor undertakes to pay to the Employer the Guaranteed Sum or the full outstanding balance upon receipt of a first written demand from the employer to the Guarantor at the Guarantor's physical address calling up this Performance Guarantee, such demand stating that:
| 5.1 | the Contract has been terminated due to the Contractor's default and that this Performance Guarantee is called up in terms of 5; or
| 5.2 | a provisional or final sequestration or liquidation court order has been granted against the Contractor and that the Performance Guarantee is called up in terms of 5; and
| 5.3 | the aforesaid written demand is accompanied by a copy of the notice of termination and/or the provisional/final sequestration and/or the provisional liquidation court order.
6 | It is recorded that the aggregate amount of payments required to be made by the Guarantor in terms of 4 and 5 shall not exceed the Guarantor's maximum liability in terms of 1.
7 | Where the Guarantor has made payments in terms of 5, the Employer shall upon the date of issue of the Final Payment Certificate submit an expense account to the Guarantor showing how all monies received in terms of this Payment Guarantee have been expended and shall refund to the Guarantor any resulting surplus. All monies refunded to the Guarantor in terms of this Performance Guarantee shall bear interest at the prime overdraft rate of the Employer's bank compounded monthly and calculated from the date payment was made by the Guarantor to the Employer until the date of refund.
8 | Payment by the Guarantor in terms of 4 or 5 shall be made with seven (7) calendar days upon receipt of the first written demand to the Guarantor.
9 | Payment by the Guarantor in terms of 5 will only be made against the return of the original Performance Guarantee by the Employer.
10 | The Employer shall have the absolute right to arrange his affairs with the Contractor in any manner which the Employer may deem fit and the Guarantor shall not have the right to claim his release from this Performance Guarantee on account of any conduct alleged to be prejudicial to the Guarantor.
11 | The Guarantor chooses the physical address as stated above for the service of all notices for all purposes in connection herewith.
12 | This Performance Guarantee is neither negotiable nor transferable and shall expire in terms of 2, where after no claims will be considered by the Guarantor. The original of this Guarantee shall be returned to the Guarantor after it has expired.
13 | This Performance Guarantee, with the required demand notices in terms of 4 or 5, shall be regarded as a liquid document for the purposes of obtaining a court order.
14 | Where this Performance Guarantee is issued in the Republic of South Africa the Guarantor hereby consents in terms of Section 45 of the Magistrate's Court Act No 32 of 1944, as amended, to this jurisdiction of the Magistrate's Court of any district having jurisdiction in terms of Section 28 of the said Act, notwithstanding that the amount of the claim may exceed the jurisdiction of the Magistrate's Court.
Signed at
Date
Guarantor's signatory (1)
Capacity
Guarantor's signatory (2)
Capacity
Witness signatory (1)
Witness signatory (2)
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C2_Pricing Data-fly
KZN Public Works: 191 Prince Alfred Street
PART C2 - PRICING DATA
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C2.1 Pricing Instructions
C2.1 PRICING INSTRUCTIONS GCC FOR CONSTRUCTION WORKS (Second Edition 2010)
Project title: |  |  | KZN Public Works: 191 Prince Alfred Street
Tender no: |  |  | ZNTM012345W | Project Code: | 012345
C2.1 Pricing Instructions
Where any item is not relevant to this specific contract, such item is marked N/A (signifying “not applicable”)
The adjustment of the preliminaries each item priced is to be allocated to one or more of the three categories by insertion of “F”, “V”, “T” as the case may be against the price in the “rate” column immediately preceding the “amount” column, where “F” denotes a fixed amount (amount not varied), “V” denotes an amount variable in proportion to value and “T” denotes an amount variable in proportion to time.
1 | MASSES AND MEASURING UNITS
These shall be in accordance with the Measuring Units and National Measuring Standards Act No. 76 of 1973 and amendments thereto. The pages of each of these documents are numbered consecutively and before the Tenderer submits his tender he should check the number of pages, and if any are found missing or duplicated, or the figures or writing indistinct, or the documents contain any obvious error, he should apply to the Head : Public Works AT ONCE and have same rectified as no liability whatsoever will be admitted by the Administration in respect of errors in Tender due to the foregoing.
2 | PRICES FOR VARIATIONS
Where prices or quotations for variations are submitted by the Contractor during the currency of the Contract, it is to be clearly understood that these are for the purpose of consideration by the Head : Public Works and that there is no assumption of acceptance. The Contractor will be notified of acceptance of prices or quotations either by insertion of the amount on the variation order or by written intimation.
3 | SCALE
The scale to which the Drawings are made is only to be made use of when no figured dimensions are given either on the Drawings or in the tender documents and the figured dimensions are always to be followed though they may not coincide with the scale of the Drawings, but dimensions where possible are to be taken from the buildings.
4 | PROVISIONAL ITEMS
All items described as "Provisional" shall be used as directed by the Employer and measured and valued or paid for. No work for which "Provisional" items are allowed shall be commenced without written instructions from the Head : Public Works.
5 | TIMELY ORDERING OF MATERIALS
The Contractor is warned to place all orders for materials or special articles as early as possible, as he will be held solely responsible for any delay in the delivery of such goods. Nevertheless this tender is conditional upon no liability being attached to the Contractor if delivery of materials is rendered impossible by reason of any act of the Government.
6 | ELECTRICAL LIGHTING, POWER AND WATER REQUIREMENTS
The Contractor shall provide any artificial lighting which may be necessary or required for the proper execution of the works, and provide electric power and water required by all Sub-Contractors, Nominated Sub-Contractors and Sub-Contractors appointed directly by the Employer.
The Contractor shall give all notices and pay all fees in connection with temporary electrical and water connections and shall connect temporary Electrical and Water meters for and pay for all current and water consumed.
Tenderers are advised that the permanent light fittings and water points of any kind installed in the Works are not to be used to provide temporary lighting and supplement water requirements for construction purposes.
7 | IMPORT PERMITS, DUTIES AND SURCHARGES.
All tenders by means of which imported products are being called for, must use the rate of exchange 14 days prior to the closing date indicated in the tender documents. If this day falls on a weekend or public holiday, the next working day must be used.
Furthermore, Tenderers must submit documentary proof (in the form of a certified copy) from their bank or legally recognised financial institution, clearly indicating what the rate of exchange was 14 days prior to the closing date, as mentioned above.
Together with this, the Tenderer must confirm that the tender price relating to an imported product, was based on the rate of exchange 14 days prior to the closing date as mentioned above.
8 | STANDARD SYSTEM OF MEASUREMENT WHERE BILLS OF QUANTITIES FORM PART OF THE TENDER DOCUMENTS
The work executed under this Contract has been measured in accordance with the;
Standard System of Measuring Builders Work (7th Edition)
including all amendments unless descriptions of items indicate a deviation and it shall be understood that the system of measurement which is herein adopted is the only system of measurement which will be recognised in connection with this contract. Any contradictions to this system of measurement contained in the “Model Preambles for Trades 2008” shall be disregarded (unless same have been accommodated in the system of measurement) but applicable rates shall be included for all requirements stated and not measured separately in compliance with this system.
9 | PRICING OF ROCK EXCAVATIONS
It is a condition of this tender that should the tenderer elect to price the Rock Excavation included in this tender, the rates must be market related and should be identically priced for the same classification of excavations and not vary for similar billed items in the different sections.
10 | BROAD BASED BLACK ECONOMIC EMPOWERMENT
| 1. | It is the deliberate policy of the Provincial Administration of KwaZulu-Natal to foster and to encourage the economic empowerment of Black South Africans. This policy will be implemented without prescription and without prejudicing the principles and the integrity of the Provincial Administration of KwaZulu-Natal. Subject to these constraints and also subject to good business practise and commercial consideration, it is therefore considered appropriate that the Provincial Administration of KwaZulu-Natal should encourage business relationships with companies which actively pursue Affirmative Action and Black Economic Empowerment Programmes.
| 2. | In responding to this tender you are therefore encouraged to devote attention to these two subjects of Affirmative Action and Economic Empowerment. In addition, in considering the appointment of sub-contractors, you are requested to extend the spirit of these policies.
| 3. | The foregoing enunciations of this policy are not intended to be prescriptive nor to preclude any individual or operation from responding to this tender.
11 | REGISTRATION ON THE CENTRAL SUPPLIERS DATABASE
| 1. | In terms of the Public Finance Management Act (PFMA), 1999 (Act No 1 of 1999) Section 38 (1) (a) (iii) and 51 (1) (iii) and Section 76 (4) of PFMA National Treasury developed a single platform, The Central Supplier Database (CSD) for the registration of prospective suppliers including the varification functionality of key supplier information.
| 2. | Prospective suppliers will be able to self - register on the CSD website: www.csd.gov.za
| 3. | Once the supplier information has been varified with external data sources by National Treasury a unique supplier number and security code will be allocated and communicated to the supplier. Suppliers will be required to keep their data updated regularly and should confirm at least once a year that their data is still current and updated.
| 4. | Suppliers can provide their CSD supplier number and unique security code to organs of state to view their varified CSD information.
| 5 | Tenderers are required to fill in clearly, legibly, in bold print and black ink their CSD supplier number in the space hereunder:
Name of Supplier
Central Supplier Database (CSD) Supplier Number:
12 | TAX CLEARANCE REQUIREMENTS
It is a condition of tender that the taxes of the successful tenderer must be in order, or that satisfactory arrangements have been made with South African Revenue Service (SARS) to meet the Tenderder’s tax obligations. It is a condition of this Offer of Commission that your practice remains in good standing with SARS (South African Revenue Services) in terms of its tax clearance, during the project, which is required to process your payment certificates.
| 1 | In order to meet this requirement tenderers are required to apply via e-filing at any SARS branch office nationally. The Tax Complance Status (TCS) requirements are also applicable to foreign Tenderders / individuals who wish to submit Tenders.
| 2 | SARS will then furnish the Tenderder with a Tax Compliance Status (TCS) PIN that will be valid for a period of 1 (one) year from the date of approval.
| 3 | In tenders where Consortia / Joint Ventures / Sub-contractors are involved, each party must submit a separate Tax Compliance Status (TCS) PIN.
| 4 |  | Application for Tax Compliance Status (TCS) PIN can be done via e-filing at any SARS branch office nationally or on the website www.sars.gov.za.
| 5 |  | Tax Clearance Certificates may be printed via eFiling. In order to use this provision, taxpayers will need to register with SARS as eFilers through the website www.sars.gov.za.
| 6 |  | Tax Clearance Certificates may be printed via eFiling. In order to use this provision, taxpayers will need to register with SARS as eFilers through the website www.sars.gov.za.
Security PIN Number
Company / Entity Tax Reference Number
13 | DEVELOPMENT OF SKILLS THROUGH INFRASTRUCTURE CONTRACTS
The contractor shall achieve in the execution of this contract the Contract Participation Goals (CPG) relating to the engagement of targeted enterprises as established in the CIDB Standard for Indirect Targeting for Enterprise Development through Construction works Contracts Published in Government Gazette No 48491)
14 | BILLS OF QUANTITIES/LUMP SUM DOCUMENT
| The Bills of Quantities document forms part of and must be read and priced in conjunction with all the other documents forming part of the contract documents, the Standard Conditions of Tender, Conditions of Contract, Standard Preambles to all Trades, Specifications, Drawings and all other relevant documentation. |  |  |  |  | The latest Standard for Uniformity in Construction Procurement published in terms of the Construction Industry Development Board (CIDB) Act, 2000 (Act no. 38 of 2000), the Standardized Construction Procurement Documents for Engineering and Construction Works as issued by the CIDB and any other relevant documentation pertaining thereto must be studied and all principles in this regard must be applied to all procurement documentation, practices and procedures.
The consultant(s)/project manager must acquaint themselves fully with all relevant matters pertaining to this section in order to enable prospective Tenderders to price for all eventualities.
15 | VALUE ADDED TAX
| The tender price must include for Value Added Tax (VAT). All rates, provisional sums, etc. in the Bills of Quantities must however be net (exclusive of VAT) with VAT calculated and added to the Total Value thereof in the Final Summary. |  |  |  |  | The following items must be Included in this Pricing Instruction. Any additional items deemed necessary must be included herein
16 | FIXED PRICE CONTRACT
Should the Bills of Quantities/Lump Sum Document be a fixed price contract, the following clause must be inserted in the Pricing Instructions: Tenderders are to take note that the contract price adjustments are not applicable to this contract. Tenderders should therefore make provision in the Contract Sum, schedule of rates, etc. for possible price increases during the contract period, as no claims in this regard shall be entertained.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C2.2_Prelim Fly
KZN Public Works: 191 Prince Alfred Street
C2.2 - Preliminaries for GCC for Construction works - 2nd Edition 2010
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C2.2_Notes to QS Prelims & Gen
KZN Public Works: 191 Prince Alfred Street
BILL NO. 1
C2 .2 PRELIMINARY AND GENERAL
| NOTES | UNIT | QUANTITY | RATE | AMOUNT
i) | The agreement is to be the General Conditions of Contract for Works of Civil Engineering Construction (2010) (Second Edition) , published by the S. A. Institution Of Civil Engineering.
ii) | The Preliminaries are to be the Construction and management requirements for works contracts - Part 1: General engineering and construction works (SANS 1921-1: 2004 Edition 1) prepared by Standards South Africa and shall be deemed to be incorporated herein.
iii) | Tenderers are referred to the abovementioned documents for the full intent and meaning of each clause thereof (hereinafter referred to by heading and clause number only) for which such allowance must be made as may be considered necessary.
iv) | Where standard clauses or alternatives are not entirely applicable to this contract such modifications, corrections or supplements as will apply are given under each relevant clause heading.
v) | Where any item is not relevant to this specific contract such item is marked N/A (signifying "not applicable").
vi) | Adjustment of the preliminaries: each item priced, is to be allocated to one or more of the three categories, where "F" denotes a fixed amount (amount not to be varied), "V" denotes an amount variable in proportion to value and "T" denotes an amount in proportion to time.
vii) | Time (T) related Preliminaries will only be adjusted for omissions or additions, issued by the Employer, or delays caused by the Employer, for which variation and extension of time has been granted. See Contract Data.
SECTION A: GENERAL CONDITIONS OF CONTRACT
A1 | General (clause 1)
| F:............................. V:............................ T:............................ | Item
A2 | Basis of Contract (clause 2)
| F:............................. V:............................ T:............................ | Item
A3 | Engineer (clause 3)
| F:............................. V:............................ T:............................ | Item
A4 | Contractor's General Obligation (clause 4)
| F:............................. V:............................ T:............................ | Item
A5 | Time and Related Matters (clause 5) - As referred to in the Contract Data under Special Condition of Contract. The Contract Period shall be deemed to include all Non – Working Days, Special Non – Working Days and the year-end Builders Annual Industry Holiday Periods.
| F:............................. V:............................ T:............................ | Item
| Carried forward to collection |  |  | R
|  | UNIT | QUANTITY | RATE | AMOUNT
A6 | Payment and Related Matters (clause 6)
| F:............................. V:............................ T:............................ | Item
A7 | Quality and Related Matters (clause 7)
| F:............................. V:............................ T:............................ | Item
A8 | Risk and Related Matters (clause 8)
| F:............................. V:............................ T:............................ | Item
A9 | Termination of Contract (clause 9)
| F:............................. V:............................ T:............................ | Item
A10 | Claims and Disputes (clause 10)
| F:............................. V:............................ T:............................ | Item
SECTION B: SANS 1921-1:2004 (Edition 1): CONSTRUCTION AND MANAGEMENT REQUIREMENTS FOR WORKS CONTRACTS: PART 1
Refer to the SCOPE OF WORK for detail requirements:
B1 | Scope
| F:............................. V:............................ T:............................ | Item
B2 | Normative references
| F:............................. V:............................ T:............................ | Item
B3 | Definitions
| F:............................. V:............................ T:............................ | Item
B4 | Requirements for construction and management
| F:............................. V:............................ T:............................ | Item
B4.1 | General
| F:............................. V:............................ T:............................ | Item
B4.2 | Responsibilities for design and construction
| F:............................. V:............................ T:............................ | Item
B4.3 | Planning, programme and method statements
| F:............................. V:............................ T:............................ | Item
| Carried forward to collection |  |  | R
|  | UNIT | QUANTITY | RATE | AMOUNT
B4.4 | Quality assurance
| F:............................. V:............................ T:............................ | Item
B4.5 | Setting out
| F:............................. V:............................ T:............................ | Item
B4.6 | Management and disposal of water
| F:............................. V:............................ T:............................ | Item
B4.7 | Blasting
| F:............................. V:............................ T:............................ | Item
B4.8 | Works adjacent to services and structures
| F:............................. V:............................ T:............................ | Item
B4.9 | Management of the Works and site
| F:............................. V:............................ T:............................ | Item
B4.10 | Earthworks
| F:............................. V:............................ T:............................ | Item
B4.11 | Testing
| F:............................. V:............................ T:............................ | Item
B4.12 | Materials, samples and fabrication drawings
| F:............................. V:............................ T:............................ | Item
B4.13 | Equipment
| F:............................. V:............................ T:............................ | Item
B4.14 | Site establishment
| F:............................. V:............................ T:............................ | Item
B4.15 | Survey control
| F:............................. V:............................ T:............................ | Item
B4.16 | Temporary works
| F:............................. V:............................ T:............................ | Item
| Carried forward to collection |  |  | R
|  | UNIT | QUANTITY | RATE | AMOUNT
B4.17 | Existing services
| F:............................. V:............................ T:............................ | Item
B4.18 | Health and safety
| F:............................. V:............................ T:............................ | Item
B4.19 | Environmental requirements
| F:............................. V:............................ T:............................ | Item
B4.20 | Alterations, additions, extensions and modifications to existing works
| F:............................. V:............................ T:............................ | Item
B4.21 | Inspection of adjoining structures, services, buildings and property
| F:............................. V:............................ T:............................ | Item
B4.22 | Attendance on nominated and selected subcontractors
| F:............................. V:............................ T:............................ | Item
SECTION C: SCOPE OF WORK in accordance with SANS 10403
(The reference to Clauses refer to Table B.1 of SANS 1921-1:2004)
C1 | Certification by recognised bodies - CLAUSE 4.4
| F:............................. V:............................ T:............................ | Item
C2 | Agrément certificates - CLAUSE 4.5
| F:............................. V:............................ T:............................ | N/A
C3 | Other services and facilities - CLAUSE 4.8
| F:............................. V:............................ T:............................ | Item
C4 | Recording of weather - CLAUSE 5.2
| F:............................. V:............................ T:............................ | Item
C5 | Management meetings - CLAUSE 5.3
| F:............................. V:............................ T:............................ | Item
C6 | Daily records CLAUSE 5.6
| F:............................. V:............................ T:............................ | Item
C7 | Bond and guarantees - CLAUSE 5.7
| F:............................. V:............................ T:............................ | Item
| Carried forward to collection |  |  | R
|  | UNIT | QUANTITY | RATE | AMOUNT
C8 | Permits - CLAUSE 5.9
| F:............................. V:............................ T:............................ | Item
C9 | Proof of compliance with the law - CLAUSE 5.10
| F:............................. V:............................ T:............................ | Item
SECTION D: SPECIFICATION DATA ASSOCIATED WITH SANS 1921-1:2004 (Table A.1)
D1 | Requirements for drawings, information and calculations for which the contractor is responsible CLAUSE 4.1.7
| F:............................. V:............................ T:............................ | Item
D2 | The responsibility strategy assigned to the contractor for the works CLAUSE 4.2.1
| F:............................. V:............................ T:............................ | Item
D3 | The planning, programme and method statements - CLAUSE 4.3
| F:............................. V:............................ T:............................ | Item
D4 | Samples of materials, workmanship and finishes - CLAUSE 4.12.1
| F:............................. V:............................ T:............................ | Item
D5 | Fabrication drawings that the contractor is to provide and deliver to the employer - CLAUSE 4.12.2
| F:............................. V:............................ T:............................ | Item
D6 | Office for the foreman CLAUSE 4.14.3
| F:............................. V:............................ T:............................ | Item
D7 | Telephone - CLAUSE 4.14.3
| F:............................. V:............................ T:............................ | Item
D8 | Office for inspector of works - CLAUSE 4.14.3
| F:............................. V:............................ T:............................ | Item
D9 | Telephone in office for inspector of works - CLAUSE 4.14.3
| F:............................. V:............................ T:............................ | Item
D10 | Sheds - CLAUSE 4.14.3
| F:............................. V:............................ T:............................ | Item
| Carried forward to collection |  |  | R
|  | UNIT | QUANTITY | RATE | AMOUNT
D11 | Provision and erection of signboards - CLAUSE 4.14.6
| F:............................. V:............................ T:............................ | Item
D12 | Termination, diversion or maintenance of existing services - CLAUSE4.17.1
| F:............................. V:............................ T:............................ | Item
D13 | Services which are known to exist - CLAUSE 4.17.3
| F:............................. V:............................ T:............................ | Item
D14 | Detection apparatus - CLAUSE 4.17.4
| F:............................. V:............................ T:............................ | Item
D15 | Additional health and safety requirements - CLAUSE 4.18
| F:............................. V:............................ T:............................ | Item
SECTION E: SPECIFIC PRELIMINARIES
Section E contains Specific Preliminary items which apply to this contract except where "N/A" (Not Applicable) appears against the item.
E1 | PROPRIETARY BRANDED PRODUCTS
The contractor shall take delivery of, handle, store, use apply and/or fix all proprietary branded products in strict accordance with the manufacturers' instruction after consultation with the manufacturer's authorised representative.
| F:............................. V:............................ T:............................ | Item
E2 | OVERTIME
Should overtime be required to be worked for any reason whatsoever, the costs of such overtime are to be borne by the Contractor unless the Engineer/Principal Agent has specifically authorised in writing, prior to the execution thereof, that costs for such overtime are to be borne by the Employer.
| F:............................. V:............................ T:............................ | Item
E3 | AS BUILT DRAWINGS
The position of construction breaks and the extent of individual concrete pours are to be recorded by the Contractor on the Structural Engineer's drawings and are to be submitted to the Engineer/Principal Agent and the Structural Engineer for their records.
| F:............................. V:............................ T:............................ | Item
| Carried forward to collection |  |  | R
SECTION E: SPECIFIC PRELIMINARIES
|  | UNIT | QUANTITY | RATE | AMOUNT
E4 | SITE INSTRUCTIONS
Site Instructions issued on site are to be recorded in triplicate in a Site Instruction book which is to be maintained on site by the Contractor.
| F:............................. V:............................ T:............................ | Item
E5 | LABOUR RECORD
At the end of each week the Contractor shall provide the Engineer/Principal Agent with a written record, in schedule form, reflecting the number and description of tradesmen and labourers employed by him and all sub-contractors on the works each day.
| F:............................. V:............................ T:............................ | Item
Note: In the event that the contractor fails to satisfy the requirements of this specification, the Employer (Head: Public Works) may apply any of the sanctions provided in the contract. Sanctions may include the application of a financial penalty of .04% of the Contract Sum per calendar day of which the required report has not been submitted.
E6 | PLANT RECORD
At the end of each week the Contractor shall provide the Engineer/Principal Agent with a written record, in schedule form, reflecting the number, type and capacity of all plant, excluding hand tools, currently used on the works.
| F:............................. V:............................ T:............................ | Item
E7 | NON CESSION OF MONIES
The Contractor shall not cede nor assign his rights or claims to any monies due or to become due under this contract.
| F:............................. V:............................ T:............................ | Item
E8 | SECTIONAL COMPLETION
When it is required that the contract be executed in sections or portions, the tenderer shall allow for all costs in this regard as no claim for additional costs will be entertained.
| F:............................. V:............................ T:............................ | Item
E9 | LOCAL LABOUR
It is a general requirement of this contract that persons normally resident in the locality of the works (Local Labour) be given preference for employment on the contract. Provided, however, that should adequate and appropriate Labour not be available within the locality, others may be employed subject to satisfactory proof being provided that every reasonable endeavour has been made to employ Local Labour. The Contractor shall identify the local community leaders with the purpose of negotiating with them regarding the utilization of Local Labour in the construction process. In this regard, the Contractor shall furthermore give preference, wherever possible to the employment of single heads of households, women and youth. The Contractor shall, in general, maximize the involvement of the local community.
| F:............................. V:............................ T:............................ | Item
| Carried forward to collection |  |  | R
|  | UNIT | QUANTITY | RATE | AMOUNT
E10 | IMPORT PERMITS AND DUTIES
The responsibility for obtaining the necessary import permits shall rest with the successful Tenderer. No foreign exchange will be arranged or provided by the Administration.
Tenderers are to allow in their tenders and pay the ordinary levy imposed on imported items in terms of item 196.10 of Part 8 of Schedule No. 1 of the Customs and Excise Act, 1964 with effect from 1 October 1989.
| F:............................. V:............................ T:............................ | Item
E11 | CONTRACT PRICE ADJUSTMENT PROVISIONS (CPAP)
| Notwithstanding anything to the contrary contained in the GCC for Construction Works 2010 2nd Edition, this Contract shall only when the Construction Period exceeds 6 months and the Contract sum exceeds R1,000,000,00 be subject to the Contract Price Adjustment Provisions Indices Application Manual for use with P0151 indices (CPAP) (Revised 1 January 2013) as published by Statistics South Africa. Tenderers are advised that with reference to Clause 3.4.6 of the Contract Price Adjustment Provisions (CPAP) Indices Applications Manual, the Head: Public Works will not accept the submission by Tenderers of lists of additional items. |  |  |  |  | Contract Price Adjustment Provisions (CPAP) Indices Application Manual for use with P0151 indices (Revised 1 January 2013)" as published by Statistics South Africa. The Contract Price Adjustment Provision (CPAP) will be subject to the most recently released indices by Statistic South Africa. Tenderders are advised that with reference to Clause 3.4.6 of the Contract Price Adjustment Provisions (CPAP) Indices Applications Manual, the Head: Public Works will not accept the submission by Tenderders of lists of additional items."
Where this contract is a Lump Sum contract, the contract will be subject to Contract Price Adjustment Provisions (CPAP) only where the contract period equals or exceeds 6 calendar months. The applicable work group shall be WG 180 for domestic buildings or WG 181 for commercial and industrial buildings.
| F:............................. V:............................ T:............................ | Item
E12 | EPWP CONDITIONS AND SPECIFICATIONS
12.1 EMPLOYMENT TARGETS
E12.1 a Employment Targets
The contractor needs to provide a realistic estimate on the number of jobs that the project has the potential to create throughout the project duration as the project will be implemented using labour intensive construction methods on elements where it is economical and feasible for this construction method.
No of jobs to be created = ………. [Contractor to fill in an estimated number]
| F:............................. V:............................ T:............................ | Item
E12.1 b Employment requirements
Tenderers are advised that this contract will be subject to the Expanded Public Works Program (EPWP) aimed at alleviating and reducing unemployment.
Tenderers must allow for any costs for the employement of unskilled labour as per the requirements of the EPWP program;
1. 55% of unskilled labour to be women
2. 55% of unskilled labour to be youth aged between 18 and 35 years
3. 2% of unskilled labour to be people living with disability
4. 100% Unskilled labour utilised must reside within the boundries of the Municipality Ward where this contract is executed, with preference to the local community closest or at the walking distance to the contract site. Wherever possible local skilled tradesmen are to be employed on this contract with the view to maximize utilization of local resources.
| F:............................. V:............................ T:............................ | Item
| Carried forward to collection |  |  | R
|  | UNIT | QUANTITY | RATE | AMOUNT
E12.1 c Labour rate and payment intervals
The contractor should ensure that labour rate paid to unskilled local labour is commensurate to the daily task. When determining the rate, consideration should be given to that EPWP beneficiaries are mostly bread winners in their families, as the program intends alleviating poverty. There should also be consideration that the labour rate promotes creation of expanded number of jobs created and person days of work.
Contractors should make endeavours to ensure that labourers, particularly unskilled are remunerated on fortnight basis and prior notification be made should there be a shortfall on their wages.
The labour rate for local unskilled shall also be determined in consideration of the location of the project, i.e. for projects implemented in urbanized municipalities will not be the same as that for rural municipalities.
| F:............................. V:............................ T:............................ | Item
12.2 LABOUR INTENSIVE CONSTRUCTION METHOD
E12.2 a Labour Intensive Construction (LIC) method
On site there must a person(s) having competency in managing and implementing LIC methods.
*Foreman @ NQF Level 4 the Unit Standard on Implementing LIC methods on site.
*Site Agent/ Managers @ NQF level 5 the Unit Standard on Manage Labour-Intensive Skills Programme both must be CETA accredited
| F:............................. V:............................ T:............................ | Item
E12.2 b Labour Intensive Construction Method
Those parts of the contract to be constructed using Labour Intensive methods will be marked in the BoQ with letter LI (indicating Labour Intensive) against every item so designated. Such works will only be constructed using method so indicated.
Reference to be made to Guidelines for the implementation of Labour Intensive Infrastructure projects under EPWP. "Scope of Work in Respect of Work Relating to the Expanded Public Works Programme (EPWP)"
| F:............................. V:............................ T:............................ | Item
E12.3 RECORD KEEPING
12.3.1 Every employer must keep in the project site office the following minutes of site progress minutes; contractors’ monthly site progress reports; accurately recorded attendance register; proof of payment as means to verify authenticity of data in the EPWP Beneficiary form submitted with payment certificates. Copies of submitted EPWP beneficiary data forms should also be kept in the site office.
| F:............................. V:............................ T:............................ | Item
12.3.2 The employer must keep this record for a period of at least three (3) years after the completion of the project in his/her office as the project site office would have been relocated.
This should be safely kept for job creation data verifications and periodical audits on projects conducted by National and Provincial Department of Public Works after one (1) or two (2) quarters of submitting captured EPWP Data to the National EPWP coordinating Department.
| F:............................. V:............................ T:............................ | Item
| Carried forward to collection |  |  | R
|  | UNIT | QUANTITY | RATE | AMOUNT
E12.4 EPWP REPORTING as per EPWP DATA FORM
At the end of each month as part of site progress report and to be attached to every contractors’ progress payment certificate; the contractor shall provide the principal agent & Public Works with a written records, as per EPWP data form; which will be reflecting, beneficiaries full name & surname; ID No and job description of labour employed by main contractor and sub-contractors on site. At the end of each month the contractor must submit the following documents to be attached to the Progress payment certificate: 1. EPWP monthly data collection form 2. Worker monthly payment upload 3. Worker monthly proof of payment i.e 3.1 Acknowledgement of receipt of payment or 3.2 Payslips 3.3 Bank statement highlighted the workers paid 4. Worker monthly training form 5. Monthly attendance register 6. Certified copies of ID’s (once off) 7. ID size photos (once off) 8. Proof of UIF 9. Proof of COIDA
| F:............................. V:............................ T:............................ | Item
E12.5 EPWP PROMOTION
12.5.1 EPWP signage board
EPWP Program at the project level shall always be promoted through have the projects signage board that embrace EPWP logo at the bottom, correct measurement for this signage board will be provided by the project leader during the site handing over meeting. the standard "HELVETIVA MEDUIM " letters are to be used . Professional title to be 10 mm above line . Line thickness to be 8 mm thick . Space between bottom of the line and bottom of the lettering below the line has to be 100 mm. Letter sizes are as follows : Helvetica meduim 100 mm black upper case to be for project name and owner . Helvetica meduim 75mm black upper case only to be used for professional titles.Project name and owner shall be black lettering on white background.board sizes are as follows : Board to be minomum 2000mm from ground level and to be constructed from reinforced formed chromadek panels minimum 0,6mm thick chromadek. The contractor is responsible for ensuring that the project board remains neatly and safely erected for the full duration including maintenance period,after which the project board and post are to be dismantled and handed to the client in good order.
| F:............................. V:............................ T:............................ | Item
12.5.2 Branding of labour apparel
Contractor & Sub-contractors’ labourers shall be provided with EPWP branded Personal Protective Equipment (PPE), reflector vest with EPWP wording at the back is an ideal and cost effective means of promoting program on site.
The contractor is then advised to price for both item 17.5.1 and 17.5.2
| F:............................. V:............................ T:............................ | Item
E12.6 COMMUNITY LIAISON OFFICER (CLO)
UTILISATION OF A COMMUNITY LIAISON OFFICER
In addition to the requirements of Clause E9, contained in this document;
The Contractor shall allow for and pay any and all costs necessary for the engagement of the services of a Community Liaison Officer (CLO) for the full duration of this contract
In the interest of providing a sound service to both the community and the Contractor, a CLO may only manage one project at a given time.
A CLO will be identified by the local structures of the ward areas and appointed following fair and transparent interviewing process, to be conducted in the presence of local structures and the contractor representative, in order to assist the Contractor in the procurement of any local labour, etc. required for this project. The Contractor is to liaise with the CLO and afford him any assistance needed in ensuring sound working relations with the local community.
Key Responsibilities of the CLO are envisaged to include and not necessary be limited to:
1. Assisting local leadership in conducting skills and resources audit which facilitates sourcing labour from within the ward or targeted areas for employment, as required by contractor.
2. Assisting in sourcing labour-only domestic sub-contractors and the procurement of materials from local resources, as required by the contractor.
3. Assisting the contractor by identifying areas of potential conflict and or threats to the project or to stakeholders in the project and recommend appropriate action to the contractor.
4. Assisting contractor and stakeholders in the project in the resolution of any conflict which may arise.
5. Establishing and ensuring that sufficient and open communication channels between the contractor and the work force are maintained.
6. Establish and ensuring that efficient and open communication channels between the contractor and the community are maintained
7. Identifying and reporting to the Contractor regarding issues where communication between stakeholder is necessary, recommend courses of action and facilitate such communications
| Carried forward to collection |  |  | R
|  | UNIT | QUANTITY | RATE | AMOUNT
8. Assisting the Contractor and the work force in the establishment of grievance procedures and necessary recommenda-tion to the Contractor regarding the grievances and solution thereto.
9. Attending to site meetings and project implementation meetings as required by the Contractor and prepare periodic reports as may be required by the Contractor from time to time.
10. Attending to such other duties which are consistent with the functions of a CLO, as may be required by the Contractor from time to time.
Tenderers are to price twice the rate of unskilled local labour rate against this item for any and all costs arising out of compliance with the foregoing and in the event of a Tenderer failing to price against this item or making inadequate financial provision against this item for compliance as aforesaid, then no claim for costs or additional cost incurred will be entertained by the Head: Works
| F:............................. V:............................ T:............................ | Item
E12.7 SKILLS DEVELOPMENT ON SITE
Contractor in conforming to the object of EPWP that its beneficiaries need to be capacitated with skills that will render them employable in the future. It is then the responsibility of the Contractor that mandatory life skills are provided to 100% of workforce on site and on the job training to labourers from whom the potential for further development has been identified. The latter is not mandatory to all as it covers technical skills.
Contractor should also make provision for the possibility that there might be local youth that will need to be placed on the project with an intention to be provided support towards improving their level of competency and productivity.
Contractor shall also provide all necessary on-the-job training to targeted labour to enable such labour to master and advance on techniques required to undertake the work in accordance with requirements of the contract in a manner that does not compromise workers health and safety.
| F:............................. V:............................ T:............................ | Item
E12.8 LABOUR ONLY Sub Contracting for local emerging enterprises
Tenderer’s are advised that this contract is subject to the Expanded Public Works Programme (EPWP) and the following criteria will apply:
African Equity Ownership
a) The Tenderer is to allow for 5% of the total value of works to be undertaken by a Priority Population Group. This percentage excludes the costs of employing local unskilled labour. The allocation of this percentage from the Project, the screening of people, the selection of skills, will be for the Contractor to adjudicate.
b) The Priority Population Group consists of women, youth and disabled people.
c) The Contractor is to give first option for prospective PPG’s from the surrounding areas of the Project. Should there be insufficient suitable people fitting the criteria of PPG’s, the Contractor may hire people from further afield. This is to be done only after consultation with the Department of Works EPWP Co-ordinator and the Community Liaison Officer (CLO).
d) A Mentor is to be employed by the Contractor, in consultation with the Department of Works for the purposes of quality control and liaison between the Contractor and the selected PPG’s on site. The mentor will be responsible for ensuring an acceptable level of quality workmanship and that such work carried out by the PPG's is executed within the time frames stipulated.
In so far as possible, the Contractor is encouraged to expand the PPG’s skills, knowledge and performance levels.
| F:............................. V:............................ T:............................ | Item
| Carried forward to collection |  |  | R
|  | UNIT | QUANTITY | RATE | AMOUNT
TENDERER’S TO NOTE CONDITIONS
a) The contract to be entered into between the Contractor and the PPG’s will be a LABOUR ONLY sub-contract.
b) The Contractor will be responsible for ensuring that all materials for use by the PPG’s in the works are to be on site timeously. The Contractor shall liaise with The Mentor and PPG to determine the nature and extent of materials required and the lead time necessary.
c) The Contractor shall be responsible for the overall programming of the Works and he is to allow for monitoring the PPG’s programme and progress.
d) In conjunction with the Mentor, he is to allow for the supervision and mentoring (where necessary) of the PPG to ensure quality and adherence to standard building practice
e) The Contractor is to allow for extra storage facilities on site for the PPG’s tools and equipment.
f) Basic tools shall be provided by the PPG’s and where these are not available; the Contractor will supply him with the necessary tools and equipment and deduct the costs thereof from the interim claims made by the PPG.
g) Work requiring specialized tools will be provided free of chargeby the Contractor with the provision that these be returned upon completion of the Work.
CO-ORDINATION
The Contractor is to co-ordinate the work of all the PPG’s, Sub-Contractors and Nominated Sub- Contractors appointed direct by the Employer in such a manner and at all times as will suit the building programme and he is to allow adequate access, for the PPG’s, where required, to carry out their work in an efficient manner as no claims for extras in this connection will be entertained.
| F:............................. V:............................ T:............................ | Item
ATTENDANCE
The Contractor may allow for attendance upon the PPG’s concerned to execute the work. The Contractor is to allow the PPG’s the use of any scaffolding belonging to him while it remains so erected on the site.
Where scaffolding is necessary for the use by any PPG and the Contractor has not erected any for his own use or has removed same after his own use, the Contractor shall supply sufficient scaffolding to the PPG to be erected and dismantled by the PPG and returned to the Contractor.
This attendance upon PPG’s to execute the work is to include for the scaffolding provisions as aforesaid and, in addition, is to include for co-operating to the fullest extent with all the parties, attending on off-loading materials, providing suitable storage for tools and materials used by the PPG’s, use of general facilities such as latrines, etc., supply and cost of power, lighting, water and the like.
| F:............................. V:............................ T:............................ | Item
E12.9 EPWP CONTRACT FOR LABOUR
It is compulsory that shortly after the contractor and or sub contractor has appointed local labour, the employment contract should be signed by both parties, prior to commencement with works on site. The employment contract forms part of the Ministerial Determination or from the regional EPWP officials. Each contract will lapse at the end of each financial year therefore requiring the Contractor to do a renewal of each contract should the need of employment still exist for that particular labourer.
F:............................. V:............................ T:.....................................
| Carried forward to collection |  |  | R
|  | UNIT | QUANTITY | RATE | AMOUNT
E12.10 EPWP SCOPE of WORK
Note:
Contractors are to price any item on the Bill of Quantities having below, bearing in mind that they are regarded as main sources of job creation, whether sub contracted or undertaken by the main contractor.
Elements on the scope of work where application of Labour Intensive Construction methods as will indicated with letters (LI) are regarded feasible are as follows;
i) Excavating trenches for foundations and any other civil works with the depth not more than 1.5 m
ii) All masonry works which include concrete mixing on site; brickwork; plastering; screed works; jointing; etc.
iii) Painting, Plumbing, Ironmongery; roof cladding; glazing; tilling; carpentry; flooring; waterproofing; etc.
| F:............................. V:............................ T:............................ | Item
Note:
It is a general requirement of this contract that persons normally resident in the ward of the works (local labour) be given preference for employment on the contract. Provided, however, that should adequate and appropriate labour not be available within the ward, others may be employed subject to satisfactory proof being provided that every reasonable endeavour has been made to employ local labour (Local Sub-contractor(s); Skilled; Semi-Skilled and Unskilled). The contractor shall in consultation with the local community leaders with the purpose of negotiating with them regarding the utilization of local resources in the construction process. In this regard, the contractor shall furthermore give preference, wherever possible to the employment of single heads of households, women and youth as well as families declared as most indigent by War on Poverty/ Sukuma Sakhe program profiling process. The contractor should aim, in general, to maximise the involvement of the local community, however workers from other communities should not exceed 20% of all persons working on the project, where local employees possess skills at level of competency that meet contractors requirements.
Payment for the labour-intensive component of the works
Payment for works identified in the Scope of Work as being labour-intensive shall only be made in accordance with the provisions of the Contract if the works are constructed strictly in accordance with the provisions of the Scope of Work. Any non-payment for such works shall not relieve the Contractor in any way from his obligations either in contract or in delict.
Linkage of payment for labour-intensive component of works to submission of project data
The Contractor’s payment invoices shall be accompanied by labour information for the corresponding period in a format specified by the employer. If the contractor chooses to delay submitting payment invoices, labour returns shall still be submitted as per frequency and timeframe stipulated by the Employer. The contractor’s invoices shall not be paid until all pending labour information has been submitted.
Applicable labour laws
The current Ministerial Determination (also downloadable at www.epwp.gov.za) Expanded Public Works Programmes, issued in terms of the Basic Conditions of Employment Act of 1997 by the Minister of Labour in Government Notice , shall apply to works described in the scope of work as being labour-intensive and which are undertaken by unskilled or semi-skilled workers.
| F:............................. V:............................ T:............................ | Item
| Carried forward to collection |  |  | R
|  | UNIT | QUANTITY | RATE | AMOUNT
E13 | HIV/AIDS AWARENESS
Tenderers are to price against the following items for compliance with the SPECIFICATION FOR HIV/AIDS AWARENESS bound into this document (The clauses referred to are those of the Specification for HIV/AIDS)
E13.1 | Provide and maintain a condom dispenser in terms of Clause 5.1a)
| F:............................. V:............................ T:............................ | Item
E13.2 | Provide and maintain HIV/AIDS awareness posters terms of Clause 5.1b)
| F:............................. V:............................ T:............................ | Item
E13.3 | HIV /Aids Awareness Programme on Site for not less than 90% of workers inclusive of all direct and indirect costs;
Engage a qualified service provider as described in the scope of works to conduct an HIV Awareness Programme in terms of Clause 5.2.1a)
| F:............................. V:............................ T:............................ | Item
E13.4 | Arrange for workers to attend the HIV Awareness Programme in terms of Clause 5.2.1b)
| F:............................. V:............................ T:............................ | Item
E13.5 | Reporting
Prepare and attach to claims for payment a brief report in terms of Clause 5.3 (see also HIV/STI Compliance Report included with this document).
| F:............................. V:............................ T:............................ | Item
Note: In the event that the contractor fails to satisfy the requirements of this specification, the employer (Head: Public Works) may apply any of the sanctions provided for in the contract. Sanctions may include the application of a financial penalty of .04% of the Contract Sum per calendar day of which the required reports has not been submitted.
E14 | OCCUPATIONAL HEALTH AND SAFETY ACT NO. 85 OF 1993
Tenderers are to allow for costs in providing a project specific ' Construction Phase Safety, Health and Environmental Plan' in accordance with "Section 2 - Specification Data associated with SANS 1921-1:2004" clause C4.18 in "Part C3 - Scope of Work"
| F:............................. V:............................ T:............................ | Item
E15 | NOTICE BOARD, SITE OFFICE, ETC.
Tenderers are to allow for the provision and removal of a project notice board and a site office in accordance with the Principal Agent's requirements.
| F:............................. V:............................ T:............................ | Item
E16 | IMPORTED MATERIALS AND EQUIPMENT
Where imported items are listed in the tender documents, the tenderer shall provide all information called for, failing which the price of any such item, material or equipment shall be excluded from currency fluctuations. (Refer to T2.14 - Schedule of Imported Materials and Equipment.
| F:............................. V:............................ T:............................ | Item
E17 | CONTRACT DOCUMENTS
The drawings issues with these Tender documents do not comprise the complete set but serves as a guide only for tendering purposes and for indicating the scope of works to enable the Tenderer to acquaint him with the nature and extent of the works and the manner in which they are to be executed.
Should any part of the drawings not be clearly legible to the Tenderer he shall, before submitting his Tender, obtain clarification in writing from the principal agent.
| F:............................. V:............................ T:............................ | Item
| Carried forward to collection |  |  | R
|  | UNIT | QUANTITY | RATE | AMOUNT
E18 | GENERAL PREAMBLES
The Document Preambles will be the “ASAQS Model Preambles for Trades – 2008” and is obtainable from the various Regional Office’s of the Department of Public Works and shall be read in conjunction with the Bills of Quantities and be referred to for the full descriptions of work to be done and materials to be used.
| F:............................. V:............................ T:............................ | Item
E19 | TRADE NAMES
Wherever a Trade Name for any product has been described in the Bills of Quantities the Tenderer's attention is drawn to the fact that any other product of equal quality may be used subject to the written approval of the Principal Agent being obtained prior to the closing date for submission of Tenders.
| F:............................. V:............................ T:............................ | Item
E20 | EXISTING PREMISES OCCUPIED
Refer to Scope of Works Part C3 of this Tender Document for information on the occupation of existing buildings.
| F:............................. V:............................ T:............................ | Item
E21 | INACCURATE AND DEFECTIVE WORK EXECUTED UNDER PREVIOUS CONTRACT
The contractor shall, after taking possession of the site and before commencing the work, check all levels, liners, profiles and the like and satisfy himself as to the dimensional accuracy of all work executed under the previous contract which may affect his work.
Should any inaccurate or defective work be found, the contractor shall immediately notify the principal agent in writing requesting his instructions with regard thereto and afford every facility to those rectifying such inaccurate or defective work.
| F:............................. V:............................ T:............................ | Item
E22 | VIEWING THE SITE IN SECURITY AREAS
If the site is situated in a security area and the Tenderder must arrange with the Authorities to obtain permission to enter the site for Tenderding purposes.
| F:............................. V:............................ T:............................ | Item
E23 | COMMENCEMENT OF WORKS IN SECURITY AREAS
If the works falls within a security area, the contractor must arrange with the Authorities and give the necessary notices before commencement of the works. Should the contractor fail to make such arrangements, admission to the site may be refused and any additional costs will be for the contractor's account.
| F:............................. V:............................ T:............................ | Item
E24 | ENTRANCE PERMITS TO SECURITY AREAS
If the works fall within a security area, the contractor shall obtain entrance permits for his personnel and workmen entering the area and shall comply with all regulations and instructions which may be issued from time to time regarding the protection of persons and property under control of the Authority.
| F:............................. V:............................ T:............................ | Item
| Carried forward to collection |  |  | R
|  | UNIT | QUANTITY | RATE | AMOUNT
E25 | SECURITY CHECK OF PERSONNEL
The principal agent may require the contractor to have his personnel and workmen, or a certain number of them, security classified.
In the event of the principal agent requesting the removal of a person or persons from the works for security reasons, the contractor shall do so forthwith and shall thereafter ensure that such person or persons are denied access to the works and the site and/or to any document or information relating to the works.
| F:............................. V:............................ T:............................ | Item
E26 | PROHIBITION ON TAKING PHOTOGRAPHS
In terms of article 119 of the Defence Act, 44 of 1957, it is prohibited to sketch or to take photographs of any military site or installation or any building or civil works thereon or to be in possession of a camera or other apparatus used for taking photographs, except when authorised thereto by or on behalf of the Minister.
The same prohibition is also applicable to all Correctional Institutions in terms of article 44.1(e) of the Correctional Services Act 8 of 1959.
| F:............................. V:............................ T:............................ | Item
E27 | Management of Water Water for Construction purposes must be obtained from alternative water sources (i.e. supply other than water that is produced and distributed by a regulated water service authority from a licenced water treatment works for human consumption), eg dams, rivers, boreholes, springs, rainwater harvesting, recycled sewerage water,etc. The alternative water source shall not be of an inferior quality / standard than that required for construction purposes. The client reserves the rigfht through his agents to test such supplies or request certificates confirming the grade and nature of the water supply. Relevant knowledge of the respective area will be an advantage.
E28 | DEVELOPMENT OF SKILLS THROUGH INFRASTRUCTURE CONTRACTS
The contractor shall achieve in the execution of this contract the Contract Participation Goals (CPG) relating to the engagement of targeted enterprises as established in the CIDB Standard for Indirect Targeting for Enterprise Development through Construction works Contracts Published in Government Gazette No 48491)
| F:............................. V:............................ T:............................ | Item
| Carried forward to collection |  |  | R
| Carried forward to collection |  |  | R
SECTION 1
SUMMARY – PRELIMINARY & GENERAL
Collection |  |  | Page No. | Amount
|  |  | 1 | R
|  |  | 2 | R
|  |  | 3 | R
|  |  | 4 | R
|  |  | 5 | R
|  |  | 6 | R
|  |  | 7 | R
|  |  | 8 | R
|  |  | 9 | R
|  |  | 10 | R
|  |  | 11 | R
|  |  | 12 | R
|  |  | 13 | R
|  |  | 14 | R
|  |  | 15 | R
|  |  | 16 | R
Carried forward to Final Summary |  |  |  | R
Section No. 1
Preliminary & General
Summary
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C2.3_BOQ - Fly
KZN Public Works: 191 Prince Alfred Street
PART C2.3 BILL OF QUANTITIES
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C.3_Scope of Work - Fly
KZN Public Works: 191 Prince Alfred Street
PART C3. SCOPE OF WORKS
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C3.1_Scope of Works
C3.1 SCOPE OF WORKS GCC FOR CONSTRUCTION WORKS (Edition 2 of 2010)
Scope of Works complied in accordance with SANS 10403 where reference is made to this part of SANS 1921-1:2004
Project title: |  |  | KZN Public Works: 191 Prince Alfred Street
Tender no: |  |  | ZNTM012345W |  |  |  | Project Code: | 012345
SECTION 1
1 | EXTENT OF THE WORKS | [8 empty] | The consultant(s)/project manager must acquaint themselves fully with all relevant matters pertaining to this section in order to enable prospective tenderer’s to price for all eventualities.
1.1 | EMPLOYERS OBJECTIVES
| Upgrade existing domestic and fire water supply and reticulation by installing new pipes, water storage tanks, pumps, pump house, boreholes, etc. whilst the existing system remains in operation, and switching over to the new system upon completion. | [8 empty] | The following serves as a guideline only with regard to items to be Included in this Scope of Work.
1.2 | OVERVIEW OF THE WORKS
The rehabilitation of all road and pavement crossings.
1.3 | EXTENT OF THE WORKS
The contract comprises the construction of the above (Item 1) face brick buildings with tiled roofs.
1.4 | LOCATION OF THE WORKS
The site is situated within the premises of the Mosvold Hospital on the fringe of the town of Ingwavuma. GPS Co-ordinates for the site is .............................................................................................................
1.5 | TEMPORARY WORKS
All temporary work to comply with the Occupational Health and safety Act (Act 85 of 1993)
2 | ENGINEERING
2.1 | EMPLOYER'S DESIGN
Not applicable
2.2 | DESIGN BRIEF
Not applicable
2.3 | DRAWINGS
See list of drawings/Annexure's attached to this document.
2.4 | DESIGN PROCEDURES
Not applicable
3 | PROCUREMENT
3.1 | PREFERENTIAL PROCUREMENT PROCEDURES
This tender will be subject to the implementation of the Preferential Procurement Regulations, 2022, pertaining to the Preferential Procurement Policy Framework Act, Act Number 5 of 2000 and the relevant Supply Chain Management Legislation and the KwaZulu-Natal Supply Chain Management Policy Framework published by the KwaZulu-Natal Provincial Treasury. Tenderders are referred to www.kzntreasury.gov.za for access to the relevant documents. Tenderders are advised to familiarize themselves with the contents of the KwaZulu-Natal Supply Chain Management Policy Framework regarding Preference Point Systems, evaluation of tenders appeals and other matters.
3.2 | RESOURCE STANDARD PERTAINING TO TARGETED PROCUREMENT
NOTE : This project will be adjudicated as not exceeding R 50,000 000,00
3.3 | SCOPE OF MANDATORY SUBCONTRACT WORK
Not applicable
3.4 | PREFERRED SUBCONTRACTORS/SUPPLIERS
Not applicable
3.5 | SUBCONTRACTING PROCEDURES
Not applicable
4 | CONSTRUCTION
4.1 | APPLICABLE SANS 2001 STANDARDS FOR CONSTRUCTION WORKS
The Contractor is referred to the "Model Preambles to Trades - 2008", any "Supplementary Preambles", the Electrical Specifications and Mechanical Specification for full descriptions of materials and methods referred to in these Bills of Quantities/Lump Sum documents, insofar as they apply. The Contractor is advised to study the "Standard Preambles to all Trades", any "Supplementary Preambles", the Electrical Specifications and Mechanical Specification, before pricing Bills of Quantities/Lump Sum documents.
Where the description in the Bills of Quantities/Lump Sum documents differ from those in the Standard Electrical Specifications, the descriptions in the Bills of Quantities/Lump Sum documents are to apply. No claim whatsoever will be allowed in respect of errors in pricing due to brevity of description of items in the Bills of Quantities/Lump Sum documents which are fully described when read in conjunction with the relevant Preambles and/or Specifications. Suppliers of materials and the like, whose quality systems apply with one or more of the SABS/SANS ISO 9000 Series should be used whenever possible in the absence of a particular SABS/SANS Specification Standard Mark.
Wherever the words "shall be deemed to be included in the description", "shall be stated" or other words having the same effect, appear in the Standard System, it shall be deemed that all descriptions in these Bills of Quantities/Lump Sum documents incorporated such inclusions and statements whether specifically stated or not.
The Contractor is hereby informed that where SABS/SANS Specifications are referred to in these Bills of Quantities/Lump Sums documents and Specifications thereto, then ONLY the Specification of Work Clauses will apply. The method of measurement and payment clauses will NOT apply to this Contract.
The Contractor is hereby informed that risk of collapse and keeping excavations free from water (excluding subterranean water) generally are deemed to be included in the descriptions unless accommodated in the system of measurement. Please refer to the Geotechnical Investigation report when included at the end of these tender documents. Whenever reference is made to "Sub-Contractor", "Nominated Sub-Contractor" or the like in the specifications included or referred to in these Bills of Quantities/Lump Sums documents, it shall be deemed to mean "Contractor" as defined.
4.2 | APPLICABLE NATIONAL AND INTERNATIONAL STANDARDS
See above 4.1
4.3 | PARTICULAR / GENERIC SPECIFICATIONS
The Contractor is referred to the following documents whether attached to this document or not:
| SPECIFICATION | [6 empty] | PAGES HIV1 TO HIV3 1 to 49 E/1 to E/20 LP/1 to LP/6
| Specification for HIV/AIDS Awareness (CIDB) | [6 empty] | HIV1 TO HIV3
Specific Construction, Safety, Health and Environmental Plan
| Standard Preambles for all Trades (Rev 3) - DOH 2009 | [6 empty] | 1 to 95
| General Electrical Specification | [6 empty] | E/1 to E/20
| Lightning Protection Installation | [6 empty] | LP/1 to LP/6
4.4 | CERTIFICATION BY RECOGNIZED BODIES
Only contractors registered with the Electrical Contracting Board of South Africa in accordance with the Regulations of the Occupational Health and Safety Act will be accepted and permitted to do work under this contract.
4.5 | AGRÉMENT CERTIFICATES
Not applicable
4.6 | PLANT AND MATERIAL PROVIDED BY THE EMPLOYER
Not applicable
4.7 | SERVICES AND FACILITIES PROVIDED BY THE EMPLOYER
Not applicable
4.8 | OTHER SERVICES AND FACILITIES
The Contractor shall provide any artificial lighting which may be necessary or required for the proper execution of the works, and provide electric power and water required by all Sub-Contractors, Nominated Sub-Contractors and Sub-Contractors appointed directly by the Administration. The Contractor shall give all notices and pay all fees in connection with temporary electrical and water connections and shall connect temporary Electrical and Water meters for and pay for all current and water consumed. The Contractor is advised that the permanent light fittings and water points of any kind installed in the Works are not to be used to provide temporary lighting and supplement water requirements for construction purposes.
5 | MANAGEMENT
5.1 | APPLICABLE SANS 1921 STANDARDS
Tenderders are referred to SECTION 2 : SPECIFICATION DATA ASSOCIATED WITH SANS 1921-1:2004 IN THIS DOCUMENT
5.2 | RECORDING OF WEATHER
The Contractor shall keep record of abnormal climatic conditions to facilitate the adjudication of claims for extension of the contract period.
The Contractor shall allow in his programme for the following number of days for rain days (rain > 10mm per day) as per the table below:
|  | CURRENT YEAR |  |  |  | YEAR + 1 |  |  | YEAR + 2
|  | January |  | w/days |  | 3 |  |  | 3
|  | February |  | w/days |  | 3 |  |  | 3
|  | March |  | w/days |  | 3 |  |  | 3
|  | April |  | w/days |  | 3 |  |  | 3
|  | May |  | w/days |  | 3 |  |  | 3
|  | June |  | w/days |  | 3 |  |  | 3
|  | July |  | w/days |  | 3
|  | August |  | w/days |  | 3
|  | September |  | w/days |  | 3
|  | October |  | w/days |  | 3
|  | November |  | w/days |  | 3
|  | December |  | w/days | 3 | 3
5.3 | MANAGEMENT MEETINGS
In order to facilitate the smooth functioning of the Works and to ensure the closest co-operation between all the parties concerned, the Employer will call for regular meetings to be held on the site, at which a senior member of the Contracting firm and the General Foreman of the Works will always be required to be present. In addition to the above, other persons will be required to attend these meetings as and when their presence is necessary, e.g., Consultants in all disciplines, representatives of the various Sub-Contractors, etc. Proper minutes of these meetings will be kept by the Employer\Principal Agent and copies will be circulated to all persons attending the meetings and to others who need to be kept informed.
5.4 | FORMS FOR CONTRACT ADMINISTRATION
The Employer shall provide all necessary forms.
5.5 | ELECTRONIC PAYMENTS
The Contractor shall provide all required information to the Employer to facilitate electronic payments upon request.
5.6 | DAILY RECORDS
The Contractor shall keep daily records of people and equipment employed as well as a site diary in respect of work performed on the site. At the end of each week the Contractor shall provide the Principal Agent with a written record, in schedule form, reflecting the number and description of tradesmen and labourers employed by him and all Sub-Contractors on the works each day. At the end of each week the Contractor shall provide the Principal Agent with a written record, in schedule form, reflecting the number, type and capacity of all plant, excluding hand tools, currently used on the works.
5.7 | BONDS AND GUARANTEES
The Contractor shall within 10 calendar days after receiving notice from the Engineer and prior to receiving a completed copy of this agreement, including the schedule of deviations (if any), contact the Employer’s agent (whose details are given in the contract data) to arrange the delivery of any bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data.
5.8 | PAYMENT CERTIFICATES
Requirements will be in accordance with the Employers prescriptions.
5.9 | PERMITS
The Contractor is advised that, in the case of an existing building or institution, all security measures in force will remain in operation and he must acquaint himself and his Employees with them as he and his Employees will at all times be subject to these measures. The Contractor will on no account extend his operations beyond the confines of the building site as indicated by the Employer and must ensure that all his Employees are made aware of these limits. Any Employee disregarding this instruction and found outside the limit of the building site without authority, shall be redeployed immediately and shall not again be employed on this Contract. The Contractor will be responsible for ensuring that this instruction is strictly enforced and must provide and remove upon completion or when directed, such other necessary temporary barriers, fences, etc., as may be required and is to allow opposite this item for any charges he may wish to make in this connection. The Employer will accept no responsibility whatsoever for damage to or the loss of plant, materials, etc., from the site.
5.10 | PROOF OF COMPLIANCE WITH THE LAW
The following certificates must be provided before first delivery is taken: - HIV/STI Report (Bound into this document) - Electrical Compliance Certificate - Plumbing Compliance Certificate - Lightning Certificate - Soil Protection Certificate - Concrete test and cube certificates - Waterproofing Guarantee certificates - TR1 and TR2 prefabricated roof truss certificates - Soil compaction certificates - Electrical and Mechanical test certificates - Plumbing and drainage pressure test certificates - Fire Compliance Certificate - Entomology Certificate - SANS 10400-A:2010 compliance certificates - Latest National Building Regulation
5.11 | INSURANCE PROVIDED BY THE EMPLOYER
Not Applicable
SECTION 2
SPECIFICATION DATA ASSOCIATED WITH SANS 1921-2004
Clause Numbers
4.1.7 | The requirements for drawings, information and calculations for which the Contractor is responsible are:
Prefabricated roof trusses design must be submitted for approval 30 days prior to erections.
4.2.1 | The responsibility strategy assigned to the Contractor for the works is:
Strategy A
4.2.2 | The structural engineer is:
ABC Engineers
4.2.3 | Drawings & other info are to be submitted in accordance with the contractors programme
N/A
4.3 | The planning, programme and method statement are to comply with the following:
N/A
4.12.1 | Samples of materials
The work is to be executed with materials of the best specified and in the most substantial and workmanlike manner under the inspection of the Employer and to his satisfaction. The Contractor shall furnish, without delay, such samples as called for or may be called for by the Employer, who may reject all materials or workmanship not corresponding with the approved sample. The samples of materials, workmanship and finishes that the Contractor is to provide and deliver to the employer are:
- Tile sample. - Brick sample. - Light fitting sample. - Screed panel 2m x 2m impact test. - Tested trial mix to be approved by the Engineer.
4.12.2 | Fabrication drawings that the contractor is to provide to the employer are:
None
4.12.3 | Office accommodation, equipment, accommodation for site meetings and other facilities for use by the employer and his agents are:
OFFICE FOR FOREMAN
Provide, erect, maintain and remove at completion a suitable temporary office for the Contractor or his Foreman, perfectly secured, lighted and ventilated and having a desk with drawers.
TELEPHONE
The Contractor shall provide a telephone on the site for the use of the Contractor and all Sub-Contractors for the duration of the Contract, and must make the necessary application for connection, give all notices and pay all fees, rentals and charges for the service and also for all calls.
OFFICE FOR INSPECTOR OF WORKS
Provide, erect, maintain and remove at completion a well constructed temporary office for the Inspector of Works not less than 4 x 3 m on plan and 3 m high to eaves to the approval of the Employer. The office shall be constructed of wood framing covered externally with corrugated iron or corrugated asbestos and with a lean-to roof covered with the same material as the external wall covering. The office shall be lined internally with soft board or other approved material and a ceiling shall be provided of the same material as the internal lining. A suspended wood floor shall be provided and is to finish not less than 300 mm above the ground level. A lockable door and a window, which provides adequate light and ventilation, shall be fitted. An office constructed of 115 mm thick brick-work and provided with a screeded concrete floor and roofed and ceiled as above described may be accepted as an alterative but prior permission of the Employer will be necessary before construction of such an office is commenced and his requirements shall be stated and fulfilled by the Contractor. The office shall be fitted in an approved manner with a sloping topped desk of height and length suitable for the laying out and studying of drawings, a desk or table with not less than two lock-up drawers, shelves, seating and wash-stand, and the Contractor shall provide all necessary attendance.
TELEPHONE IN OFFICE FOR INSPECTOR OF WORKS
The Contractor shall arrange for the installation of a lockable telephone in the Office for the Inspector of Works for the duration of the Contract. The Contractor will be required to make the necessary application for connection and give all notices on behalf of the Employer. The Employer will, however, be responsible for the direct payment of all fees, rentals and other charges by Telkom for the service for the Inspector of Works and for all calls made from this telephone.
SHED
Provide, erect, maintain and remove at completion, ample temporary sheds for the proper storage of materials and for the use of the workmen, and remove when no longer required.
4.14.6 | The requirement for provision and erection of signboards are:
Supply, erect, maintain and remove at completion a painted notice board, size overall 2800 x 2345 mm high sign written to detail as Drawing No. T9506 which drawing is available from offices of the Department of Public Works. Only the official notice board is to be displayed on the site and no Sub-Contractor's boards will be permitted. The Contractor, at his own cost, may provide a board on which all sub-contract firms' names may be sign written. The notice board is to be to the approval of the Employer and is to be maintained in first class condition and placed where directed at the entrance to the site and remain there for the duration of the Contract.
4.17.1 | Requirement for the termination, diversion or maintenance of existing services:
Should the Contractor come in contact with any underground cables or pipes during excavations, immediate notification must be made to the Employer and all work in the vicinity of such cables, pipes, etc., shall cease until authority to proceed has been obtained from the Employer. Should the Contractor damage underground cables or pipes resulting in a disruption of services to an existing institution such damage shall be repaired immediately.
4.17.3 | Services which are known to exist on the site:
Investigate and provide detail drawings.
4.17.4 | Requirement for detection apparatus
None
4.18 | ADDITIONAL HEALTH AND SAFETY REQUIREMENTS ARE:
By the submission of a tender, any Tenderder will, if awarded the contract to which this tender document relates, be deemed to be the mandatory as envisaged by Section 37 (2) of the Act. As a mandatory the successful Tenderder will be deemed to be the “principal contractor” and an employer in his/her/their own right with duties as prescribed in the Act and accordingly will be deemed to have agreed to be solely responsible for ensuring that in connection with the service to which this tender document relates, all work will be performed and machinery and plant used in accordance with the Act. Should the Contractor, for whatever reason be unable to perform as required by the Act, the Contractor undertakes to inform the Employer accordingly. Tenderders are advised that it is a Condition of this Tender that a 'Construction Phase Safety, Health and Environmental Plan' specifically relates to the project for which tenders are being submitted and must be prepared by the Tenderder and submitted with the other tender documents at the time of tender. Failure to do so will invalidate the tender.
Tenderders are therefore advised to study the 'Construction Safety, Health and Environmental Specification' which is issued as part of this tender document, the Model Preambles to Trades - 2008, any project Specification included in this tender document and any and all drawings which are referred to and issued as part of this tender document before preparing their own project specific 'Construction Phase Safety, Health and Environmental Plan' . Tenderders are also advised that such a plan which is submitted with a tender but is incomplete or considered inadequate by the Employer or his Representative will invalidate the tender. The Contractor will be deemed to have satisfied himself with his obligations in terms of the Act and to have allowed for all costs arising from compliance with the Act as no claim for extra costs arising from compliance with, and obligations in terms of the Act will be entertained.
4.22 | WORK BY NOMINATED AND SELECTED SUBCONTRACTORS COMPRISE:
[Provide list of applicable contractors]
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C3.2_Spec for HIV
C3.2 - SPECIFICATION FOR HIV/AIDS AWARENESS
1 | Scope
This generic specification contains requirements applicable to the reduction of the risk of transfer of the HIV virus between and among construction workers and the local community through the following four strategies:
| a) | raising awareness about HIV/AIDS;
| b) | providing construction workers with access to condoms;
| c) | HIV counselling, testing and referral services; and
| d) | Sexually Transmitted Infection diagnosis and treatment.
2 | Normative references:
The following standard contains provisions that, through reference in this text, constitute provisions of this standard:
SANS 4074 ISO 4074, Condom Rubbers
3 | Definitions and Abbreviations
| 3.1 | Definitions
Construction Worker: all persons in the employ of the contractor or in the employ of any of the subcontractors contracted by the contractor.
Local Community: the communities local to the site which are most likely to have contact with the construction worker and, in particular, sex workers in those communities.
Service provider: the natural or juristic person recognised by the South African Department of Health as specialist in conducting Aids Awareness Programmes.
| 3.2 | Abbreviations
STI: Sexually transmitted infection
HIV: Human Immunodeficiency Virus
AIDS: Acquired Immune Deficiency Syndrome
4 | Objectives
The objectives are to:
| a) | reduce the risk of transfer of the HIV virus between and among construction workers and the local community;
| b) | raise awareness amongst construction workers and the local community of the risk of infection with the HIV virus;
| c) | promote early diagnosis; and
| d) | assist affected individuals to access care and counselling.
5 | Requirements
| 5.1 | General requirement
The contractor shall, in order to satisfy the objectives stated in 4:
| a) | make condoms complying with the requirements of SABS ISO 4074 available to all construction workers at readily accessible points on the site, suitably protected from the elements, for the duration of the contract;
| b) | either place and maintain HIV/AIDS awareness posters of size of not less than A1 in areas which are highly trafficked by construction workers, or provide construction workers with a pamphlet, in languages largely understood by construction workers, which
| c) | encourage voluntary HIV/STI testing;
| d) | provide information concerning counselling, support and care of those that are infected services; and
| e) | comply with the requirements of 5.2.
The provisions of 5.1 c) and d) do not apply to this contract.
| 5.2 | HIV awareness programme
|  | 5.2.1 | The contractor shall:
|  |  | a) | engage a qualified service provider as described in the scope of works to conduct an HIV Awareness Programme which is structured to achieve the outcomes stated in 5.2.3 for contract workers as soon as a construction workers camp is established and populated or, where no such camp is established, within two weeks of the commencement of a significant portion of the works and at subsequent intervals, if any, provided for in the scope of works; and
|  |  | b) | arrange for, provide a suitable venue, and instruct all construction workers to attend the HIV Awareness Programme and notify the Employer's Representative of the date, time and venue whenever a session with construction workers is conducted.
The contact particulars of qualified service providers are as follows:
Name
Fax
Tel
email
Note: The National Department of Public Works maintains a list of qualified service providers.
|  | 5.2.2 | The contractor shall do nothing to dissuade construction workers from attending such an HIV Awareness Programme and shall take all reasonable steps to ensure that a minimum of 90% of construction workers engaged in the works attend such a programme, when it is conducted.
|  | 5.2.3 | The outcomes of the HIV Awareness Programme shall as a minimum, result in contract workers exposed to such a programme being able to:
|  |  | a) | communicate the existence of problems of HIV and be able to outline the consequences of transmission of HIV to or from the local community;
|  |  | b) | recall and communicate the mode of HIV transmission and preventative measures including the proper use of the condom.
The HIV/ Aids awareness programme described in 5.2 is to be repeated at four month intervals throughout the duration of the contract. (Four times in total, including the initial one at the start of the contract)
| 5.3 | Reporting
|  | 5.3.1 | The contractor shall prepare and attach to his claims for payment a brief report which outlines how the actions taken by the contractor in the period for which payment is claimed satisfy the requirements and a schedule which lists the names, identity numbers, trade / occupation and name of employer of all construction workers exposed to the programme (see HIV/STI Compliance Report).
|  | 5.3.2 | The employer's representative shall certify the report and schedule described in 5.3.1 whenever a claim for payment is issued to the employer.
Note: In the event that the contractor fails to satisfy the requirements of this specification, the employer (Head: Public Works) may apply any of the sanctions provided for in the contract. Sanctions may include the application of a financial penalty of .04% of the Contract Sum.
The HIV /Aids awareness programme described in 5.2 shall in addition be conducted for the benefit of the local community on two occasions in the community centre nearest to the building site. The contractor shall be responsible for inviting identifiable community-based institutions and organisations, churches, and schools to participate in the programme.
ANNEX A: ITEMS WHICH MAY NEED TO BE CONSIDERED WHEN PREPARING THE SCOPE OF WORK FOR A PARTICULAR PROJECT.
(Normative)
The scope of work prepared in accordance with the provisions of Annex D of SANS 10403 (The formatting and compilation of procurement documents) for a specific project should commence with a description of the works and thereafter describe items relating t
Example
Health and Safety
The generic specification for HIV/ Aids Awareness as published by the Construction Industry Development Board (see www.cidb.org.za) is applicable to this contract. The HIV/ Aids awareness programme described in 5.2 is to be repeated at four month interval
The HIV /Aids awareness programme described in 5.2 shall in addition be conducted for the benefit of the local community on two occasions in the XXXXX community centre. The contractor shall be responsible for inviting identifiable community-based institute
The contact particulars of qualified service providers (see 5.2.1a) are as follows: Name Tel Fax email
The variations to this generic specification are as follows: nil
or
The provisions of 5.1 c) and d) do not apply to this contract.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C3.3_HIV Compliance Report
C3.3 - HIV/STI COMPLIANCE REPORT
Pro-forma reporting format in terms of the SPECIFICATION FOR HIV/AIDS AWARENESS
Project Code: | 012345
Payment Claim number: |  | Period covered by payment claim:
1. Distribution of condoms (briefly describe where and how condoms are distributed).
2. Posters / pamphlets (briefly describe where posters were placed / how pamphlets were distributed).
3. Voluntary testing (briefly describe the actions taken / information provided to promote testing).
4. Counselling, support and care (summarise information provided).
5. HIV awareness programme (briefly describe action).
6. Schedule of construction workers exposed to the HIV awareness programme.
Name | Identity number |  | Trade / occupation | Name of employer
I hereby declare the above to be a true reflection of actions taken to ensure compliance with the specification.
For Contractor: |  |  | Employer's representative:
Name: |  |  | Name:
Signature: |  |  | Signature:
Date: |  |  | Date:
NOT APPLICABLE
NOT APPLICABLE
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C4_Site Info - Fly
KZN Public Works: 191 Prince Alfred Street
PART C4. SITE INFORMATION
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C4.1_Site Information
C4.1 SITE INFORMATION GCC FOR CONSTRUCTION WORKS (2 Edition of 2010)
Project title: |  |  | KZN Public Works: 191 Prince Alfred Street
Tender No. |  |  | ZNTM012345W | Project Code: | 012345
C4.1 |  |  | Site Information
C4.1 |  | GENERAL
| (a) | Describe nature of ground, surface conditions, water table as visible in test holes, and other indisputable facts that may affect construction. Provide available data and information. |  |  |  | The Standard for Uniformity in Construction Procurement published in terms of the Construction Industry Development Board (CIDB) Act, 2000 (Act no. 38 of 2000), the Standardized Construction Procurement Documents for Engineering and Construction Works as issued by the CIDB and any other relevant documentation pertaining thereto must be studied and all principles in this regard must be applied to all procurement documentation, practices and procedures.
| (b) | Specific requirements must be described.
| (c) | Any additional site information such as location, improvements on site, adjacent buildings, environmental issues, etc. must be described in detail herein. If project is phased, indicate the phased work procedure with a colour coded site plan or graphical key or sorts. |  |  |  | The consultant(s)/project manager must acquaint themselves fully with all relevant matters pertaining to this section in order to enable prospective tenderer’s to price for all eventualities.
C4.2 |  | GEOTECHNICAL INVESTIGATION REPORT
| (a) | Not applicable
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C5_List of Dwg - fly
KZN Public Works: 191 Prince Alfred Street
PART C5 - DRAWINGS / ANNEXURES
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## C5.1_List of Drawings
C5.1 - LIST OF DRAWINGS/ANNEXURES
KZN Public Works: 191 Prince Alfred Street
Tender No.: | ZNTM012345W |  | Project Code: | 012345
(Where drawings/annexure's are issued, document compilers must insert the following paragraph and list the applicable drawings/annexure's below.)
The following drawings/annexure's shall be issued during the Tender period to form part of the tender documentation. Where applicable, drawings/annexure's could be re-issued to the Contractor at commencement of the construction phase.
DRAWING NO |  |  | DESCRIPTION
???????? |  |  | Site Layout
???????? |  |  | etc.
???????? |  |  | etc.
???????? |  |  | ect.
???????? |  |  | ect.
???????? |  |  | ect.
ect.
ANNEXURES
Annexure 1 |  | Standard Preambles for all Trades (Rev 3) - DOH 2009
Annexure 2 |  | General Electrical Specifications
Annexure 3 |  | Lightning Protection Specifications
Annexure 4 |  | Map of Tender submission location
Annexure 5 |  | Joint Venture Agreement
Annexure 6 |  | #REF!
Annexure 7 |  | Health and Safety Specification
Annexure 8 |  | Health and Safety Bill of Quantities
Annexure 9 |  | Builders Lien Agreement
Annexure 10 |  | Geotechnical Investigation Report (If applicable)
Annexure 11 |  | EPWP Employment Contract
Annexure 12 |  | Attendance Register - Infrastructure and Other projects
Annexure 13 |  | EPWP Data Collection tool for Phase 3 system
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## Annexures - fly
KZN Public Works: 191 Prince Alfred Street
ANNEXURES
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## PMB
N
DOPW - Head Office Tender Box Location
191 Prince Alfred street
Pietermaritzburg
PIETERMARITZBURG
DOPW Southern Region- Tender Box Location
10 Prince Alfred street
Pietermaritzburg
Back to Main Menu
Print

## ULUNDI
ADMINISTRATIVE BUILDING
DOPW - Tender Box Location
North Coast Region
1 st Floor Stair Landing
N
ULUNDI
Back to Main Menu
Print

## LSMITH
LADYSMITH
DOPW
N
DOPW- Tender Box Location
40 Shepstone road
Ladysmith
Back to Main Menu
Print

## DURBAN
DOPW
N
MAYVILLE - DURBAN
DOPW- Tender Box Location
455A King Cetshwayo Hwy
Mayville
Back to Main Menu
Print

## Joint Venture Agreement
Annexure 5
Joint Venture Agreement
(March 2004)
(First Edition of CIDB document 1017)
Please do a print preview before printing
1. | PREAMBLE
This agreement is made and entered into by and between
of the first part and
of the second part and
of the third part.
(allow for additional parties as necessary).
Whereas the foregoing parties have resolved to form a Joint Venture under the title of
for the exclusive purposes of securing and/or executing the Contract to be awarded by
(name of Employer)
to the KZN Department of Public Works in respect of the following project:
for (brief description of Contract)
KZN Public Works: 191 Prince Alfred Street
Now it is hereby agreed as follows :
2. | DEFINITIONS AND INTERPRETATION
2.1 | Definitions
The following words and expressions shall have the meanings indicated, except where the context otherwise
requires. Defined terms and words are, in general, signified in the text of the Agreement by the use of capital
initial letters, but the absence of such letters does not necessarily signify that a term, or word, is not defined.
‘Agreement’ means the agreement between the Members of the Joint Venture and includes this model form of
agreement together with the Preamble, Specific Provisions, if any, Schedules ‘A’, ‘B’ and ‘C’ and
any relevant Documents prepared prior to the signing of the Agreement and appended thereto.
‘Contract’ means the contract with the Employer for the supply of the Deliverables, for the purposes of securing
and executing which, the Joint Venture has been formed.
‘Deliverables’ means the works and/or services, equipment, materials, goods, etc. to be furnished by the
Joint Venture to the Employer in terms of the Contract.
‘Document’ means any written, drawn, typed, printed, or photographic material, which relates to the Agreement.
‘Employer’ means the person, or body, which is to award the Contract and will employ the Joint Venture if it is
awarded the Contract.
‘Joint Venture’ means the joint venture formed by the Members in accordance with the Agreement.
‘Management Committee’ means the body established in terms of the Agreement to manage all aspects of the
work of the Joint Venture in securing and executing the Contract and in meeting the provisions
for the Agreement.
‘Member’ means a person, or body which, being a party to the Agreement, is a member of the Joint Venture.
‘Member’s Interest’ means the proportion expressed as a percentage, which the total monetary value of all
resources provided and contributions made by a Member towards the execution by the Joint
Venture of the Contract bears to the total of such values by all Members and, unless otherwise
indicated in the Agreement, represents the extent to which the Member participates in the fortunes
of the Joint Venture.
‘Representative’ means the person representing a Member on the Management Committee.
‘Schedules’ means Schedules ‘A’, ‘B’ and ‘C’ which set out general, financial and other information relating
to the Members and the obligations, duties, rights, risks and benefits arising from their participation
in the Joint Venture.
‘Specific Provisions’ means the variations, if any, required to this standard form of agreement for the specific
purposes of the Agreement.
2.2 | Interpretation
Unless inconsistent with the context, an expression in the Agreement which denotes:
• any gender shall include the other genders
• a natural person shall include a juristic person and vice versa
• the singular shall include the plural and vice versa
2.3 | Headings
The headings to clauses of the Agreement shall not be considered part thereof, nor shall the words they
contain be taken into account in the interpretation of any clause.
2.4 | Law
The Agreement shall be construed in accordance with and governed by the laws of the Republic of South Africa
and the English language versions shall prevail.
2.5 | Language
English shall be exclusively used by the Members in the preparation of Documents unless otherwise indicated.
2.6 | Conflict between Agreement and Contract
Should any provision of the Agreement be in conflict with the terms of the Contract, the Agreement shall be
amended to the approval of the Management Committee so as to eliminate the conflict.
3. | JOINT VENTURE GENERAL
3.1 | Establishment and Purpose
The Joint Venture established by the Members in terms of the Agreement is an unincorporated association with
the exclusive purposes of securing and executing the Contract for the benefit of the Members.
3.2 | Termination
The operation of the Joint Venture and the validity of the Agreement shall terminate if and when it becomes
evident that the Joint Venture will not be awarded the Contract, or, if the Joint Venture secures the Contract,
when all obligations and rights of the Joint Venture and the Members in connection with the Contract and the
Agreement have ceased and/or been satisfactorily discharged.
Unless otherwise decided by the Management Committee, the Agreement shall not terminate if a Member
changes its name, or is taken over by, or merged with, another body.
| This agreement will terminate when any one of the Members resigns, are liquidated or opts out of this agreement and the Joint Venture will be in breach of contract with the Employer and their contract could be cancelled. |  |  | 2014-10-01
3.3 | Exclusivity
Unless otherwise agreed by the Management Committee, or provided for in the Contract no Member shall
engage in any activity related to the Contract other than as a Member of the Joint Venture and Members shall
ensure that their subsidiaries and other bodies over which they have control comply with this requirement.
3.4 | Participation of Members
Except as may otherwise be stipulated in the Agreement, each Member shall be responsible for all costs incurred by it prior to the date of inception of the Agreement.
Subsequent to the date of inception of the Agreement, each Member shall, participate in the operations, risks, responsibilities and fortunes of the Joint Venture including, inter alia, the provision of funding, sureties, guarantees, insurances, human and other resources and participation in profits and losses to the extents indicated in the Schedules. Participation in any aspect not covered in the Schedules shall, if an agreement cannot be reached between the Members, be to the same extents as indicated by the Members Interests.
3.5 | Management
The affairs of the Joint Venture shall be directed and controlled by the Management Committee, as set out in Section 4 hereof.
3.6 | Confidentiality
All matters relating to the Agreement and the Contract shall be treated by the Members as confidential and no such matter shall be disclosed to any third party without the prior written approval of the Management Committee.
No Member shall be party to the dissemination of publicity relating to the Contract, or the Agreement, without the prior written approval of the Management Committee and the Employer.
3.7 | Assignment
No Member shall cede, assign, or in any other way make over any of its rights, or obligations, under the Agreement without the prior written consent of the Management Committee.
3.8 | Subcontracting
No Member shall subcontract any obligation, work or duty for which it is, itself, responsible in terms of the Agreement without the prior written consent of the Management Committee.
3.9 | Variations to Agreement
No variation, modification, or waiver of any part of the Agreement shall be of any force, or effect, unless unanimously agreed by the Members and reduced to writing.
3.10 | Liability
Each Member warrants that it will indemnify the other Members against all legal liabilities arising out of, or in connection with the performance of its obligations under the Agreement.
It is acknowledged by the Members that they may be held jointly and severally liable in respect of claims against the Joint Venture by the Employer or third parties.
4. | MANAGEMENT OF JOINT VENTURE
4.1 | General
The affairs of the Joint Venture shall be directed, controlled and managed by the Management Committee, which, within the terms of the Agreement and the Contract, shall have full authority to bind the Members in all matters relating to the affairs of the Joint Venture.
Communication between the Joint Venture and the Employer, or third parties, relating to the Contract shall be conducted exclusively by the Management Committee, or by such person as it may delegate to perform this function.
The Management Committee shall have the power to appoint a project manager and/or such other persons as it may see fit to appoint for the purpose of executing the Contract and may delegate such of its powers, responsibilities and duties as it may consider necessary, or desirable, to persons or bodies appointed or seconded for this purpose.
Such administrative functions as are necessary to ensure the effective operation of the Management Committee shall be performed by its chairman.
4.2 | Management Committee
4.2.1 | Composition
The Management Committee shall, unless otherwise agreed by all the Members, consist of one Representative of each Member and each Member shall be obliged, at all times, to maintain a Representative on the Management Committee.
Each member shall, not later than three working days after the signing of the Agreement, appoint its Representative and notify the other Members of the name and contact details of the Representative. Such Representative shall have the power to bind the Member that he represents in all matters relating to the execution of the Contract and the performance of the Agreement.
A Member shall be entitled, after giving the other Members not less than three working days written notice of his intention to do so, appoint, remove and/or replace, an alternate who shall, at any meeting of the Management Committee from which the Representative whom he represents is absent, be vested with all rights and powers and subjected to all the obligations of the absent Representative.
The chairman of the Management Committee shall be the Representative of the Member which has the largest Member’s Interest. If two, or more, Members have the same, largest Member’s Interest, the chairmanship shall rotate between the Representatives of such Members at three monthly intervals, the order of rotation to be determined by ballot.
Notwithstanding the foregoing, the chairmanship of the Management Committee may be determined, or changed, at any time by unanimous decision of the Management Committee.
No remuneration shall be paid by the Joint Venture to Representatives or their alternates for serving on the Management Committee, unless otherwise decided by the Management Committee.
4.2.2 | Meetings
Meetings of the Management Committee shall take place at such times and places as the Management Committee may determine, provided that the chairman shall convene a meeting of the Management Committee to be held not later than ten working days after he has been requested, in writing, by a Member to do so. Not less than five working days written notice of any meeting of the Management Committee shall be given to all Representatives and their alternates.
The Management Committee may permit, or invite, persons other than Representatives or alternates to attend any of its meetings, but such persons shall not have voting rights.
4.2.3 | Decisions
Each Representative shall have one vote on the Management Committee and where, in terms of this clause, a casting vote is required, this shall be exercised by the chairman.
All decisions of the Management Committee shall, desirably, be unanimous. Accordingly, if unanimity cannot, initially, be achieved in regard to a decision, the meeting at which that decision is sought shall be adjourned for a period of 48 hours to enable Representatives to consult with their principals. If, on resumption of the adjourned meeting, unanimity can still not be achieved, the decision, provided it is not one requiring unanimity of the Members, shall be taken by majority vote and, in the event of a tie, the chairman shall exercise a casting vote.
A Member not satisfied with a majority decision of the Management Committee may declare a dispute, to be dealt with in terms of Clause 8 hereof, but the majority decision shall, nevertheless, be implemented with immediate effect.
Decisions of the Management Committee, whether taken at a meeting, or otherwise, shall be recorded in written minutes, which shall be distributed by the chairman to reach the Representatives not later than five working days after those decisions were taken. Such minutes shall be deemed to have been affirmed by the Representatives unless written notice of dissent is received by the chairman not later than three working days after receipt of the minutes by the Representative.
4.2.4 | Powers and duties
The functions, responsibilities and powers of the Management Committee shall include, inter alia, those listed below:
4.2.4.1 | Formulating overall policy in regard to the achievement of the objectives of the Joint Venture.
4.2.4.2 | Managing the day to day affairs of the Joint Venture.
4.2.4.3 | Monitoring, directing and co-ordinating the activities of the Members to ensure that the objectives of the Joint Venture are achieved and that the obligations and responsibilities of the individual Members are met.
4.2.4.4 | Monitoring and controlling the financial affairs of the Joint Venture and ensuring that proper books of account and financial records relating to affairs of the Joint Venture are maintained in an approved form and submitted to the Management Committee for approval at regular intervals, which shall not be longer than one month.
4.2.4.5 | Determining the necessity for and the details of any changes in the duties and responsibilities of Members provided that any resulting changes in Members’ Interests shall be unanimously approved by the Members.
4.2.4.6 | Determining the terms and conditions of employment of personnel and the emoluments applicable to staff seconded to the Joint Venture by the Members.
4.2.4.7 | Controlling and approving the appointment of all subcontractors.
4.2.4.8 | Procuring, after the completion of the Contract and the release of all bonds, guarantees and sureties given in respect of the performances of the Joint Venture and the Members, the preparation and auditing of a final set of accounts, on the basis of which the final profits, or losses, attributable to the individual Members shall be determined and any necessary adjustments effected.
5 | RESOURCES OF JOINT VENTURE
The resources to be utilised by the Joint Venture in securing and executing the Contract shall, insofar as these are to be provided directly by the Members, be as set out in the Schedules and may, from time to time, be amended by decision of the Management Committee, provided that the Member’s Interests are not, except with the unanimous approval of the Members, affected thereby.
Similarly, specific areas of responsibility of the Members for the performance of work and the provision of facilities shall be as set out in the Schedules and may, from time to time, be amended by decision of the Management Committee, provided that the Members’ Interest are not, except with the unanimous approval of the Members, affected thereby.
5.1 | Schedule ‘A’ (General)
Schedule ‘A’ shall contain general information relating to the Joint Venture including, inter alia,
the following :
1. The Employer’s name and address.
2. A brief description of the Contract and the Deliverables.
3. The name, physical address, communications addresses and domicilium citandi et executandi of each Member and of the Joint Venture.
4. The Members’ Interests.
5. A statement indicating whether, or not, Specific Provisions apply to the Agreement.
6. A schedule of insurance policies which must be taken out by the Joint Venture and by the individual Members.
7. A Schedule of sureties, indemnities and guarantees that must be furnished by the Joint Venture and by the individual Members.
8. Details of the persons, who, in the event of failure by the Members to reach agreement on the appointments of mediator and arbitrator, will nominate appointees to these positions in terms of Clauses 8.2 and 8.3.
5.2 | Schedule ‘B’ (Financial)
Schedule ‘B’ shall contain information regarding the financial affairs of the Joint Venture including, inter alia, the following :
1. The working capital required by the Joint Venture and the extent to which and manner whereby this will be provided and/or guaranteed by the individual Members from time to time.
2. The banking accounts that are to be opened in the name of the Joint Venture and the manner in which these are to be operated.
3. The rates of interest that will be applicable to amounts by which Members are in debit, or credit, to the Joint Venture.
4. The names of the auditors and others, if any, who will provide auditing and accounting services to the Joint Venture.
5. The intervals at which interim financial accounts and forecasts will be prepared for approval by the Management Committee.
6. Insofar as not covered in Schedule ‘C’, the basis on which contributions of various types by the Members towards the work of the Joint Venture in securing, executing, managing and satisfactorily completing the Contract, will be valued.
7. The basis on which profits and/or surplus cash will, if available from time to time, be distributed to Members.
8. The basis upon which losses, if any, are to be apportioned to Members.
5.3 | Schedule ‘C’ (Contributions by Members)
Schedule ‘C’ shall set out the contributions of various types, other than cash, that will be made by the individual Members towards the work and obligations of the Joint Venture and shall, as far as possible, indicate the monetary values to be placed on such contributions, which may include, inter alia, the following :
1. Staff seconded to the Joint Venture.
2. Work carried out and services provided to, or on behalf of, the Joint Venture.
3. Plant, equipment, facilities etc. made available for use by the Joint Venture.
4. Materials and goods supplied to, or on behalf of, the Joint Venture.
5. Licences, sureties, guarantees and indemnities furnished to, or on behalf of, the Joint
Venture.
6. Joint Venture Disclosure form required for the Contract.
6. | BREACH OF AGREEMENT
If a Member breaches any material provision of the Agreement, or delays or fails to fulfil its obligations in whole, or in part, and does not remedy the situation within fourteen calendar days of receipt of notice from the Management Committee, or another Member, to do so, the other Members shall have the right, without prejudice to any other rights arising from the default, to summarily terminate the Agreement and re-assign the defaulting Member’s rights and obligations in the Joint Venture as they see fit and withhold any moneys due to the defaulting member by the Joint Venture.
Each Member shall indemnify the other Members against all losses, costs and claims which may arise against them in the event of the Agreement being terminated as a result of breach of the Agreement by the said Member.
7. | INSOLVENCY OF MEMBER
Should a Member be placed in liquidation, or under judicial management, whether provisionally or finally, or propose any compromise with its creditors, the other Members shall be entitled to proceed in terms of Clause 6, as if the Member had breached the Agreement.
8. | DISPUTES
8.1 | Settlement
The Members shall negotiate in good faith and make every effort to settle any dispute, or claim, that may arise out of, or relate to, the Agreement.
If agreement cannot be reached, an aggrieved Member shall, if he intends to proceed further in terms of Clause 8.2 hereof, advise all other Members in writing that negotiations have failed and that he intends to refer the matter to mediation in terms of Clause 8.2.
8.2 | Mediation
Not earlier than ten working days after having advised the other Members, in terms of Clause 8.1, that negotiations in regard to a dispute have failed, an aggrieved Member may require that the dispute be referred, without legal representation, to mediation by a single mediator.
The mediator shall be selected by agreement between the Members, or, failing such agreement, by the person named for this purpose in Schedule ‘A’. The costs of the mediation shall be borne equally by all Members.
The mediator shall convene a hearing of the Members and may hold separate discussions with any Member and shall assist the Members in reaching a mutually acceptable settlement of their differences through means of reconciliation, interpretation, clarification, suggestion and advice. The Members shall record such agreement in writing and thereafter they shall be bound by such agreement.
The mediator is authorised to end the mediation process whenever in his opinion further efforts at mediation would not contribute to a resolution of the dispute between the Members.
8.3 | Arbitration
Where a dispute or claim is not resolved by mediation, it shall be referred to arbitration by a single arbitrator to be selected by agreement between the Members or, failing agreement, to be nominated by the person named for this purpose in Schedule ‘A’.
The Member requiring referral to arbitration shall notify the other Members, in writing, thereof, not later than thirty calendar days after the mediator has expressed his opinion, failing which the mediator’s opinion shall be deemed to have been accepted by all Members and shall be put into effect.
Arbitration shall be conducted in accordance with the provisions of the Arbitration Act No. 42 of 1965, as amended, and in accordance with such procedure as may be agreed by the Members or, failing such agreement, in accordance with the rules for the Conduct of Arbitrations published by the Association of Arbitrators and current at the date that the arbitrator is appointed.
The decisions of the arbitrator shall be final and binding on the Members, shall be carried into immediate effect and, if necessary, be made an order of any court of competent jurisdiction.
9. | DOMICILIUM
The Members choose domicilium citandi et executandi for all purposes of and in connection with the Agreement as stated in Schedule ‘A’. A Member shall be entitled to change his domicilium from time to time, but such change shall be effective only on receipt of written notice of the change by all other Members.
Member No. 1
Thus done and signed at ______________________________ this _____ day of ____________________20___
For and on behalf of___________________________________________________________________[Company]
by [name] ______________________________________________________ who warrants his authority to do so.
________________________
As witnesses 1. ___________________________ As witnesses 2. ___________________________
Member No. 2
Thus done and signed at ______________________________ this _____ day of ____________________20___
For and on behalf of___________________________________________________________________[Company]
by [name] ______________________________________________________ who warrants his authority to do so.
________________________
As witnesses 1. ___________________________ As witnesses 2. ___________________________
Member No. 3
Thus done and signed at ______________________________ this _____ day of ____________________20___
For and on behalf of___________________________________________________________________[Company]
by [name] ______________________________________________________ who warrants his authority to do so.
________________________
As witnesses 1. ___________________________ As witnesses 2. ___________________________
[Allow for additional parties as necessary].
Back to Main Menu
Print
Print Preview
Enter Data

## OHS Spec
Annexure 6
Occupational Health and Safety Specification
(OHSE SPEC)
Project Name: |  | KZN Public Works: 191 Prince Alfred Street
| Project Code: |  | 012345
| Agent Name: |  | Ms. L. Ntuli (Head Office)
| Region: |  | Southern Region
| District: |  | Pietermarizburg
| Ward no.: |  | ??
NOTE TO THE COMPILER OF THIS DOCUMENT : PLEASE INSERT PROJECT SPECIFIC HEALTH AND SAFETY SPECIFICATION AS RECEIVED FROM THE KZN DoPW OFFICIAL APPOINTED TO THE PROJECT OR AN APPOINTED PROFESSIONAL CONSTRUCTION HEALTH AND SAFETY AGENT.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## OHS Bill
Annexure 7
HEALTH AND SAFETY IMPLEMENTATION COSTING
Contractor to give a breakdown of his Health and Safety costs on this sheet.
ITEM | DESCRIPTION | UNIT | QUAN- TITY | MONTHS (Indicative) | RATE | AMOUNT
|  |  | (a) |  | (b) | (a) x (b)
1 | MEDICALS
1.1 | Pre-employment medical | Nr. | 0
1.2 | Re-medicals - yearly | Nr. | 0
TOTAL
2 | PERSONAL PROTECTIVE EQUIPMENT
2.1 | Overalls | Nr.
2.2 | Hard Hats | Nr.
2.3 | Safety boots/shoes | Nr.
2.4 | Gloves | Nr.
2.5 | Gumboots steel toe cap | Nr.
2.6 | Safety glasses | Nr.
2.7 | Reflector Bibs | Nr.
2.8 | Barricading Material | M
2.9 | Dust masks | Box 20
TOTAL
3 | FIRE FIGHTING
3.1 | Fire extinguishers - 4.5Kg | Nr.
3.2 | Surveys - Annual Service | Nr.
TOTAL
4 | HEALTH AND SAFETY PERSONNEL
4.1 | Safety Manager | Nr.
4.2 | Safety Officer | Nr.
4.3 | Construction Phase Safety, Health, Environmental and Waste Management Plan | Nr.
TOTAL
5 | FACILITIES
5.1 | Provision of ablution facilities | Nr.
5.2 | Service and maintenance of ablution facilities | Nr.
5.3 | Provision of eating areas | Nr.
5.4 | Cleaning of Lay down and other storage areas | Nr.
5.5 | Wash hand basin | Nr.
5.6 | Hot and Cold running water | Nr.
5.7 | Degreasing & Toilet soap | Nr.
TOTAL
6 | FALL PREVENTION / PROTECTION
6.1 | Safety harnesses with double lanyards | Nr.
6.2 | Safety harnesses with Scaffold hooks | Nr.
6.3 | Lifelines and vertical fall arrest systems | Nr.
6.4 | Scaffolding – material, erection and inspection (Estimate for project) | Nr.
6.5 | Temporary hand railing material and kick flats | Nr.
6.6 | Chin Straps | Nr.
TOTAL
7 | FIRST AID
7.1 | Replenishment of boxes and other supplies | Nr
TOTAL
8 | TRAINING
8.1 | SHE Representative | Nr.
8.2 | First Aid Level 1 | Nr.
8.3 | Fire Fighting | Nr.
TOTAL
9 | SIGNAGE
9.1 | All Signage as required by Law, regulatory, warning and information | Nr.
9.2 | Posters for awareness | Nr.
TOTAL
10 | ELECTRICAL
10.1 | Replacement of Locks required for lockouts | Nr.
10.2 | Replacement of tags | Nr.
10.3 | Replacement for Permit books | Nr.
10.4 | Replacement of Callipers | Nr.
TOTAL
11 | OTHERS (Project Specific)
11.1 |  | Nr.
TOTAL
GRAND TOTAL TO BE CARRIED TO THE PRELIMINARIES AND GENERAL IN BILL OF QUANTITIES
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## WaverofLien
Annexure 8
WAIVER OF CONTRACTOR'S LIEN
DEFINITIONS
Contractor:
Employer: | Head: Public Works (KZN Department of Public Works: Province of KwaZulu-Natal)
Agreement: | GCC FOR CONSTRUCTION WORKS - SECOND EDITION 2010
KZN Public Works: 191 Prince Alfred Street
Works (description):
Site: | Region: District Municipality: Local Municipality: Ward Nr.: Cluster Nr x:
AGREEMENT
The Contractor waives, in favour of the Employer, any lien or right of retention that is or may be held in respect of the Works to be executed on the Site
Thus done and signed at |  | on
[Date]
Name of signatory |  | Capacity of signatory
As witness |  | For and on behalf of the contractor who by signature hereof warrants authorisation hereto
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## EPWP
ADDITIONAL SPECIFICATION - EPWP
SL | EMPLOYMENT AND TRAINING OF EPWP BENEFICIARY ON THE EXPANDED PUBLIC WORKS PROGRAMME (EPWP) Infrastructure Projects:
CONTENTS | [5 empty] | Please do a print preview before printing
SL 01 | SCOPE
SL 02 | TERMINOLOGY AND DEFINITIONS
SL 03 | APPLICABLE LABOUR LAWS
SL 04 | EXTRACTS FROM MINISTERIAL DETERMINATION REGARDING EPWP
SL 05 | EMPLOYER’S RESPONSIBILITIES
SL 06 | PLACEMENT OF RECRUITED EPWP BENEFICIARY
SL 07 | TRAINING OF YOUTH WORKERS
SL 08 | BENEFICIARY (EPWP BENEFICIARY) SELECTION CRITERIA
SL 09 | CONTRACTUAL OBLIGATIONS IN RELATION TO EPWP BENEFICIARY
SL 10 | PROVINCIAL RATES OF PAY
SL 11 | MEASUREMENTS AND PAYMENT
EXAMPLE | EPWP EMPLOYMENT AGREEMENT
SL 01 | SCOPE
This project is part of the Expanded Public Works Programme aims to train young people and provide them with practical work experience as part of this programme. Youth aged between 18 and 35 will be recruited and trained in skills relevant to the work to be done on this project. These youth will have to be employed by the contractor as part of this project so that they can gain their work experience on these projects. The training of the youth will be coordinated and implemented by a separate service provider. This service provider will provide the contractor with a list of all the youth and the training each of these youth have received. The Contractor will be required to employ all of these youth for a minimum period of 6 months. Furthermore the Contractor will be required to supervise these youth to ensure that the work they perform is of the required standard. If necessary the contractor’s staff will be required to assist and mentor the youth to ensure that they are able to perform the type of work they need to do to the satisfactory standards required. The contractor will not be required to employ all youth in the programme at the same time, but may rotate the youth on the project, as long as all youth are employed for the minimum duration stated earlier.
This specification contains the standard terms and conditions for workers employed in elementary occupations and trained on a Expanded Public Works Programme (EPWP) for the Infrastructure Programme.
SL 02 | TERMINOLOGY AND DEFINITIONS
SL 02.01 | TERMINOLOGY
| (a) | EPWP | The Code of Good Practice for Expanded Public Works Programmes, which has been gazetted by the Department of Labour, and which provides for special conditions of employment for these EPWP projects. In terms of the Code of Good Practice, the workers on these projects are entitled to formal training, which will be provided by training providers appointed (and funded) by the Department of Labour. For projects of up to six months in duration, this training will cover life-skills and information about other education, training and employment opportunities.
| (b) | EPWP | Expanded Public Works Programme, a National Programme of the government of South Africa, approved by Cabinet.
| (c) | UYF | Umsobumvu Youth Fund.
| (d) | DOL | Department of Labour.
SL 02.02 | DEFINITIONS
| (a) | “employer” |  | means the contractor or any party employing the worker / beneficiary under the EPWP Programme.
| (b) | “client” |  | means the Department of Public Works.
| (c) | “ worker / trainee” |  | means any person working or training in an elementary occupation on a EPWP.
SL 03 | APPLICABLE LABOUR LAWS
In line with the Expanded Public Works Programme (EPWP) policies, the Ministerial Determination, Special Public Works Programmes, issued in terms of the Basic Conditions of Employment Act of 1997 by the Minister of labour in government Notice No. R63 of 25 January 2002, of which extracts have been reproduced below in clauses SL 04 shall apply to works described in the scope of work and which are undertaken by unskilled or semi-skilled workers. The Code of Good Practise for Employment and Conditions of Work for Expanded Public Works Programmes, issued in terms of the Basic Conditions of Employment Act of 1997 by the Minister of Labour in Government Notice No. R64 of 25 January 2002 shall apply to works described in the scope of work and which unskilled or semi-skilled workers undertake.
Sl 04 | EXTRACTS FROM MINISTERIAL DETERMINATION REGARDING EPWP
SL 04.01 | DEFINITIONS
| (a) | “department” means any department of the State, implementing agent or contractor;
| (b) | “employer” means any department that hires workers to work in elementary occupations on a EPWP;
| (c) | “worker” means any person working in an elementary occupation on a EPWP;
| (d) | “elementary occupation” means any occupation involving unskilled or semi-skilled work;
| (e) | “management” means any person employed by a department or implementing agency to administer or execute a EPWP;
| (f) | “task” means a fixed quantity of work;
| (g) | “task-based work” means work in which a worker is paid a fixed rate for performing a task;
| (h) | “task-rated worker” means a worker paid on the basis of the number of tasks completed;
| (i) | “time-rated worker” means a worker paid on the basis of the length of time worked
| (j) | “Service Provider” means the consultant appointed by Department to coordinate and arrange the employment and training of labour on EPWP infrastructure projects.
SL 04.02 | TERMS OF WORK
| (a) | Workers on a EPWP are employed on a temporary basis.
| (b) | A worker may NOT be employed for longer than 24 months in any five-year cycle on a EPWP.
| (c) | Employment on a EPWP does not qualify as employment and a worker so employed does not have to register as a contributor for the purposes of the Unemployment Insurance Act 30 of 1966.
SL 04.03 | NORMAL HOURS OF WORK
| (a) | An employer may not set tasks or hours of work that require a worker to work–
(i) more than forty hours in any week
(ii) on more than five days in any week; and
(iii) for more than eight hours on any day.
| (b) | An employer and a worker may agree that the worker will work four days per week. The worker may then work up to ten hours per day.
| (c) | A task-rated worker may not work more than a total of 55 hours in any week to complete the tasks (based on a 40-hour week) allocated to him.
Every work is entitled to a daily rest period of at least eight consecutive hours. The daily rest period is measured from the time the worker ends work on one day until the time the worker starts work on the next day.
SL 04.04 | MEAL BREAKS
| (a) | A worker may not work for more than five hours without taking a meal break of at least thirty minutes duration.
| (b) | An employer and worker may agree on longer meal breaks.
| (c) | A worker may not work during a meal break. However, an employer may require a worker to perform duties during a meal break if those duties cannot be left unattended and cannot be performed by another worker. An employer must take reasonable steps to ensure that a worker is relieved of his or her duties during the meal break.
SL 04.05 | SPECIAL CONDITIONS FOR SECURITY GUARDS
| (a) | A security guard may work up to 55 hours per week and up to eleven hours per day.
| (b) | A security guard who works more than ten hours per day must have a meal break of at least one hour duration or two breaks of at least 30 minutes duration each.
SL 04.06 | DAILY REST PERIOD
Every worker is entitled to a daily rest period of at least eight consecutive hours. The daily rest period is measured from the time the worker ends work on one day until the time the worker starts work on the next day.
SL 04.07 | WEEKLY REST PERIOD
Every worker must have two days off every week. A worker may only work on their day off to perform work which must be done without delay and cannot be performed by workers during their ordinary hours of work (“emergency work”).
SL 04.08 | WORK ON SUNDAYS AND PUBLIC HOLIDAYS
| (a) | A worker may only work on a Sunday or public holiday to perform emergency or security work.
| (b) | Work on Sundays is paid at the ordinary rate of pay.
| (c) | A task-rated worker who works on a public holiday must be paid –
|  | (i) | the worker’s daily task rate, if the worker works for less than four hours;
|  | (ii) | double the worker’s daily task rate, if the worker works for more than four hours.
| (d) | A time-rated worker who works on a public holiday must be paid –
|  | (i) | the worker’s daily rate of pay, if the worker works for less than four hours on the public holiday;
|  | (ii) | double the worker’s daily rate of pay, if the worker works for more than four hours on the public holiday.
SL 04.09 | SICK LEAVE
| (a) | Only workers who work four or more days per week have the right to claim sick-pay in terms of this clause.
| (b) | A worker who is unable to work on account of illness or injury is entitled to claim one day’s paid sick leave for every full month that the worker has worked in terms of a contract.
| (c) | A worker may accumulate a maximum of twelve days' sick leave in a year.
| (d) | Accumulated sick-leave may not be transferred from one contract to another contract.
| (e) | An employer must pay a task-rated worker the worker’s daily task rate for a day’s sick leave.
| (f) | An employer must pay a time-rated worker the worker’s daily rate of pay for a day’s sick leave.
| (g) | An employer must pay a worker sick pay on the worker’s usual payday.
| (h) | Before paying sick-pay, an employer may require a worker to produce a certificate stating that the worker was unable to work on account of sickness or injury if the worker is –
|  | (i) | absent from work for more than two consecutive days; or
|  | (ii) | absent from work on more than two occasions in any eight-week period.
| (i) | A medical certificate must be issued and signed by a medical practitioner, a qualified nurse or a clinic staff member authorised to issue medical certificates indicating the duration and reason for incapacity.
| (j) | A worker is not entitled to paid sick-leave for a work-related injury or occupational disease for which the worker can claim compensation under the Compensation for Occupational Injuries and Diseases Act.
SL 04.10 | MATERNITY LEAVE
| (a) | A worker may take up to four consecutive months’ unpaid maternity leave.
| (b) | A worker is not entitled to any payment or employment-related benefits during maternity leave.
| (c) | A worker must give her employer reasonable notice of when she will start maternity leave and when she will return to work.
| (d) | A worker is not required to take the full period of maternity leave. However, a worker may not work for four weeks before the expected date of birth of her child or for six weeks after the birth of her child, unless a medical practitioner, midwife or qualified nurse certifies that she is fit to do so.
| (e) | A worker may begin maternity leave –
|  | (i) | four weeks before the expected date of birth; or
|  | (ii) | on an earlier date –
|  |  | (1) | if a medical practitioner, midwife or certified nurse certifies that it is necessary for the health of the worker or that of her unborn child; or
|  |  | (2) | if agreed to between employer and worker; or
|  | (iii) | on a later date, if a medical practitioner, midwife or certified nurse has certified that the worker is able to continue to work without endangering her health.
| (f) | A worker who has a miscarriage during the third trimester of pregnancy or bears a stillborn child may take maternity leave for up to six weeks after the miscarriage or stillbirth.
| (g) | A worker who returns to work after maternity leave, has the right to start a new cycle of twenty-four months employment, unless the EPWP on which she was employed has ended.
SL 04.11 | FAMILY RESPONSIBILITY LEAVE
| (a) | Workers, who work for at least four days per week, are entitled to three days paid family responsibility leave each year in the following circumstances -
|  | (i) | when the employee’s child is born;
|  | (ii) | when the employee’s child is sick;
|  | (iii) | in the event of the death of –
|  |  | (1) | the employee’s spouse or life partner
|  |  | (2) | the employee’s parent, adoptive parent, grandparent, child, adopted child, grandchild or sibling
SL 04.12 | STATEMENT OF CONDITIONS
| (a) | An employer must give a worker a statement containing the following details at the start of employment –
|  | (i) | the employer’s name and address and the name of the EPWP;
|  | (ii) | the tasks or job that the worker is to perform;
|  | (iii) | the period for which the worker is hired or, if this is not certain, the expected duration of the contract;
|  | (iv) | the worker’s rate of pay and how this is to be calculated;
|  | (v) | the training that the worker may be entitled to receive during the EPWP.
| (b) | An employer must ensure that these terms are explained in a suitable language to any employee who is unable to read the statement.
| (c) | An employer must supply each worker with a copy of the relevant conditions of employment contained in this specification.
| (d) | An employer must enter into a formal contract of employment with each employee. A copy of a pro-forma is attached at the end of this specification.
SL 04.13 | KEEPING RECORDS
| (a) | Every employer must keep a written record of at least the following –
|  | (i) | the worker’s name and position;
|  | (ii) | in the case of a task-rated worker, the number of tasks completed by the worker;
|  | (iii) | in the case of a time-rated worker, the time worked by the worker;
|  | (iv) | payments made to each worker.
| (b) | The employer must keep this record for a period of at least three years after the completion of the EPWP.
SL 04.14 | PAYMENT
| (a) | A task-rated worker will only be paid for tasks that have been completed.
| (b) | An employer must pay a task-rated worker within five weeks of the work being completed and the work having been approved by the manager or the contractor having submitted an invoice to the employer. Payment must be made in cash, by cheque or by direct deposit into a bank account designated by the worker.
| (c) | A time-rated worker will be paid at the end of each month and payment must be made in cash, by cheque or by direct deposit into a bank account designated by the worker.
| (d) | Payment in cash or by cheque must take place –
|  | (i) | at the workplace or at a place agreed to by at least 75% of the workers; and
|  | (ii) | during the worker’s working hours or within fifteen minutes of the start or finish of work;
| (e) | All payments must be enclosed in a sealed envelope which becomes the property of the worker.
| (f) | An employer must give a worker the following information in writing –
|  | (i) | the period for which payment is made;
|  | (ii) | the number of tasks completed or hours worked;
|  | (iii) | the worker’s earnings;
|  | (iv) | any money deducted from the payment;
|  | (v) | the actual amount paid to the worker.
| (g) | If the worker is paid in cash or by cheque, this information must be recorded on the envelope and the worker must acknowledge receipt of payment by signing for it.
| (h) | If a worker’s employment is terminated, the employer must pay all monies owing to that worker within one month of the termination of employment.
SL 04.15 | DEDUCTIONS
| (a) | An employer may not deduct money from a worker’s payment unless the deduction is required in terms of a law.
| (b) | An employer must deduct and pay to the SA Revenue Services any income tax that the worker is required to pay.
| (c) | An employer who deducts money from a worker’s pay for payment to another person must pay the money to that person within the time period and other requirements specified in the agreement law, court order or arbitration award concerned.
| (d) | An employer may not require or allow a worker to –
|  | (i) | repay any payment except an overpayment previously made by the employer by mistake;
|  | (ii) | state that the worker received a greater amount of money than the employer actually paid to the worker; or
|  | (iii) | pay the employer or any other person for having been employed.
SL 04.16 | HEALTH AND SAFETY
| (a) | Employers must take all reasonable steps to ensure that the working environment is healthy and safe and that all legal requirements regarding health and safety are strictly adhered to.
| (b) | A worker must:
|  | (i) | work in a way that does not endanger his/her health and safety or that of any other person;
|  | (ii) | obey any health and safety instruction;
|  | (iii) | obey all health and safety rules;
|  | (iv) | use any personal protective equipment or clothing issued by the employer;
|  | (v) | report any accident, near-miss incident or dangerous behaviour by another person to their employer or manager.
SL 04.17 | COMPENSATION FOR INJURIES AND DISEASES
| (a) | It is the responsibility of employers to arrange for all persons employed on a EPWP to be covered in terms of the Compensation for Occupational Injuries and Diseases Act, 130 of 1993.
| (b) | A worker must report any work-related injury or occupational disease to their employer or manager.
| (c) | The employer must report the accident or disease to the Compensation Commissioner.
| (d) | An employer must pay a worker who is unable to work because of an injury caused by an accident at work 75% of their earnings for up to three months. The employer will be refunded this amount by the Compensation Commissioner. This does NOT apply to injuries caused by accidents outside the workplace such as road accidents or accidents at home.
SL 04.18 | TERMINATION
| (a) | The employer may terminate the employment of a worker provided he has a valid reason and after following existing termination procedures.
| (b) | A worker will not receive severance pay on termination.
| (c) | A worker is not required to give notice to terminate employment. However, a worker who wishes to resign should advise the employer in advance to allow the employer to find a replacement.
| (d) | A worker who is absent for more than three consecutive days without informing the employer of an intention to return to work will have terminated the contract. However, the worker may be re-engaged if a position becomes available for the balance of the 24-month period.
| (e) | A worker who does not attend required training events, without good reason, will have terminated the contract. However, the worker may be re-engaged if a position becomes available for the balance of the 24-month period.
SL 04.19 | CERTIFICATE OF SERVICE
| (a) | On termination of employment, a worker is entitled to a certificate stating –
|  | (i) | the worker’s full name;
|  | (ii) | the name and address of the employer;
|  | (iii) | the SPWP on which the worker worked;
|  | (iv) | the work performed by the worker;
|  | (v) | any training received by the worker as part of the EPWP;
|  | (vi) | the period for which the worker worked on the EPWP;
|  | (vii) | any other information agreed on by the employer and worker.
SL 05 | EMPLOYER’S RESPONSIBILITIES
The employer shall adhere to the conditions of employment as stipulated in the Code of Good Practice for Employment and Conditions of Work for Expanded Public Works Programmes. Over and above the conditions stipulated above, he shall be responsible to:
| (a) | formulate and design a contract between himself/ herself and each of the recruited EPWP beneficiary, ensuring that the contract does not contravene any of the Acts stipulated in South African Law, e.g. Basic Conditions of Employment Act, etc. (A copy of a pro-forma contract is attached at the end of this specification);
| (b) | screen and select suitable candidates for employment from the priority list of EPWP beneficiary provided by the Umsobumvu Youth Fund (UYF);
| (c) | ensure that the recruited EPWP beneficiary are made available to receive basic life skills training which will be conducted and paid for by the Umsobumvu Youth Fund;
| (d) | ensure that all EPWP beneficiary receive instruction on safety on site prior to them commencing with work on site;
| (e) | ensure that all EPWP beneficiary are covered under workmen’s compensation for as long as they are contracted to the contractor. Payment to the Compensation Commissioner shall be the responsibility of the contractor;
| (f) | assist in the identification and assessment of potential EPWP beneficiary to undergo advanced technical training in respective trades;
| (g) | test and implement strict quality control and to ensure that the health and safety regulations are adhered to;
| (h) | provide all EPWP beneficiary with the necessary protective clothing as required by law for the specific trades that they are involved in.
| (i) | provide overall supervision and day-to-day management of EPWP beneficiary and/or sub-contractors; and
| (j) | ensure that all EPWP beneficiary are paid their wages on time through a pre-agreed payment method as stipulated in the contract with the EPWP beneficiary.
SL 06 | PLACEMENT OF RECRUITED EPWP BENEFICIARY
Employers will be contractually obliged to:
| (a) | employ EPWP beneficiary from targeted social groups from the priority list provided by the Service Provider/ Umsobumvu Youth Fund.
| (b) | facilitate on-the-job training and skills development programmes for the EPWP beneficiary;
| (c) | achieve the following minimum employment targets:
|  | (i) | 55% people between the ages of 18 and 35
|  | (ii) | 55% women;
|  | (iii) | 2% people with disabilities.
| (d) | brief EPWP beneficiary on the conditions of employment as specified in sub clause SL 04.09 above;
| (e) | enter into a contract with each EPWP beneficiary, which contract will form part of the Employment Agreement;
| (f) | allow EPWP beneficiary the opportunity to attend life skills training through DOL. This shall be arranged at the beginning of the contract;
| (g) | ensure that payments to EPWP beneficiary are made as set out in sub clauses SL 04.14 and SL 04.15 above.
| (h) | set up of personal profile files as prescribed by EPWP beneficiary and as set out in sub clause SL 04.13 above.
| (i) | in addition to (h) |  |  | - a copy of the I.D;
- qualifications;
- career progress;
- EPWP Employment Agreement, and
- list of small trade tools;
must be included in the EPWP beneficiary's personal profile file.
SL 07 | TRAINING OF EPWP BENEFICIARY
Three types of training are applicable, namely
· Life skills;
· On the job training and
· Technical Skills training.
Training will be implemented by training instructors accredited by DOL and/or CETA :
· EPWP beneficiary shall be employed on the projects for an average of 6 months.
· EPWP beneficiary shall be deployed on projects in the vicinity of their homes. The same arrangements as for other workers regarding accommodation, subsistence and travel shall be applicable to EPWP beneficiary.
| (a) | Life skills training
All EPWP beneficiary are entitled to undergo life skills training. Training of this module will be flexible enough to meet the needs of the employer. Training should take place immediately after site hand-over and during the period of site establishment and pre-planning before actual construction starts, alternatively this will be spread over the duration of the contract period. The contractor will be required to work closely with the person to schedule the training sessions so that the timing of the training is aligned with the contractors work schedule and his demand for workers.
| (b) | On-the job training
The Employer shall provide EPWP beneficiary with on-the-job training to enable them to fulfil their employment requirements. The employer shall also be expected to closely monitor the job performance of EPWP beneficiary and shall identify potential EPWP beneficiary for skills development programmes.
| (c) | Technical skills training
The Employer shall assist in identifying EPWP beneficiary for further training. These EPWP beneficiary will undergo further technical training to prepare them for opportunities as semi-skilled labourers.
Such training will comprise of an off-site theoretical component and practical training on-site. The contractor will be responsible for on-site practical work under his supervision. EPWP beneficiary who graduate from the first phase of the training programme will be identified and given opportunities to register for skills development programmes. These can ultimately result in a accredited qualification. The programme will consist of theoretical instruction away from the construction site as well as on-site practical work under the supervision of the employer. Candidates will be entitled to employment to complete all training modules.
SL 08 | BENEFICIARY (EPWP BENEFICIARY) SELECTION CRITERIA
SL 08.01 | PREAMBLE
The Code of Good Practise for Employment and Conditions of Work for Expanded Public Works Programmes encourages:
· optimal use of locally-based labour in a Expanded Public Works Programme (EPWP);
· a focus on targeted groups which consist of namely youth, consisting of women, female- headed households, disabled and households coping with HIV/AIDS; and
· the empowerment of individuals and communities engaged in a SPWP through the provision of training.
SL 08.02 | BENEFICIARY (EPWP BENEFICIARY) SELECTION CRITERIA
| (a) | The EPWP beneficiary of the programmes should preferably be non-working individuals from the most vulnerable sections of disadvantaged communities who do not receive any social security pension income. The local community must, through all structures available, be informed of and consulted about the establishment of any EPWP
| (b) | In order to spread the benefit as broadly as possible in the community, a maximum of one person per household should be employed, taking local circumstances into account.
| (c) | Skilled artisans from other areas may be employed if they have skills that are required for a project and there are not enough persons in the local communities who have those skills or who could undergo appropriate skills training. However, this should not result in more than 20% of persons working on a programme not being from local communities.
| (d) | Programmes should set participation targets for employment with respect to youth, single male- and female-headed households, women, people with disabilities, households coping with HIV/AIDS, people who have never worked, and those in long-term unemployment.
| (e) | The proposed targets as set out in sub clause SL 06 (c)
· 55% youth from 18 to 35 years of age;
· 55% women;
· 2% disabled.
SL 09 | CONTRACTUAL OBLIGATIONS IN RELATION TO YOUTH LABOUR
The EPWP beneficiary to be employed in the programme (EPWP) shall be directly contracted to the employer. Over and above the construction and project management responsibilities, the employer will be expected to perform the tasks and responsibilities as set out in clause SL 05 above.
SL 10 | PROVINCIAL RATES OF PAY
It is stipulated that youth workers on the EPWP receive a minimum of R 1 000 per month whilst working and R 600 per month whilst on training in ALL provinces. Should EPWP beneficiary be attending training whilst employed by the contractor, the contractor will still be responsible for payment to the EPWP beneficiary whilst at training.
SL 11 | MEASUREMENTS AND PAYMENT
The number of EPWP beneficiary specified for this contract that will receive life skills training is 50 and technical training is 50
SL 11.01 | PAYMENT FOR TRAINING OF EPWP BENEFICIARY
(TARGET:- 50 EPWP BENEFICIARY)
SL 11.01.01 | Skills development and Technical training for EPWP beneficiary for an average of 10 days ……(Prov.Sum)…………..…..Unit: R/EPWP beneficiary
The above item is only applicable if DoL does not fund the Technical Training PRIOR to site handover.
SL 11.01.02 | Penalty due to not meeting the target as in SL 11.01.01….………………………………………………………..Unit: EPWP beneficiary
LESS R 2000 per EPWP beneficiary
SL 11.02 | PAYMENT FOR TRAVELLING AND ACCOMMODATION DURING OFF-SITE TRAINING
SL 11.02.01 | Life skills training for 26 days:
| 01 | Travelling (based on 50 km/EPWP beneficiary) …………………………………….Unit: km
| 02 | Accommodation……………………………………..(Prov.Sum)…..Unit: R/EPWP beneficiary
| 03 | Profit and attendance………………………………………………………………. Unit: %
SL 11.02.02 | Skilled development and Technical training:
| 01 | Travelling (based on 50 km/EPWP beneficiary)……………………………………...Unit: km
| 02 | Accommodation……………………………………….(Prov.Sum)….Unit: R/EPWP beneficiary
| 03 | Profit and attendance …………………………………………………………….. Unit: %
The units of measurement for sub items SL 11.02.01 (01) and SL 11.02.02 (01) above shall be the distance travelled in km by the EPWP beneficiary trained off site. The tendered rate shall include full compensation to safely transport the youth workers to and from the training venue/s.
The unit of measurement for sub items SL 11.02.01 (02) and SL 11.02.02 (02) above shall be the amounts in Rand expended for accommodation and daily meal allowances for the EPWP beneficiary trained off site that must be arranged by the contractor. Amounts quoted shall be corrected according to re-measurement based on actual invoices.
The tendered percentages under sub items SL 11.02.01 (03) and SL 11.02.02 (03) will be paid to the contractor on the value of each payment pertaining to the accommodation and advance meal allowances to cover his expenses in this regard.
SL 11.03 | ALTERNATIVE WORKERS FOR THE PERIOD OF OFF-SITE TRAINING
SL 11.03.01 | Life skills training for 26 days ………………………………………………. Unit: worker-days
SL 11.03.02 | Skilled development and Technical training for EPWP beneficiary for (…….) days………………………………………………………….. Unit: worker-days
The unit of measurement shall be the number of EPWP beneficiary replaced while in training multiplied by the number of days absent from the site.
The rates tendered shall include full compensation for additional replacement labour during periods of off-site training.
SL 11.04 | EMPLOYMENT OF EPWP BENEFICIARY
SL 11.04.01 | Employment of EPWP beneficiary……………………………...(Prov.Sum)¼.Unit: R/ worker-month
SL 11.04.02 | Employment of EPWP beneficiary……………………………...(Prov.Sum)¼.Unit: R/ worker-month
The unit of measurement shall be the number of EPWP beneficiary at the statutory labour rates of R ………. multiplied by the period employed in months and the rate tendered shall include full compensation for all costs associated with the employment of EPWP beneficiary and for complying with the conditions of contract. The cost for the training shall be excluded from this item. This item is based on 6 months appointment for EPWP beneficiary.
SL 11.05 | PROVISION OF EPWP DESIGNED OVERALLS TO EPWP BENEFICIARY
SL 11.05.01 | Supply EPWP designed overalls to EPWP beneficiary …………………………….………………….. (Prov.Sum)…………….Unit: R
EPWP beneficiary overalls should be orange (top and bottom) as per EPWP specification with the exception of Correctional Services contracts where the EPWP beneficiary top would be blue and the bottom orange.
SL 11.05.02 | Profit and attendance……………………………………………………………………... Unit: %
An amount has been provided in the Schedule of Quantities under sub item SL 10.05.01 for the supply of EPWP designed overalls, as per the specification provided by the EPWP unit, arranged by the Service Provider. The Engineer will have sole authority to spend the amounts or part thereof. The tendered percentage under sub items SL 10.05.02 will be paid to the contractor on the value of each payment pertaining to the supply of overalls to cover his expenses in this regard.
SL 11.06 | PROVISION OF SMALL TOOLS FOR EPWP BENEFICIARY
SL 11.06.01 | Provide all EPWP beneficiary with prescribed tools for their respective trades. Specification for the mentioned tools to be provided by the EPWP Service Provider. These tools will become the property of the EPWP beneficiary after the completion of the programme............................................................(Prov.Sum)….Unit: R 500-00 /youth worker
SL 11.06.02 | Profit and attendance……………………………………………………………………... Unit: %
SL 11.07 | APPOINTMENT OF EPWP BENEFICIARY TEAM LEADER/S
SL 11.07.01 | Appointment of (_____) EPWP beneficiary team leader/s for the duration of the contract……………………………………….(Prov.Sum)……..... Unit: R / EPWP beneficiary team leader
The EPWP beneficiary Team Leader will act as CLO/PLO to facilitate the project work between the EPWP beneficiary and the contractor. Umsobumvu Youth Fund can assist with the sourcing of EPWP beneficiary Team Leader for employment by the contractor.
SL 11.08 | LIAISON WITH SERVICE PROVIDER ………………………………………………….Unit: hours
The tendered rate shall include full compensation for the cost of liaising with the Service Provider and Social Facilitators on all issues regarding the works.
Back to Main Menu
Print
Print Preview
Enter Data

## EPWP BQ
PAGE NO | ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
1 |  | BILL NO 2
1 |  | EMPLOYMENT AND TRAINING OF LABOUR ON THE EPWP BENEFICIARY INFRASTRUCTURE PROJECTS
1 |  | PREAMBLES
1 |  | Tenderers are advised to study the Additional Specification SL:
Employment and training of Labour on the Expanded Public
Works Programme (EPWP) Infrastructure Projects
as bound elsewhere in the Bills of Quantities and
then price this Bill accordingly
1 |  | TRAINING OF EPWP BENEFICIARY
1 |  | (TARGET: 50 EPWP BENEFICIARY)
1 |  | Skills development and Technical training:
1 | 1 | Skills development and technical training for EPWP beneficiary | Item | 1
for an average of 10 days (ref. SL11.01.01)
1 | 2 | Penalty due to not meeting the target as in SL 11.01.02 | Y/Work | 2000
1 |  | TRAVELLING AND ACCOMMODATION DURING OFF
SITE TRAINING:
1 |  | Life skills training for 26 days (ref. SL 11.02.01)
1 | 3 | Travelling (based on 50km/EPWP beneficiary) | km | 2500
1 | 4 | Profit and attendance on Items 1, 2 & 3 | %
1 |  | EMPLOYMENT OF EPWP BENEFICIARY
1 | 5 | Employment of EPWP beneficiary (30 youth) [New Office Block] | Item | 1
1 |  | The unit of measurement shall be the number of EPWP beneficiary
at the statutory labour rates of R 100/day multiplied by the
period employed in months and the rate tendered shall include
full compensation for all costs associated with the employment
of EPWP beneficiary and for complying with the conditions of
contract. The cost for training shall be excluded from this item.
This item is based on 6 months appointment for EPWP beneficiary
1 | 6 | Employment of EPWP beneficiary(40 youth) [Parking garage] | Item | 1
TOTAL CARRIED TO SUMMARY
|  |  | UNIT | QUANTITY | RATE | AMOUNT
2 |  | The unit of measurement shall be the number of EPWP beneficiary
at the statutory labour rates of R 110/day multiplied by the
period employed in months and the rate tendered shall include
full compensation for all costs associated with the employment
of EPWP beneficiary and for complying with the conditions of
contract. The cost for training shall be excluded from this item.
This item is based on 12 months appointment for EPWP beneficiary
2 | 7 | Employment of EPWP beneficiary (30 youth) [Conference Centre & Canteen] | Item | 1
2 |  | The unit of measurement shall be the number of EPWP beneficiary
at the statutory labour rates of R 120/day multiplied by the
period employed in months and the rate tendered shall include
full compensation for all costs associated with the employment
of EPWP beneficiary and for complying with the conditions of
contract. The cost for training shall be excluded from this item.
This item is based on 12 months appointment for EPWP beneficiary
2 |  | PROVISION OF EPWP DESIGNED OVERALLS TO
YOUTH WORKERS
2 | 8 | Supply EPWP designed overalls to EPWP beneficiary (ref. SL | Item | 1
11.05.01) for 100 workers
2 | 9 | Profit and attendance on Items 5 - 8 (ref. SL 11.05.02) | % | 7.5
2 |  | PROVISION OF SMALL TOOLS FOR
EPWP BENEFICIARY
2 | 10 | Supply of small tools to EPWP beneficiary. Specification to be | Item | 1
supplied by the EPWP-NYS Serviced Provider for the
respective trades (ref. SL 11.06.01) for 100 workers
2 | 11 | Profit and attendance (ref. SL 11.06.02) | % | 7.5
2 |  | APPOINTMENT OF YOUTH TEAM LEADERS
2 | 12 | Appointment of EPWP beneficiary Team Leaders for the duration of the | Item | 1
contract (ref. SL 11.07)
2 | 13 | Liaison with Service Provider (ref. SL 11.08) | Hrs | 30
2 | 14 | Profit and attendance on Items 12 & 13 | % | 7.5
FINAL TOTAL CARRIED TO PRELIMINARY AND GENERAL IN BILL OF QUANTITIES
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## EPWPScope
SCOPE OF WORKS IN RESPECT OF WORK RELATING TO THE EXTENDEND PUBLIC WORKS PROGRAMME (EPWP)
Project title: |  |  | KZN Public Works: 191 Prince Alfred Street
Project Code: |  |  | 012345 |  | EPWP NO: |  | N/A
Introductory notes:
1. | The works, or parts of the works will be constructed using labour-intensive methods only in terms of this specification. The use of plant to provide such works, other than plant specifically provided for in the scope of work, is a variation to the contract. The items marked with the letters LI are not necessarily an exhaustive list of all the activities which must be done by hand, and this clause does not over-ride any of the requirements in the generic labour intensive specification in the Scope of Works.
2. | Payment for items which are designated to be constructed labour-intensively (either in this schedule or in the Scope of Works) will not be made unless they are constructed using labour-intensive methods. Any unauthorised use of plant to carry out work which was to be done labour-intensively will not be condoned and any works so constructed will not be certified for payment.
DESCRIPTION OF THE WORKS
Employer's objectives
The employer’s objectives are to deliver public infrastructure using labour-intensive methods in accordance with EPWP Guidelines.
Labour-intensive works
Labour-intensive works comprise the activities described in the Labour-Intensive Specification. Labour-intensive works shall be constructed/maintained using local workers who are temporarily employed in terms of the scope of work.
LABOUR-INTENSIVE COMPETENCIES OF SUPERVISORY AND MANAGEMENT STAFF
Contractors shall only engage supervisory and management staff in labour-intensive works that have completed the skills programme including Foremen/ Supervisors at NQF level 4 “National Certificate: Supervision of Civil Engineering Construction Processes” and Site Agent/ Manager at NQF level 5 "Manage Labour-Intensive Construction Processes" or equivalent QCTO qualifications (See Appendix C). at NQF outlined in Table 1. (See GUIDELINES FOR THE IMPLEMENTATION OF LABOUR-INTENSIVE INFRASTRUCTURE PROJECTS UNDER THE EXPANDED PUBLIC WORKS PROGRAMME (EPWP) -THIRD EDITION 2015)
Emerging contractors shall have personally completed, or be registered on a skills programme for the NQF level 2 unit standard. All other site supervisory staff in the employ of emerging contractors must have completed, or be registered on a skills programme for the NQF level 2 unit standards or NQF level 4 unit standards. Table 1: Skills programme for supervisory and management staff.
Table 1: Skills programme for supervisory and management staff
Personnel |  |  | NQF level | Unit standard titles |  | Skills programme description
Team leader / supervisor |  |  | 2 | Apply Labour-Intensive Construction Systems and Techniques to Work Activities |  | This unit standard must be completed, and
Use Labour-Intensive Construction Methods to Construct and Maintain Roads and Storm water Drainage
Use Labour-Intensive Construction Methods to Construct and Maintain Water and Sanitation Services
any one of these 3 unit standards
Use Labour-Intensive Construction Methods to Construct, Repair and Maintain structures
Personnel |  |  | NQF level | Unit standard titles |  | Skills programme description
Foreman/supervisor |  |  | 4 | Implement Labour-Intensive Construction Systems and Techniques |  | This unit standard must be completed, and
|  |  |  | Use Labour-Intensive Construction Methods to Construct and Maintain Roads and Storm water Drainage |  | any one of these 3 unit standards
Use Labour-Intensive Construction Methods to Construct and Maintain Water an Sanitation Services
Use Labour-Intensive Construction Methods to Construct, Repair and Maintain structures
Site Agent /Manager (i.e. the contractor's most senior representative that is resident on the site) |  |  | 5 | Manage Labour-Intensive Construction Processes |  | Skills Programme against this single unit standard
Details of these skills programmes may be obtained from the CETA ETQA manager (e-mail :gerard@ceta.co.za , tel: 011-265 5900)
EMPLOYMENT OF UNSKILLED AND SEMI-SKILLED WORKERS IN LABOUR­INTENSIVE WORKS
1.1 | Requirements for the sourcing and engagement of labour.
1.1.1 | Unskilled and semi-skilled labour required for the execution of all labour-intensive works shall be engaged strictly in accordance with prevailing legislation and SANS 1914-5, Participation of Targeted Labour.
1.1.2 | The rate of pay set for the SPWP per task or per day will be an acceptable rate determined by the Department of Labour.
1.1.3 | Tasks established by the contractor must be such that:
| a) | the average worker completes 5 tasks per week in 40 hours or less; and
| b) | the weakest worker completes 5 tasks per week in 55 hours or less.
1.1.4 | The contractor must revise the time taken to complete a task whenever it is established that the time taken to complete a weekly task is not within the requirements of 1.1.3.
1.1.5 | The Contractor shall, through all available community structures, inform the local community of the labour-intensive works and the employment opportunities presented thereby. Preference must be given to people with previous practical experience in construction and / or who come from households:
| a) | where the head of the household has less than a primary school education;
| b) | that have less than one full time person earning an income;
| c) | where subsistence-agriculture is the source of income.
| d) | that who are not in receipt of any social security pension income
1.1.6 | The Contractor shall endeavour to ensure that the expenditure on the employment of unskilled and semi-skilled workers is in the following proportions:
| a) | 55% women;
| b) | 55% youth who are between the ages of 18 and 35; and
| c) | 2% on persons with disabilities.
1.2 | Specific provisions pertaining to SANS 1914-5
| 1.2.1 | Definitions
Targeted labour: Unemployed persons who are employed as local labour on the project.
| 1.2.2 | Contract participation goals
|  | 1.2.2.1 | There is no specified contract participation goal for the contract. The contract participation goal shall be measured in the performance of the contract to enable the employment provided to targeted labour to be quantified.
|  | 1.2.2.2 | The wages and allowances used to calculate the contract participation goal shall, with respect to both time-rated and task rated workers, comprise all wages paid and any training allowance paid in respect of agreed training programmes.
| 1.2.3 | Terms and conditions for the engagement of targeted labour
Further to the provisions of clause 3.3.2 of SANS 1914-5, written contracts shall be entered into with targeted labour.
| 1.2.4 | Terms and conditions for the engagement of targeted labour
Further to the provisions of clause 3.3.2 of SANS 1914-5, written contracts shall be entered into with targeted labour.
| 1.2.5 | Variations to SANS 1914-5
|  | 1.2.5.1 | The definition for net amount shall be amended as follows:
Financial value of the contract upon completion, exclusive of any value added tax or sales tax which the law requires the employer to pay the contractor.
|  | 1.2.5.2 | The schedule referred to in 5.2 shall in addition reflect the status of targeted labour as women, youth and persons with disabilities and the number of days of formal training provided to targeted labour.
1.3 | Training of targeted labour
| 1.3.1 | The contractor shall provide all the necessary on-the-job training to targeted labour to enable such labour to master the basic work techniques required to undertake the work in accordance with the requirements of the contract in a manner that does not compromise worker health and safety.
| 1.3.2 | The cost of the formal training of targeted labour, will be funded by the local office of the Department of Labour. This training will take place as close to the project site as practically possible. The contractor must access this training by informing the relevant regional office of the Department of Labour in writing, within 14 days of being awarded the contract, of the likely number of persons that will undergo training and when such training is required. The Employer and the Department of Public Works (Fax: 012 3258625/ EPWP Unit, Private Bag X65, Pretoria 0001) must be furnished with a copy of this request.
| 1.3.3 | The contractor shall do nothing to dissuade targeted labour from participating in training programmes and shall take all reasonable steps to ensure that each beneficiary is provided with two days of formal training for every 22 days worked.
| 1.3.4 | An allowance equal to 100% of the task rate or daily rate shall be paid by the contractor to workers who attend formal training, in terms of the above.
| 1.3.5 | Proof of compliance with the above requirements must be provided by the Contractor to the Employer prior to submission of the final payment certificate.
GENERIC LABOUR-INTENSIVE SPECIFICATION
1 | Scope
This specification establishes general requirements for activities which are to be executed by hand involving the following:
| a) | trenches having a depth of less than 1.5 metres
| b) | storm water drainage
| c) | low-volume roads and sidewalks
2 | Precedence
Where this specification is in conflict with any other standard or specification referred to in the Scope of Works to this Contract, the requirements of this specification shall prevail.
3 | Hand excavateable material
Hand excavateable material is material:
| a) | Granular materials:
| i) | whose consistency when profiled may in terms of table 1 be classified as very loose, loose, medium dense, or dense; or
| ii) | where the material is a gravel having a maximum particle size of 10mm and contains no cobbles or isolated boulders, no more than 15 blows of a dynamic cone penetrometer is required to penetrate 100mm;
| b) | Cohesive materials:
| i) | whose consistency when profiled may in terms of table 1 be classified as very soft, soft, firm, stiff and stiff / very stiff; or
| ii) | where the material is a gravel having a maximum particle size of 10mm and contains no cobbles or isolated boulders, no more than 8 blows of a dynamic cone penetrometer is required to penetrate 100mm;
| Note: |  | 1) A boulder, a cobble and gravel is material with a particle size greater than 200mm, between 60 and 200mm.
2) A dynamic cone penetrometer is an instrument used to measure the in-situ shear resistance of a soil comprising a drop weight of approximately 10 kg which falls through a height of 400mm and drives a cone having a maximum diameter of 20mm (cone angle of. 60 degrees with respect to the horizontal) into the material being used.
Table 2: Consistency of materials when profiled
GRANULAR MATERIALS |  |  |  |  | COHESIVE MATERIALS
CONSISTENCY |  |  |  | DESCRIPTION | CONSISTENCY |  | DESCRIPTION
Very loose |  |  |  | Crumbles very easily when scraped with a geological pick. | Very soft |  | Geological pick head can easily be pushed in as far as the shaft of the handle.
Loose |  |  |  | Small resistance to penetration by sharp end of a geological pick. | Soft |  | Easily dented by thumb; sharp end of a geological pick can be pushed in 30-40 mm; can be moulded by fingers with some pressure.
Medium dense |  |  |  | Considerable resistance to penetration by sharp end of a geological pick. | Firm |  | Indented by thumb with effort; sharp end of geological pick can be pushed in upto 10 mm; very difficult to mould with fingers; can just be penetrated with an ordinary hand spade.
Dense |  |  |  | Very high resistance to penetration by the sharp end of a geological pick; requires many blows for excavation. | stiff |  | Can be indented by thumb-nail; slight indentation produced by pushing geological pick point into soil; cannot be moulded by fingers.
Very dense |  |  |  | High resistance to repeated blows of a geological pick. | Very stiff |  | Indented by thumb-nail' with difficulty; slight indentation produced by blow of a geological pick point.
4 | Trench excavation
All hand excavateable material in trenches having a depth of less than 1,5 metres shall be excavated by hand.
5 | Compaction of backfilling to trenches (areas not subject to traffic)
Backfilling to trenches shall be placed in layers of thickness (before compaction) not exceeding 100mm. Each layer shall be compacted using hand stampers
| a) | to 90% Proctor density;
| b) | such that in excess of 5 blows of a dynamic cone penetrometer (DCP) is required to penetrate 100 mm of the backfill, provided that backfill does not comprise more than 10% gravel of size less than 10mm and contains no isolated boulders, or
| c) | such that the density of the compacted trench backfill is not less than that of the surrounding undisturbed soil when tested comparatively with a DCP.
6 | Excavation
All hand excavateable material including topsoil classified as hand excavateable shall be excavated by hand. Harder material may be loosened by mechanical means prior to excavation by hand.
The excavation of any material which presents the possibility of danger or injury to workers shall not be excavated by hand.
7 | Clearing and grubbing
Grass and small bushes shall be cleared by hand.
8 | Shaping
All shaping shall be undertaken by hand.
9 | Loading
All loading shall be done by hand, regardless of the method of haulage.
10 | Haul
Excavation material shall be hauled to its point of placement by means of wheelbarrows where the haul distance is not greater than 150 m.
11 | Offloading
All material, however transported, is to be off-loaded by hand, unless tipper-trucks are utilised for haulage.
12 | Spreading
All material shall be spread by hand.
13 | Compaction
Small areas may be compacted by hand provided that the specified compaction is achieved.
14 | Grassing
All grassing shall be undertaking by sprigging, sodding, or seeding by hand.
15 | Stone pitching and rubble concrete masonry
All stone required for stone pitching and rubble concrete masonry, whether grouted or dry, must be collected, loaded, off loaded and placed by hand.
Sand and stone shall be hauled to its point of placement by means of wheelbarrows where the haul distance is not greater than 150m.
Grout shall be mixed and placed by hand.
16 | Manufactured Elements
Elements manufactured or designed by the Contractor, such as manhole rings and cover slabs, precast concrete planks and pipes, masonry units and edge beams shall not individually, have a mass of more than 320kg. In addition, the items shall be large enough so that four workers can conveniently and simultaneously acquire a proper handhold on them.
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## EPWP EmpCont
Annexure 10
(Insert Your Company Logo)
(This shall serve as the cover page on employment contracts for local labour)
EMPLOYMENT AGREEMENT
BETWEEN
[CONTRACTOR NAME]...........................
AND
[WORKER NAME].......................................
1. | PARTIES
The Parties to this Agreement are -
| 1.1. | Contractor:
herein represented by:
duly authorised thereto
And
| 1.2. | Mr / Me:
[worker's name]
2. | DEFINITIONS AND INTERPRETATION
| 2.1. | In this Agreement and any Annexure thereto, unless inconsistent with or otherwise indicated by the context-
|  | “Agreement” |  | means the contents of this Agreement.
|  | “Company” |  | means the company that employs the worker
|  | “Department” |  | means the Department of Public Works
|  | “Worker” |  | is a person that performs a specific or necessary task or who completes tasks in a certain way
|  | “EPWP” |  | The Expanded Public Works Programme is a government programme aimed at the alleviation of poverty and unemployment. The programme ensures the full engagement on Labour Intensive Methods of Construction (LIC) to contractors for skills development. The EPWP focuses at reducing unemployment by increasing economic growth by means of improving skills levels through education and training and improving the enabling environment for the industry to flourish.
3. | PURPOSE
The purpose of this agreement is to:-
Ensure that the agreement is binding to both the Worker and the Employer.
4. | TERMS AND CONDITIONS
| ◦ | The worker will have no entitlement to the benefits of a full time employee, namely;
| ◦ | The worker should not have the expectation that this contract will be renewed or extended.
| ◦ | The worker will be subject to all laws, rules, policies, codes and procedures applicable to the;
| ◦ | The worker must meet the standards and requirements of the contractor
| ◦ | The worker must render his/her services during normal working hours of minimum of forty to fifty five hours in any week; which comprise of an eight-hour working day in a five-day week.
5. | REMUNERATION
The worker will receive compensation to the amount of R______________________00 which must be paid by the 25th or on the last day of each month.
6. | ROLES AND RESPONSIBILITIES
| 6.1 | Employer / Worker
| ◦ | Work for ________________________ in terms of the period as specified in the employment agreement contract.
| ◦ | Be available for and participate in all learning and work experience required by the company.
| ◦ | Comply with workplace policies and procedures.
| ◦ | Complete any attendance or any written assessment tools supplied by the contractor to record relevant workplace experience.
| ◦ | Demonstrate willingness to grow and learn through work experience.
Provide the following documentation to the employer,
|  | ▪ | Certified identity document not longer than 3 months
|  | ▪ | ID size photos
|  | ▪ | Sign employment contract
| 6.2 | Employer
| ◦ | Employ the worker for a period specified in the agreement.
| ◦ | Provide the worker with appropriate work based experience in the work environment.
| ◦ | Facilitate payments of wages / stipends.
| ◦ | Keep accurate records of workers.
| ◦ | Where a worker/ learner is disabled, the employer will have to provide in the additional needs e.g. special materials, learning aids and in some cases physical or professional support (such aids remain the property of the employer).
| ◦ | Keep up to date records of learning and discuss progress with the intern on a regular basis.
| ◦ | Apply fair disciplinary, grievance and dispute resolution procedures to the worker.
| ◦ | Prepare an orientation/ induction course to introduce worker/ learner to the workplace and specific workplace requirements.
| ◦ | Ensure the daily attendance register is signed by the worker.
7. DURATION.
This agreement commences on:
and
expires on:
8. BREACH.
If either party commits any breach of the terms of this contract (and fails to rectify it within 30 days of receipt of a written notice calling it to do so, then) the other party shall be entitled to terminate the contract or to claim specific performance without prejudice to any of its other legal rights, including its rights to claim damages.
9. | CONDITIONS OF EMPLOYMENT
| 9.1. | Meal Breaks
| 9.1.1 | A worker may not work for more than five hours without taking a meal break of at least thirty minutes duration.
| 9.1.2 | An employer and worker may agree on longer meal breaks.
| 9.1.3 | A worker may not work during a meal break. However, an employer may require a worker to perform duties during a meal break if those duties cannot be left unattended and cannot be performed by another worker. An employer must take reasonable steps to ensure that a worker is relieved of his or her duties during the meal break.
| 9.1.4 | A worker is not entitled to payment for the period of a meal break. However, a worker who is paid on the basis of time worked must be paid if the worker is required to work or to be available for work during the meal break.
| 9.2. | Special Conditions for Security Guards (Only applicable to security Guards)
| 9.2.1 | A security guard may work up to 55 hours per week and up to eleven hours per day.
| 9.2.2 | A security guard who works more than ten hours per day must have a meal break of at least one hour or two breaks of at least 30 minutes each.
| 9.3. | Weekly Rest Period
Every worker must have two days off every week. A worker may only work on their day off to perform work which must be done without delay and cannot be performed by workers during their ordinary hours of work ("emergency work'').
| 9.4. | Work on Sundays and Public Holidays
| 9.4.1 | A worker may only work on a Sunday or public holiday to perform emergency or security work.
| 9.4.2 | Work on Sundays is paid at the ordinary rate of pay.
| 9.4.3 | A task-rated worker who works on a public holiday must be paid;
|  | (a) | the worker's daily task rate, if the worker works for less than four hours;
|  | (b) | double the worker's daily task rate, if the worker works for more than four hours.
| 9.4.4 | A time-rated worker who works on a public holiday must be paid
|  | (a) | the worker's daily rate of pay, if the worker works for less than four hours on the public holiday;
|  | (b) | double the worker's daily rate of pay, if the worker works for more than four hours on the public holiday.
| 9.5 | Sick leave
| 9.5.1 | Only workers who work more than 24 hours per month have the right to claim sick-pay in terms of this clause.
| 9.5.2 | A worker who is unable to work on account of illness or injury is entitled to claim one day's paid sick leave for every full month that the worker has worked in terms of a contract.
| 9.5.3 | A worker may accumulate a maximum of twelve days' sick leave in a year.
| 9.5.4 | Accumulated sick-leave may not be transferred from one contract to another contract.
| 9.5.5 | An employer must pay a task-rated worker the worker's daily task rate for a day's sick leave.
| 9.5.6 | An employer must pay a time-rated worker the worker's daily rate of pay for a day's sick leave.
| 9.5.7 | An employer must pay a worker sick pay on the worker's usual payday.
| 9.5.8 | Before paying sick-pay, an employer may require a worker to produce a certificate stating that the worker was unable to work on account of sickness or injury if the worker is
|  | (a) | absent from work for more than two consecutive days; or
|  | (b) | absent from work on more than two occasions in any eight-week period.
| 9.5.9 | A medical certificate must be issued and signed by a medical practitioner, a qualified nurse or a clinic staff member authorised to issue medical certificates indicating the duration and reason for incapacity.
| 9.5.10 | A worker is not entitled to paid sick-leave for a work-related injury or occupational disease for which the worker can claim compensation under the Compensation for Occupational Injuries and Diseases Act.
| 9.6. | Maternity Leave
| 9.6.1 | A worker may take up to four consecutive months' unpaid maternity leave.
| 9.6.2 | A worker is not entitled to any payment or employment-related benefits during maternity leave.
| 9.6.3 | A worker must give her employer reasonable notice of when she will start maternity leave and when she will return to work.
| 9.6.4 | A worker is not required to take the full period of maternity leave. However, a worker may not work for four weeks before the expected date of birth of her child or for six weeks after the birth of her child, unless a medical practitioner, midwife or qualified nurse certifies that she is fit to do so.
| 9.6.5 | A worker may begin maternity leave as follows;
|  | (a) | four weeks before the expected date of birth; or
|  | (b) | on an earlier date
(i) if a medical practitioner, midwife or certified nurse certifies that it is necessary for the health of the worker or that of her unborn child; or
(ii) if agreed to between employer and worker; or
|  | (c) | on a later date, if a medical practitioner, midwife or certified nurse has certified that the worker is able to continue to work without endangering her health.
| 10.6 | A worker who has a miscarriage during the third trimester of pregnancy or bears a stillborn child may take maternity leave for up to six weeks after the miscarriage or stillbirth.
| 9.7. | Family responsibility leave
| 9.7.1 | Workers, who work for at least four days per week, are entitled to three days paid family responsibility leave each year in the following circumstances;
|  | (a) | when the employee's child is born;
|  | (b) | when the employee's child is sick;
|  | (c) | in the event of a death of
(i) the employee's spouse or life partner;
(ii) the employee's parent, adoptive parent, grandparent, child, adopted child, grandchild or sibling.
| 9.8. | Keeping Records
| 9.8.1 | Every employer must keep a written record on site for the duration of the project and three (3) year after completion records should consists of at least the following;
|  | (a) | the worker's name and position;
|  | (b) | copy of an acceptable worker identification
|  | (c) | in the case of a task-rated worker the number of tasks completed by the worker;
|  | (d) | in the case of a time-rated worker, the time worked by the worker;
|  | (e) | payments made to each worker in a form of Proof of Payment, Payroll registers and the acknowledgement of payment receipt signed by the worker.
| 9.8.2 | The employer must keep this record for a period of at least three years after the completion of the EPWP.
| 9.9. | Payment
| 9.9.1 | An employer must pay all wages at least monthly in cash or by cheque or into a bank account.
| 9.9.2 | A worker may not be paid less than the Ministerial Determination wage rate.
| 9.9.3 | A task-rated worker will only be paid for tasks that have been completed.
| 9.9.4 | An employer must pay a task-rated worker within five weeks of the work being completed and the work having been approved by the manager or the contractor having submitted an invoice to the employer.
| 9.9.5 | A time-rated worker will be paid at the end of each month.
| 9.9.6 | Payment must be made in cash, by cheque or by direct deposit into a bank account designated by the worker.
| 9.9.7 | Payment in cash or by cheque must take place
|  | (a) | at the workplace or at a place agreed to by the worker;
|  | (b) | during the worker's working hours or within fifteen minutes of the start or finish of work;
|  | (c) | in a sealed envelope which becomes the property of the worker.
| 9.9.8 | An employer must give a worker the following information in writing
|  | (a) | the period for which payment is made;
|  | (b) | the numbers of tasks completed or hours worked;
|  | (c) | the worker's earnings;
|  | (d) | any money deducted from the payment;
|  | (e) | the actual amount paid to the worker.
| 9.9.9 | If the worker is paid in cash or by cheque, this information must be recorded on the envelope and the worker must acknowledge receipt of payment by signing for it.
| 9.9.10 | If a worker's employment is terminated, the employer must pay all monies owing to that worker within one month of the termination of employment.
| 9.10. | Inclement weather
If no work has begun on site, and if an employee has reported for work, the employee will be paid for four hours. Should work be stopped after the first four hours, the employee will be paid for the hours worked. Where the employer has given employees notice on the previous working day that no work will be available due to inclement weather, then no payment will be made.
| 9.11. | Deductions
| 9.11.1 | An employer may not deduct money from a worker's payment unless the deduction is required in terms of a law.
| 9.11.2 | An employer must deduct and pay to the SA Revenue Services any income tax that the worker is required to pay.
| 9.11.3 | An employer who deducts money from a worker's pay for payment to another person must pay the money to that person within the time period and other requirements specified in the agreement of Law; court order or arbitration
| 9.11.4 | It is the responsibility of the employers to arrange for all persons employed on a Project to be covered in terms of the Unemployment Insurance Fund Contributions Act, 2002 (Act No. 4 of 2002)
| 9.11.5 | An employer may not require or allow a worker to
|  | (a) | repay any payment except an overpayment previously made by the employer by mistake;
|  | (b) | state that the worker received a greater amount of money than the employer actually paid to the worker; or
|  | (c) | pay the employer or any other person for having been employed.
| 9.12. | Health and Safety
| 9.12.1 | Employers must take all reasonable steps to ensure that the working environment is healthy and safe.
| 9.12.2 | A worker must;
|  | (a) | work in a way that does not endanger his/her health and safety or that of any other person;
|  | (b) | obey any health and safety instruction;
|  | (c) | use any personal protective equipment or clothing issued by the employer;
|  | (d) | report any accident, near-miss incident or dangerous behaviour by another person to their employer or manager.
| 9.13. | Compensation for Injuries and Diseases
| 9.13.1 | It is the responsibility of the employers to arrange for all persons employed on a Project to be covered in terms of the Compensation for Occupational Injuries and Diseases Act, 130 of 1993 as amended by COIDA Act 61, 1997.
| 9.13.2 | A worker must report any work-related injury or occupational disease to their employer or manager.
| 9.13.3 | The employer must report the accident or disease to the Compensation Commissioner.
| 9.13.4 | An employer must pay a worker who is unable to work because of an injury caused by an accident at work 75% of their earnings for up to three months. The employer will be refunded this amount by the Compensation Commissioner. This does NOT apply to injuries caused by accidents outside the workplace such as road accidents or accidents at home.
| 9.14. | Termination
| 9.14.1 | The employer may terminate the employment of a worker for good cause after following a fair procedure.
| 9.14.2 | A worker will not receive severance pay on termination.
| 9.14.3 | A worker is not required to give notice to terminate employment. However, a worker who wishes to resign should advise the employer in advance to allow the employer to find a replacement.
| 9.14.4 | A worker who is absent for more than three consecutive days without informing the employer of an intention to return to work will have terminated the contract. However, the worker may be re-engaged if a position becomes available.
| 9.14.5 | A worker who does not attend required training events, without good reason, will have terminated the contract. However, the worker may be re-engaged if a position becomes available.
Notice procedure is as follows;
|  | ◦ | One week if employed for four weeks or less
|  | ◦ | Two weeks if employed for more than four weeks but not more than a year
|  | ◦ | Four weeks of employed for one (1) year or more
9.15. Certificate of Service
| 9.15.1 | On termination of employment, a worker is entitled to a certificate stating;
|  | (a) | the worker's full name;
|  | (b) | the name and address of the employer;
|  | (c) | the Project on which the worker worked; the work performed by the worker;
|  | (d) | any training received by the worker;
|  | (e) | the period for which the worker worked on the Project; and
|  | (f) | any other information agreed on by the employer and worker.
9.16. DOMICILE
The address to which notices and all legal documents may be delivered or served are as follows:
Employee Details
Name & Surname:
ID No:
Residential Address:
Contact No:
Date of Employment:
| To be supervised by: |  |  |  | Main Contractor:
| or |  |  |  | Sub Contractor:
| Category of employment: |  |  |  | Skilled:
Semi-skilled:
Unskilled:
For Skilled & Semi-skilled state the trade:
Period of employment: Fixed for until when your services are still required on site
I confirm that I have been inducted and fully understand the condition of my appointment.
| Employee Signature: |  |  |  |  | Witness by SGB/CLO:
Signature by Witness:
Employer Details
Name & Surname:
Designation:
| Contact No: | [5 empty] | Signature:
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## Att Reg
The Attendance Register for on-site Workers
Reporting month: |  |  |  |  | Cell No:
Surname: |  |  |  |  | First Name:
Project Name: | KZN Public Works: 191 Prince Alfred Street
Project Code: | 012345 |  |  |  | Tender No | ZNTM012345W
IDENTITY NUMBER:
Day | Date | Time In | Signature | Time Out | Signature | Report On Any Formal Training Provided In The Reporting Month
WEEK 1
MONDAY
TUESDAY
WEDNESDAY
THURSDAY
FRIDAY
WEEK 2
MONDAY
TUESDAY
WEDNESDAY
THURSDAY
FRIDAY
WEEK 3
MONDAY
TUESDAY
WEDNESDAY
THURSDAY
FRIDAY
WEEK 4
MONDAY
TUESDAY
WEDNESDAY
THURSDAY
FRIDAY
WEEK 5
MONDAY
TUESDAY
WEDNESDAY
THURSDAY
FRIDAY
Total Days worked
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## Registration and Business Form
BUSINESS PLAN
Reference No
Profile ID
Project Name
Project Details
Project Name
Project Reference Number
Project description
Project Start Date
Project End Date
Estimated Budget
Project Location
Province
District/Metro Municipality
Local Municipality/Metro Region
Latitude (in decimal format)
Longitude (in decimal format)
Public Body Details
Public body sphere
Reporting public body that is the project owner (and will report on the project)
Implementing public body type
Public body that will implement the project
IDP reference number allocated to the project
EPWP Details
EPWP Sector
EPWP Program
EPWP Sub programme
Budget Amount
April 2014/March 2015
April 2015/March 2016
Total Budget Amount
Wages
UIF
COIDA
Training
Administration
Equipment and materials
Other
Describe other
Outputs and Training
Output
Despription
Target Quantity
Number of persons to be trained
Contact person
Title
Initials
First Name
Surname
Email
Tel (Office)
Fax Number
Cell Number
Physical Address 1
Physical Address 2
Physical Address 3
Physical Address 4
Postal Address 1
Postal Address 2
Postal Address 3
Postal Address 4
Back to Main Menu
Print
Print Preview
Enter Data

## Beneficiary Monthly captureform
KZN PUBLIC WORKS
Monthly Data collection for LOCAL Labour
Name of Contractor: | [14 empty] | Project Code: |  |  | 012345 |  |  |  | Project location name (area):________________________
Name of Project: |  |  |  | KZN Public Works: 191 Prince Alfred Street | [11 empty] | Reporting month:_______________ | [5 empty] | Project location (Ward No.):_________________
Beneficiary Details | [18 empty] | Experience/Literacy |  |  |  | Location Details |  |  |  | Household Details
No | First Name | Initial | Surname | ID number |  |  |  | D.O.B | Gender F/M | Disability Y/N | Start Date on the current month | End Date on the current month | Total days worked | Job description | Registered on UIF (Y/N) | Registered with COIDA (Y/N) | Are you receiving any Gov grant? (Y/N) | 1st Language | Other Language 1 | Other Language 2 | Education Level (See Codes below) | Highest Level of Education | Address | Ward No. | Cell No. | Nationality | No. of people in Household | No. of Dependants in Household | No. of Children attending school
1
2
3
4
5
6
7
8
9
10
· Education Levels – use the codes (1,2,3) on the excel spreadsheet
|  |  | o (1) Unknown |  |  |  | (3) Grade 1-3 (Sub A – Std 1) | [5 empty] | (5) Grade 5-6 (Std 3-4) ABET 2 |  |  | (7) Grade 9 (Std 7) ABET 4 |  |  | (9) Grade 12 (Std 10)
|  |  | o (2) No Schooling |  |  |  | (4) Grade 4 (Std 2) ABET 1 | [5 empty] | (6) Grade 7-8 (Std 5-6) ABET 3 |  |  | (8) Grade 10-11 (Std 8-9) |  |  | (10) Post Matric
Contractor sign:__________________________________ | [5 empty] | DPW Official/Consultant sign:__________________________________ | [6 empty] | EPWP Official sign:_______________________________________
Designation:_____________________________________ | [5 empty] | Designation:________________________________________ | [6 empty] | Designation:_____________________________________________
Date:____________________________________________ | [5 empty] | Date:_______________________________________________ | [6 empty] | Date:___________________________________________________
Contact no:_______________________________________ | [5 empty] | Contact no:__________________________________________ | [6 empty] | Contact no:______________________________________________
Please do a print preview before printing.
Back to Main Menu
Print Preview
Print
Enter Data

## Worker Monthly Payment upload
KZN PUBLIC WORKS
Worker payment capture form for LOCAL Labour
Name of Contractor: | [6 empty] | Project Code: |  | 012345
Name of Project: |  |  | KZN Public Works: 191 Prince Alfred Street
Reporting month:
Payment Upload
No. | First Name | Initials | Surname | Identity No. | D.O.B | Job Description | Daily Wage Rate | Total Paid Days | Total Amount Paid | Total days Worked Days
1
2
3
4
5
6
7
8
9
10
Contractor sign:___________________________ |  |  |  | DPW Official/Consultant sign:___________________________ |  |  |  | EPWP Official sign:______________________
Designation:___________________________ |  |  |  | Designation:________________________________________ |  |  |  | Designation:____________________________
Date:__________________________________ |  |  |  | Date:__________________________________ |  |  |  | Date:__________________________________
Contact no:___________________________ |  |  |  | Contact no:_____________________________ |  |  |  | Contact no:_____________________________
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## Worker Monthly Training form
KZN PUBLIC WORKS
Worker Training capture form for LOCAL Labour
Name of Contractor: | [7 empty] | Project Code: |  | 012345
Name of Project: |  |  | KZN Public Works: 191 Prince Alfred Street
Reporting month:
Training
No | Name | Surname | ID No. | Job description | Course Name | Was training Accredited or Non - accredited by a relevant SETA | Start date on current month | End date on current month | Training Days Paid | Training Days Not Paid | Total Number of Training Days | Cost per trainee | Is training complete or on - going | Name of Training Provider
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Contractor sign: _________________________ |  |  |  |  | DPW Official/Consultant sign: _____________________ |  |  |  |  | EPWP Official sign: ____________________
Designation: ____________________________________ |  |  |  |  | Designation: ______________________________________________ |  |  |  |  | Designation: __________________________________
Date: __________________________________________ |  |  |  |  | Date: ____________________________________________________ |  |  |  |  | Date: ________________________________________
Contact no: _____________________________________ |  |  |  |  | Contact no: ______________________________________________ |  |  |  |  | Contact no: ___________________________________
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## Location
Location
Locality Name
Municipality
Subplace
Ward
Government Facility
Latitude
Longitude
Physical Address/Location
Please do a print preview before printing.
Back to Main Menu
Print
Print Preview
Enter Data

## B U I L D Data Sheet
B.U.I.L.D: DATA
Section A: Employer Information
cidb Employer Number
Employer Name
Section B: Contract Data
cidb Contract Number
Contract Title
Name of contractor
cidb Contractor Registration (CRS)
Section C: Best Practice Project Fee
|  |  |  | Award Value (Including VAT) | R | [10 empty] |  0 0
Class of Works
[9 empty] | Best Practice Project Fee (%) |  | 0.2%
[7 empty] | Best Practice Project Fee | R | [7 empty] |  0 0
Section D: Compliance with Standard for Developing Skills Through Infrastructure Contracts
|  |  |  | Award Value (Including VAT) | R | [10 empty] |  0 0
Class of Works
Minimum Target Contract Skills Development Goal (%)
[7 empty] | Target Contract Skills Development Goal | R | [7 empty] |  0 0
Section E: Compliance with Standard for Indirect Targeting
|  |  |  | Award Value (Including VAT) | R | [10 empty] |  0 0
Class of Works
[9 empty] | Minimum Indirect Targeting Enterprise Development (%) |  | 5%
[7 empty] | Indirect Targeting Enterprise Developement | R | [7 empty] |  0 0
Section F: Contact Details; Employer's Accounting Officer
|  | Name of Accounting Officer |  |  |  | Title |  |  | Initials |  |  |  |  | Surname
e-mail
[5 empty] | Mobile |  | 0 |  |  | - |  |  |  | -
|  |  | Office Telephone |  |  |  | 0 |  |  | - |  |  |  | -
Section G: Declaration; Employer's Representative
[5 empty] | Name of Representative | Title |  |  |  | Initials |  |  |  |  | Surname
Designation
e-mail
[5 empty] | Mobile | 0 |  |  | - |  |  |  | -
[5 empty] | Office Telephone | 0 |  |  | - |  |  |  | -
[5 empty] | Date | Y | Y | Y | Y | - | M | M | - | D | D
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Employer · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct.
Signature
[5 empty] | Date completed | Y | Y | Y | Y | - | M | M | - | D | D
Notes
Please add any notes / comments as applicable:

## ED101P
cidb B.U.I.L.D PROGRAMME; STANDARD FOR INDIRECT TARGETING PROJECT COMPLETION REPORT To be completed for each qualifying enterprise
Section A: Employer Information
cidb Employer Number
Employer Name
Section B: Main/Lead Contractor / JV Information
cidb Contractor Registration Number of main / lead contractor
Name of contractor
cidb Contractor Registration Number of Joint Venture Partner 1
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 2
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 3
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 4
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 5
Name of contractor /Joint Venture
|  |  |  | Contact Person | Title |  |  |  | Initials |  |  |  |  | Surname
Designation
e-mail
|  |  |  | Mobile | 0 |  |  | - |  |  |  | -
|  |  |  | Office Telephone | 0 |  |  | - |  |  |  | -
Section C: Contract Data
cidb Contract Number
Contract Title
Contract Amount at Award(excluding VAT, including variations and any price adjustment)
|  |  |  | R | [12 empty] | .00
Section D: Compliance with CIDB Standard for Indirect Targeting for Enterprise Development (Complete one per Targeted JV Partner or Targeted Sub-Contractor)
|  |  |  | Targeted JV partner | [6 empty] | or Targeted sub-contractor
cidb Contractor Registration
Name of contractor
|  |  |  | Contact Person | Title |  |  |  | Initials |  |  |  |  | Surname
Designation
e-mail
|  |  |  | Mobile | 0 |  |  | - |  |  |  | -
|  |  |  | Office Telephone | 0 |  |  | - |  |  |  | -
a) Final value of qualifying work undertaken by Targeted Enterprise (excl. VAT, incl. variations and price adjustments):
|  |  |  | R | [12 empty] | .00
b) Contract amount at award of main/lead contract (excl. VAT, incl. variations and price adjustments):
|  |  |  | R | [12 empty] | .00
| Contract participation for targeted enterprise a/b above x 100 = (%) | [13 empty] | %
Was a developmental needs analysis undertaken? (Y/N)
Was a project specific development program with milestones developed? (Y/N)
Was a schedule of activities developed to address the identified development areas? (Y/N)
Were appropriate resources allocated for development? (Y/N)
Were the agreed development targets achieved? (Y/N)
List the areas of development identified (at least two):
Section E: Declaration; Enterprise Development Co-ordinator
|  |  |  | Name of Co-ordinator | Title |  |  |  | Initials |  |  |  |  | Surname
Designation
ID / Passport
e-mail
|  |  |  | Mobile | 0 |  |  | - |  |  |  | -
|  |  |  | Office Telephone | 0 |  |  | - |  |  |  | -
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Main/Lead Contractor / JV; and · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct
Signature
|  |  |  | Date completed | Y | Y | Y | Y | - | M | M | - | D | D
Section F: Declaration; Qualifying Developing Enterprise Representative
|  |  |  | Name of Representative | Y: Title; -: Initials; D: Surname
Designation
ID / Passport
e-mail
|  |  |  | Mobile | Y: 0; Y: -; -: -
|  |  |  | Office Telephone | Y: 0; Y: -; -: -
|  |  | I / we agree | disagree | Y: with the Enterprise Development Co-ordinator's asessment of compliance with the Enterprise Development support provided
[11 empty] | I / we appeal the assessment by the Enterprise Development Co-ordinator | Y | N
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Targeted Enterprise · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct
Signature
|  |  |  | Date completed | Y | Y | Y | Y | - | M | M | - | D | D
Section G: Declaration; Employer's Representative
|  |  |  | Name of Representative | Y: Title; -: Initials; D: Surname
Designation
ID / Passport
e-mail
|  |  |  | Mobile | Y: 0; Y: -; -: -
|  |  |  | Office Telephone | Y: 0; Y: -; -: -
|  |  | I / we agree | disagree | Y: with the Enterprise Development Co-ordinator's asessment of compliance with the Enterprise Development support provided
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Employer · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct
Signature
|  |  |  | Date completed | Y | Y | Y | Y | - | M | M | - | D | D
Section H: cidb Official Use Only
cidb Contract Number

## ED102P
cidb B.U.I.L.D PROGRAMME; STANDARD FOR INDIRECT TARGETING APPEAL FOR REVIEW OF ASSESSMENT OF ENTERPRISE DEVELOPMENT SUPPORT
Section A: Employer Information
cidb Employer Number
Employer Name
Section B: Contract Data
cidb Contract Number
Employer's contract number
Contract Title
|  | Date of application for appeal | Y | Y | Y | Y | ─ | M | M | ─ | D | D
Section C: Main Contractor / JV Information
cidb Contractor Registration Number of main / lead contractor
Name of contractor /Joint Venture
Section D: Qualifying Developing Enterprise
cidb Contractor Registration
Name of contractor
Section E: Reason for Appeal / Review
We, the undersigned, are not in agreement with the assessment of the enterprise development support provided:
(Please indicate each performance criteria seperately and provide the reasons for an appeal.)
Section E: Declaration
I, the undersigned warrant that: · I am duly authorised to submit this notice to the cidb on behalf of the Developing Enterprise / Employer * (* Delete which is not applicable) · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct · I hereby authorise the cidb to make such enquiries as necessary to verify the information contained on this form
Signature
Name (please print)
Position
|  | Date completed | Y | Y | Y | Y | - | M | M | - | D | D
Section F: cidb Official Use Only
cidb Contract Number

## ED104P
cidb B.U.I.L.D PROGRAMME; STANDARD FOR INDIRECT TARGETING TARGETED ENTERPRISE DECLARATION To be completed for each targeted enterprise
Section A: Employer Information
cidb Employer Number
Employer Name
Section B: Contract Data
cidb Contract Number
Contract Title
[5 empty] | Date of Practical Completion | Y | Y | Y | Y |  | M | M |  | D | D
Contract Amount at Award(Inclusive of VAT)
[5 empty] | R | [12 empty] | .00
Section C: Main/Lead Contractor / JV Information
cidb Contractor Registration Number of main / lead contractor
Name of contractor
cidb Contractor Registration Number of Joint Venture Partner 2
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 3
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 4
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 5
Name of contractor /Joint Venture
e-mail
[5 empty] | Mobile | 0 |  |  | - |  |  |  | -
[5 empty] | Office Telephone | 0 |  |  | - |  |  |  | -
Section D: Targeted Enterprise Information
[5 empty] | JV partner |  |  |  |  | or sub-contractor
cidb Contractor Registration
Name of contractor
[5 empty] | Contact Person | Title |  |  |  | Initials |  |  |  |  | Surname
Designation
e-mail
[5 empty] | Mobile | 0 |  |  | - |  |  |  | -
[5 empty] | Office Telephone | 0 |  |  | - |  |  |  | -
Number of full time employees other than the owner
Section D(i): Shareholding by cidb Registered Contractors (Targeted Enterprise)
| Name | [8 empty] | cidb registration | [6 empty] | Equity (%)
Section D (ii): Ownership by Black Persons of Targeted Enterprise (Complete for each person)
|  | Name | Title |  | Initials |  |  |  |  | Surname
ID or Passport
e-mail
Citizenship
|  |  |  | by birth |  |  | or by decent |  |  |  |  | or by naturalisation
[12 empty] | year of naturalisation | Y | Y | Y | Y
|  | Name | Title |  | Initials |  |  |  |  | Surname
ID or Passport
e-mail
Citizenship
|  |  |  | by birth |  |  | or by decent |  |  |  |  | or by naturalisation
[12 empty] | year of naturalisation | Y | Y | Y | Y
|  | Name | Title |  | Initials |  |  |  |  | Surname
ID or Passport
e-mail
Citizenship
|  |  |  | by birth |  |  | or by decent |  |  |  |  | or by naturalisation
[12 empty] | year of naturalisation | Y | Y | Y | Y
|  | Name | Title |  | Initials |  |  |  |  | Surname
ID or Passport
e-mail
Citizenship
|  |  |  | by birth |  |  | or by decent |  |  |  |  | or by naturalisation
[12 empty] | year of naturalisation | Y | Y | Y | Y
Section E: Agreed Areas of Developmental Support
List the areas of development identified (at least two):
Section F: Contract Participation Goal (CPG) for Targeted Enterprise
a) Final value of qualifying work undertaken by Targeted Enterprise (excl. VAT, incl. variations and any price adjustment):
[5 empty] | R | [12 empty] | .00
b) Contract amount at award of main contract (excl.VAT, incl. variations and any price adjustment):
[5 empty] | R | [12 empty] | .00
[14 empty] | CPG for targeted enterprise a/b (above) x 100 = (%) of work sub-contracted |  |  | %
Section G: Declaration; Enterprise Development Co-ordinator
[5 empty] | Name of Co-ordinator | Title |  |  |  | Initials |  |  |  |  | Surname
Designation
ID / Passport
e-mail
[5 empty] | Mobile | 0 |  |  | - |  |  |  | -
[5 empty] | Office Telephone | 0 |  |  | - |  |  |  | -
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Main/Lead Contractor / JV; and · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct
Signature
[5 empty] | Date completed | Y | Y | Y | Y | - | M | M | - | D | D
Section H: Declaration; Targeted Enterprise Representative
[5 empty] | Name of Representative | Y: Title; -: Initials; D: Surname
Designation
ID / Passport
e-mail
[5 empty] | Mobile | Y: 0; Y: -; -: -
[5 empty] | Office Telephone | Y: 0; Y: -; -: -
|  |  | I / we agree |  | disagree | Y: with the Enterprise Development Co-ordinator's asessment of compliance with the Enterprise Development support provided
[12 empty] | I / we appeal the assessment by the Enterprise Development Co-ordinator | Y | N
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Targeted Enterprise · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct
Signature
[5 empty] | Date completed | Y | Y | Y | Y | - | M | M | - | D | D
Section I: Declaration; Employer's Representative
[5 empty] | Name of Representative | Y: Title; -: Initials; D: Surname
Designation
ID / Passport
e-mail
[5 empty] | Mobile | Y: 0; Y: -; -: -
[5 empty] | Office Telephone | Y: 0; Y: -; -: -
|  |  | I / we agree |  | disagree | Y: with the Enterprise Development Co-ordinator's asessment of compliance with the Enterprise Development support provided
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Employer · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct
Signature
[5 empty] | Date completed | Y | Y | Y | Y | - | M | M | - | D | D

## ED105P
cidb B.U.I.L.D PROGRAMME; STANDARD FOR INDIRECT TARGETING PROJECT INTERIM REPORT To be completed for each qualifying enterprise
Section A: Employer Information
cidb Employer Number
Employer Name
Section B: Main/Lead Contractor / JV Information
cidb Contractor Registration Number of main / lead contractor
Name of contractor
cidb Contractor Registration Number of Joint Venture Partner 1
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 2
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 3
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 4
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 5
Name of contractor /Joint Venture
[5 empty] | Contact Person | Title |  |  |  | Initials |  |  |  |  | Surname
Designation
e-mail
[5 empty] | Mobile | 0 |  |  | - |  |  |  | -
[5 empty] | Office Telephone | 0 |  |  | - |  |  |  | -
Section C: Contract Data
cidb Contract Number
Contract Title
Contract Amount at Award(Inclusive of VAT)
[5 empty] | R | [12 empty] | .00
Section D: Report on Development Areas
Development Area 1:
Provide information on the milestones achieved as the development plan for the reporting period.
(Attach development plan)
Development Area 2:
Provide information on the milestones achieved as the development plan for the reporting period.
(Attach development plan)
Section E: Compliance with the CIDB Standard for Indirect Targeting for Enterprise Development (Complete one per Targeted Enterprise)
[5 empty] | Targeted JV partner | [6 empty] | or Targeted sub-contractor |  |  | (Please tick)
cidb Contractor Registration
Name of contractor
[5 empty] | Contact Person | Title |  |  |  | Initials |  |  |  |  | Surname
Designation
e-mail
[5 empty] | Mobile | 0 |  |  | - |  |  |  | -
[5 empty] | Office Telephone | 0 |  |  | - |  |  |  | -
a) Current value of work completed by Targeted Enterprise (excl.VAT, incl. variations and any price adjustment):
[5 empty] | R | [12 empty] | .00
b) Contract amount awarded to Targeted Enterprise (excl. VAT, incl. variations and any price adjustment):
[5 empty] | R | [12 empty] | .00
| Contract participation for targeted enterprise a/b above x 100 =(%) | [14 empty] | %
Was a developmental needs analysis undertaken? (Y/N)
Was a project specific development program with milestones developed? (Y/N)
Was a schedule of activities developed to address the identified development areas? (Y/N)
Are appropriate resources allocated for development? (Y/N)
Are the agreed development targets being achieved? (Y/N)
Section F: Declaration; Enterprise Development Co-ordinator
[5 empty] | Name of Co-ordinator | Title |  |  |  | Initials |  |  |  |  | Surname
Designation
ID / Passport
e-mail
[5 empty] | Mobile | 0 |  |  | - |  |  |  | -
[5 empty] | Office Telephone | 0 |  |  | - |  |  |  | -
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Main / Lead Contractor / JV; and · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct
Signature
[5 empty] | Date completed | Y | Y | Y | Y | - | M | M | - | D | D
Section G: Declaration; Targeted Enterprise Representative
[5 empty] | Name of Representative | Y: Title; -: Initials; D: Surname
Designation
ID / Passport
e-mail
[5 empty] | Mobile | Y: 0; Y: -; -: -
[5 empty] | Office Telephone | Y: 0; Y: -; -: -
|  |  | I / we agree |  | disagree | Y: with the Enterprise Development Co-ordinator's asessment of compliance with the Enterprise Development support provided
[12 empty] | I / we appeal the assessment by the Enterprise Development Co-ordinator | Y | N
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Targeted Developing Enterprise · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct
Signature
[5 empty] | Date completed | Y | Y | Y | Y | - | M | M | - | D | D
Section H: Declaration; Employer's Representative
[5 empty] | Name of Representative | Y: Title; -: Initials; D: Surname
Designation
ID / Passport
e-mail
[5 empty] | Mobile | Y: 0; Y: -; -: -
[5 empty] | Office Telephone | Y: 0; Y: -; -: -
|  |  | I / we agree |  | disagree | Y: with the Enterprise Development Co-ordinator's asessment of compliance with the Enterprise Development support provided
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Employer · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct
Signature
[5 empty] | Date completed | Y | Y | Y | Y | - | M | M | - | D | D

## A3_Project Training Report
FORM A3: PROJECT INTERIM TRAINING REPORT
Section A: Employer Information
cidb Employer Number
Employer Name
Section B: Contract Data
cidb Contract Number
Contract Title
Tender Value (R)
Contract Skills Development Goal (R)
SIP Number (If Applicable)
SIP Project Code (If Applicable)
SECTION C:Definitions and Beneficiary Information
Training Methods:
Method 1(M1): structured workplace learning opportunities for learners towards the attainment of a part or a full occupational qualification;
Method 2(M2): structured workplace learning opportunities for apprentices or other artisan learners towards the attainment of a trade qualification leading to a listed trade subject to at least 60% of the artisan learners being holders of public TVET college qualifications;
Method 3(M3): work integrated learning opportunities for University of Technology or Comprehensive University students completing their national diplomas;
Method 4(M4): structured workplace learning opportunities for candidates towards registration in a professional category by a statutory council listed in Table 1 in the CIDB Standard for Developing Skills Through Infrastructure Contracts Gazette No. 43495
Learner/Candidates Full Name and Surname |  | Gender |  | Ethnic Group |  |  |  |  | Identity Number | [12 empty] | Training Method (Please tick) |  |  |  | Placement Start Date | Placement End Date | Occupation/Trade Description | Description of Practical Task Completed (as per logbook or POE) | Status | Supporting documents available on request (Yes,No or N/A)
|  | Male | Female | Black | White | Coloured | Indian | Other | [13 empty] | M1 | M2 | M3 | M4 | [5 empty] | Training Plan | Attendance Register | Signed Logbooks/POE | Entry Medical Assessments | Exit Medical Assessment | Conducted Sumative Assessment | Site Induction | Health and Saftey Induction | Registered with Relevant SETA | PPE Register | Register Beneficiaries with CIDB SDA
Eg. Xolani Smith |  | 1 |  |  |  | 1 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 4 | 5 | 6 | 8 | 9 | 1 |  | X |  |  | 2021-06-01 | 2021/09/31 | Bricklaying | Read and interpret drawings | Completed | Yes | Yes | Yes | Yes | N/A | No | Yes | Yes | No | Yes | Yes
[29 empty] | Set out building as per drawing | In progress
[29 empty] | Transfer levels using dumpy level | In progress
[29 empty] | Batch and mix concrete | Completed
Section D: Declaration; Contractor Representative
[7 empty] | Name of Contractor Rep | Title | 4: Initials; 5: Surname
Designation
e-mail
[7 empty] | Mobile | 0 | bar: 3; 7
[7 empty] | Office Telephone | 0 | bar: 3; 7
[7 empty] | Date | Y | Y | Y | Y | - | M | M | - | D | D
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Contractor · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct.
Signature
[7 empty] | Date completed | Y | Y | Y | Y | - | M | M | - | D | D
Section E: Declaration; Employer's Representative
[7 empty] | Name of Representative | Y: Title; -: Initials; D: Surname
Designation
e-mail
[7 empty] | Mobile | Y: 0; Y: -; -: -
[7 empty] | Office Telephone | Y: 0; Y: -; -: -
[7 empty] | Date | Y | Y | Y | Y | - | M | M | - | D | D
I, the undersigned warrant that: · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct.
Signature
[7 empty] | Date completed | Y | Y | Y | Y | - | M | M | - | D | D

## A5_Final Training Report
FORM A5: FINAL TRAINING REPORT
Section A: Employer Information
cidb Employer Number
Employer Name
Section B: Contract Data
cidb Contract Number
Contract Title
Tender Value (R)
Contract Skills Development Goal (R)
SIP Number (If Applicable)
SIP Project Code (If Applicable)
SECTION C:Definitions and Beneficiary Information
Training Methods:
Method 1(M1): structured workplace learning opportunities for learners towards the attainment of a part or a full occupational qualification;
Method 2(M2): structured workplace learning opportunities for apprentices or other artisan learners towards the attainment of a trade qualification leading to a listed trade subject to at least 60% of the artisan learners being holders of public TVET college qualifications;
Method 3(M3): work integrated learning opportunities for University of Technology or Comprehensive University students completing their national diplomas;
Method 4(M4): structured workplace learning opportunities for candidates towards registration in a professional category by a statutory council listed in Table 1 in the CIDB Standard for Developing Skills Through Infrastructure Contracts Gazette No. 43495
Learner/Candidates Full Name and Surname |  | Gender |  | Ethnic Group |  |  |  |  | Identity Number | [12 empty] | Training Method (Please tick) |  |  |  | Placement Start Date | Placement End Date | Placement Duration | Occupation/Trade Description | Description of Practical Task Completed (as per logbook or POE) | Status | Supporting documents available on request (Yes,No or N/A)
|  | Male | Female | Black | White | Coloured | Indian | Other | [13 empty] | M1 | M2 | M3 | M4 | [6 empty] | Training Plan | Attendance Register | Signed Logbooks/POE | Entry Medical Assessments | Exit Medical Assessments | Conducted Sumative Assessment | Site Induction | Health and Saftey Induction | Registered with Relevant SETA | PPE Register | Register Beneficiaries with CIDB SDA
Eg. Xolani Smith |  | 1 |  |  |  | 1 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 4 | 5 | 6 | 8 | 9 | 1 |  | X |  |  | 2021-06-01 | 2021/09/31 |  | Bricklaying | Read and interpret drawings | Completed | Yes | Yes | Yes | Yes | Yes | N/A | Yes | Yes | No | Yes | Yes
[30 empty] | Set out building as per drawing | In progress
[30 empty] | Transfer levels using dumpy level | In progress
[30 empty] | Batch and mix concrete | Completed
Section D: Declaration; Contractor Representative
[7 empty] | Name of Contractor Rep | Title | 4: Initials; 5: Surname
Designation
e-mail
[7 empty] | Mobile | 0 | bar: 3; 7
[7 empty] | Office Telephone | 0 | bar: 3; 7
[7 empty] | Date | Y | Y | Y | Y | - | M | M | - | D | D
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Contractor · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct.
Signature
[7 empty] | Date completed | Y | Y | Y | Y | - | M | M | - | D | D
Section E: Declaration; Employer's Representative
[7 empty] | Name of Representative | Y: Title; -: Initials; D: Surname
Designation
e-mail
[7 empty] | Mobile | Y: 0; Y: -; -: -
[7 empty] | Office Telephone | Y: 0; Y: -; -: -
[7 empty] | Date | Y | Y | Y | Y | - | M | M | - | D | D
I, the undersigned warrant that: · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct.
Signature
[7 empty] | Date completed | Y | Y | Y | Y | - | M | M | - | D | D

## SD101P
cidb PROJECT ASSESSMENT SCHEME: STANDARD FOR DEVELOPING SKILLS PROJECT COMPLETION REPORT
Section A: Employer Information
cidb Employer Number
Employer Name
Section B: Contractor / JV Information
cidb Contractor Registration Number of main / lead contractor
Name of contractor
cidb Contractor Registration Number of Joint Venture Partner 2
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 3
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 4
Name of contractor /Joint Venture
[5 empty] | Contact Person | Title |  |  |  | Initials |  |  |  |  | Surname
Designation
e-mail
[5 empty] | Mobile | 0 |  |  | - |  |  |  | -
[5 empty] | Office Telephone | 0 |  |  | - |  |  |  | -
Section C: Contract Data
cidb Contract Number
Contract Title
|  |  |  | Tender Value at Award (excl. VAT) | R | [14 empty] | .00
Section D: Compliance with Contract Skills Development Goal (CSDG)
|  |  |  | Tender Sub-total (excl. VAT) | R | [13 empty] |  0 0
Class of Works
[9 empty] | Minimum Target Contract Skills Development Goal (%) | 0 
[7 empty] | Target Contract Skills Development Goal | R | [10 empty] |  0 0
[7 empty] | Contract Skills Development Goal Achieved | R | [10 empty] |  0 0
Target Contract Skills Development Goal achieved (%)
Section E: Construction Skills Development Goal Training Achieved
| Training Method |  |  |  |  | No. Unemployed |  |  |  | No. Employed |  |  |  | Duration (Months) |  |  |  | Contract Skills Development Goal (%)
Method 1 (Skills Programme)
Method 2 (TVET & Apprentice)
Method 3 (P1& P2)
Method 4 (Candidacy)
Total (%)
Section F: Actual Training Records (Complete One per beneficiary or attach pdf copy of signed Form A5 Final Training Report)
[5 empty] | Beneficiary |  | Initials |  |  |  | Surname
ID
|  |  | Gender |  |  |  |  | M | F
|  |  | Ethinic Group |  |  |  |  | A | I | C | W | Other
[5 empty] | Period of Engagement in Project |  | From | Y | Y | Y | Y | - | M | M | - | D | D
[7 empty] | To | Y | Y | Y | Y | - | M | M | - | D | D
[5 empty] | Training Method |  | From To: M1; Y Y: M2; M M: M3; D D: M4
[10 empty] | Employed | [5 empty] | Unemployed
Employer (where applicable)
Section F(i) Complete for a Professional Service Contract only (one per beneficiary)
Total hours
[5 empty] | Beneficiary |  | From To: Initials; Y Y: Surname
ID
Gender | bar: Y Y to Y Y
|  |  | Ethinic Group |  |  |  | Y Y: A; Y Y: I; Y Y: C; Y Y: W; - -: Other
[5 empty] | Period of Engagement in Project |  | From | Y | Y | Y | Y | - | M | M | - | D | D
[7 empty] | To | Y | Y | Y | Y | - | M | M | - | D | D
[5 empty] | Training Method |  | From To: M1; Y Y: M2; M M: M3; D D: M4
[10 empty] | Employed | [5 empty] | Unemployed
Employer (where applicable)
Total hours
Section G: Contact Details; Employer's Accounting Officer
|  | Name of Accounting Officer |  |  |  | Title | Y Y: Initials; M M: Surname
e-mail
[5 empty] | Mobile |  | From To: 0; Y Y: -; M M: -
|  |  | Office Telephone |  |  |  | From To: 0; Y Y: -; M M: -
Section H: Declaration; Employer's Representative
[5 empty] | Name of Representative | Title | Y Y: Initials; - -: Surname
Designation
e-mail
[5 empty] | Mobile | 0 | bar: Y Y; M M
[5 empty] | Office Telephone | 0 | bar: Y Y; M M
[5 empty] | Date | Y | Y | Y | Y | - | M | M | - | D | D
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Employer · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct.
Signature
[5 empty] | Date completed | Y | Y | Y | Y | - | M | M | - | D | D
Please attach pdf copy of signed Form A5 Final Training Report

## SD102P
cidb PROJECT ASSESSMENT SCHEME: STANDARD FOR DEVELOPING SKILLS NOTIFICATION OF THE ISSUE OF THE CANCELLATION / TERMINATION OF A CONTRACT
Section A: Employer Information
cidb Employer Number
Employer Name
Section B: Contractor / JV Information
cidb Contractor Registration Number of main / lead contractor
Name of contractor
cidb Contractor Registration Number of Joint Venture Partner 2
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 3
Name of contractor /Joint Venture
cidb Contractor Registration Number of Joint Venture Partner 4
Name of contractor /Joint Venture
|  |  |  | Contact Person | Title |  |  |  | Initials |  |  |  |  | Surname
Designation
e-mail
|  |  |  | Mobile | 0 |  |  | - |  |  |  | -
|  |  |  | Office Telephone | 0 |  |  | - |  |  |  | -
Section C: Contract Data
cidb Contract Number
Contract Title
|  |  | Final Tender Sum | R | [12 empty] | .00
|  |  |  | Date of cancellation / termination | Y | Y | Y | Y | ─ | M | M | ─ | D | D
Section D: Actual Training Costs Achieved
| Actual training costs achieved |  |  | R | [11 empty] | . 0 0
Section E: Actual Training Records (Complete One per beneficiary or attach pdf copy of signed Form A5 Final Training Report)
|  |  |  | Beneficiary | Y: Initials; M: Surname
ID
Gender | bar: Y to Y
|  | Ethinic Group |  |  | Y: A; Y: I; ─: C; M: W; M: Other
|  |  |  | Period of Engagement in Project |  | From | Y | Y | Y | Y | - | M | M | - | D | D
[6 empty] | To | Y | Y | Y | Y | - | M | M | - | D | D
|  |  |  | Training Method |  | From To: M1; Y Y: M2; M M: M3; D D: M4
[9 empty] | Employed | [5 empty] | Unemployed
Employer (where applicable)
Section E(i) Complete for a Professional Service Contract only (one per beneficiary)
Total hours
|  |  |  | Beneficiary |  | From To: Initials; Y Y: Surname
ID
Gender | bar: Y Y to Y Y
|  | Ethinic Group |  |  |  | Y Y: A; Y Y: I; Y Y: C; Y Y: W; - -: Other
|  |  |  | Period of Engagement in Project |  | From | Y | Y | Y | Y | - | M | M | - | D | D
[6 empty] | To | Y | Y | Y | Y | - | M | M | - | D | D
|  |  |  | Training Method |  | From To: M1; Y Y: M2; M M: M3; D D: M4
[9 empty] | Employed | [5 empty] | Unemployed
Employer (where applicable)
Total hours
Section F: Declaration; Employer's Representative
|  |  |  | Name of Representative | Title | Y Y: Initials; - -: Surname
Designation
e-mail
|  |  |  | Mobile | 0 | bar: Y Y; M M
|  |  |  | Office Telephone | 0 | bar: Y Y; M M
|  |  |  | Date | Y | Y | Y | Y | - | M | M | - | D | D
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Employer · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct.
Signature
|  |  |  | Date completed | Y | Y | Y | Y | - | M | M | - | D | D
Please attach pdf copy of signed Form A5 Final Training Report
cidb Official Use Only
cidb Contract Number

## SD104P
cidb PROJECT ASSESSMENT SCHEME: STANDARD FOR DEVELOPING SKILLS PROJECT TRAINING PLAN
Section A: Employer Information
cidb Employer Number
Employer Name
Section B: Contractor / JV Information
cidb Contractor Registration Number of main / lead contractor
Name of contractor
[6 empty] | Contact Person | Title |  |  |  | Initials |  |  |  |  | Surname
Designation
e-mail
[6 empty] | Mobile | 0 |  |  | - |  |  |  | -
[6 empty] | Office Telephone | 0 |  |  | - |  |  |  | -
Section C: Tender Data
cidb Contract Number
Contract Title
Section D:Contract Skills Development Goal (GSDG)
[5 empty] | Tender Sub-total (excl. VAT) | R | [12 empty] |  0 0
Class of Works
Minimum Target Contract Skills Development Goal (%)
[8 empty] | Target Contract Skills Development Goal | R | [9 empty] |  0 0
[8 empty] | Contract Skills Development Goal Planned | R | [9 empty] |  0 0
Section E: Budgeted Training Hours (Professional Services only)
|  |  | 0,015 / 100 x Tender Sub-total (excl.VAT) | [13 empty] | Hours
Section F: Construction Skills Development Goal Training Plan
| Training Method | [5 empty] | No. Unemployed |  |  |  | No. Employed |  |  |  | Duration (Months) |  |  | Contract Skills Development Goal (%)
Method 1 (Skills Programme)
Method 2 (TVET & Apprentice)
Method 3 (P1& P2)
Method 4 (Candidacy)
Total (%)
Section G: Contact Details; Employer's Accounting Officer
|  | Name of Accounting Officer |  |  |  |  | Title |  |  | Initials |  |  |  |  | Surname
e-mail
[6 empty] | Mobile |  | 0 |  |  | - |  |  |  | -
|  |  |  | Office Telephone |  |  |  | 0 |  |  | - |  |  |  | -
Section H: Declaration; Employer's Representative
[6 empty] | Name of Representative | Title |  |  |  | Initials |  |  |  |  | Surname
Designation
e-mail
[6 empty] | Mobile | 0 |  |  | - |  |  |  | -
[6 empty] | Office Telephone | 0 |  |  | - |  |  |  | -
[6 empty] | Date | Y | Y | Y | Y | - | M | M | - | D | D
I, the undersigned warrant that: · I am duly authorised to submit this notice on behalf of the Employer · The contents of this notice are within my personal knowledge, and are to the best of my belief both true and correct.
Signature
[6 empty] | Date completed | Y | Y | Y | Y | - | M | M | - | D | D
Please attach pdf copy of signed Form A2 Baseline Training Plan